## COVER
GREATER LETABA MUNICIPALITY
SDBIP FIRST QUARTER
PERFORMANCE REPORT
2013/2014

## INDEX
Table of Contents
Introduction | 3
Legislation | 3
Methodology and Contents | 4
Strategic Vision, Mission and Strategy Map | 5
Votes and Operational Objectives | 6
Municipal Transformation and Organisational Development KPI's | 7 to 9
Municipal Transformation and Organisational Development Projects | 10 to 10
Basic Service Delivery Projects | 11 to 22
Local Economic Development Projects | 23 to 23
Municipal Financial Viability KPI's | 24 to 24
Municipal Financial Viability Projects | 25 to 25
Good Governance and Public Participation KPI's | 26 to 28
Good Governance and Public Participation Projects | 29 to 31
Capital Worksplan | 31 to 34
Approval | 35 to 35

## INTR AND LEGISLATION
Introduction | The development, implementation and monitoring of a Service Delivery and Budget Implementation Plan (SDBIP) is required by the Municipal Finance Management Act (MFMA). In terms of Circular 13 of National Treasury, “the SDBIP gives effect to the Integrated Development Plan (IDP) and budget of the municipality and will be possible if the IDP and budget are fully aligned with each other, as required by the MFMA.” As the budget gives effect to the strategic priorities of the municipality it is important to supplement the budget and the IDP with a management and implementation plan. The SDBIP serves as the commitment by the Municipality, which includes the administration, council and community, whereby the intended objectives and projected achievements are expressed in order to ensure that desired outcomes over the long term are achieved and these are implemented by the administration over the next twelve months.
The SDBIP provides the basis for measuring performance in service delivery against quarterly targets and implementing the budget based on monthly projections. Circular 13 further suggests that “the SDBIP provides the vital link between the mayor, council (executive) and the administration, and facilitates the process for holding management accountable for its performance. The SDBIP is a management, implementation and monitoring tool that will assist the mayor, councillors, municipal manager, senior managers and community.” The purpose of the SDBIP is to monitor the execution of the budget, performance of senior management and achievement of the strategic objectives set by council. It enables the municipal manager to monitor the performance of senior managers, the mayor to monitor the performance of the municipal manager, and for the community to monitor the performance of the municipality.
In the interests of good governance and better accountability, the SDBIP should therefore determine and be aligned with the performance agreements of the municipal manager and senior managers. The development, implementation and monitoring of a Service Delivery and Budget Implementation Plan (SDBIP) is required by the Municipal Finance Management Act (MFMA). In terms of Circular 13 of National Treasury, “the SDBIP gives effect to the Integrated Development Plan (IDP) and budget of the municipality and will be possible if the IDP and budget are fully aligned with each other, as required by the MFMA.”
Legislation | According to the Municipal Finance Act (MFMA) the definition of a SDBIP is: 'service delivery and budget implementation plan' means a detailed plan approved by the mayor of a municipality in terms of section 53 (1) (c) (ii) for implementing the municipality's delivery of municipal services and its annual budget, and which must indicate- (a) projections for each month of- (i) revenue to be collected, by source; and (ii) operational and capital expenditure, by vote; (b) service delivery targets and performance indicators for each quarter; Section 53 of the MFMA stipulates that the Mayor should approve the SDBIP within 28 days after the approval of the budget. The Mayor must also ensure that the revenue and expenditure projections for each month and the service delivery targets and performance indicators as set out in the SDBIP are made public within 14 days after their approval.
The following National Treasury prescriptions as minimum requirements that must form part of the SDBIP are applicable to the Municipality : (1) Monthly projections of revenue to be collected by source (2) Monthly projections of expenditure (operating and capital) and revenue for each vote * (3) Quarterly projections of service delivery targets and performance indicators for each vote (4) Ward information for expenditure and service delivery (5) Detailed capital works plan broken down per ward for three years * Section 1 of the MFMA defines a “vote” as: a) one of the main segments into which a budget of a municipality is divided for the appropriation of money for the different departments or functional areas of the municipality; and b) which specifies the total amount that is appropriated for the purposes of the department or functional area concerned

## METHODOLOGY AND CONTENT
Methodology and Content | National Treasury directives are clear on the contents and methodology to derive at the SDBIP. As a first step, the IDP objectives need to be quantified and related into key performance indicators. The budget is aligned to the objectives, projects and activities to enable the SDBIP to serve as monitoring tool for service delivery. The SDBIP is describes as a layered plan. The top layer deals with consolidated service delivery targets and time frames. Top Management is held accountable for the implementation of the consolidated projects and Key Performance Indicators. From the consolidated information, top management is expected to develop the next level of detail by breaking up outputs into smaller outputs and then linking and assigning responsibility to middle-level and junior managers.
The SDBIP of the Greater Letaba Municipality consists of Strategic Objectives derived from the IDP that are aligned with the strategic intent of the organisation. Strategic indicators with targets are set to measure the objectives. The Municipal Manager takes responsibility for the Strategic Indicators and Objectives which will form part of his Performance Agreement and Plan. Projects and activities are aligned to the indicators with quarterly targets, time-frame and budget assigned to each. The Strategic Indicators give rise to the Institutional Indicators for which the Directors will take responsibility. These indicators will form part of the Performance Agreements and Plans of Senior Managers (Directors). Indicators are assigned quarterly targets and responsibilities to monitor performance. Derived from this, the next layer is developed, whereby the details with responsibilities for the next level of management is outlined and forms part of the Lower SDBIP. This lower SDBIP is a management tool for the S57 Managers and need not be made public and is a separate document for each internal department. The SDBIP serves as a management, implementation and monitoring tool that will assist the Mayor, Councilors, Municipal Manager and Directors in delivering services to the community

## STRATEGY
Vision and Mission | The strategic vision of the organisation sets the long term goal the Municipality wants to achieve. The vision of Greater Letaba Municipality is: "To be an outstanding agro-processing and eco-cultural tourism hub. The strategic Mission Speaks about what the purpose of Greater Letaba Municipality is: The mission of Greater Letaba Municipality is to ensure an effective, efficient and economically viable municipality through: Provision of accountable, transparent, consultative and co-operative governance Improving the quality of life through economic development and poverty alleviation Provision of sustainable services Ensuring a safe and healthy environment
Strategy map | The Strategy Map depicts the Strategic Objectives on how Greater Letaba Municipality will be able to become an outstanding agro-processing and eco-cultural tourism hub while providing sustainable and affordable services to all. These objectives were positioned in terms of the Balanced Scorecard Perspectives being: Learning and Growth; Institutional Processes; Financial results and Community Satisfaction. All operational outputs (projects, initiatives and process) as contained within the SDBIP are aligned to the attainment of one or more of these objectives.

## OPERATIONAL STRATEGIES
Votes and Operational objectives | Votes | Objectives and Targets
| Municipal Manager Office (Vote 040) | To lead, direct and manage a motivated and inspired Administration and account to the Greater Letaba Municipal Council as Accounting Officer for long term Municipal sustainability to achieve a good creditor rating within the requirements of the relevant legislation and whereas the following sections within the department, i.e. HIV/Aids, Youth, Disabled and Gender Desk, Communication and Internal Auditing is managed for integration, economic growth, marginalised poverty alleviation, efficient, economic and effective communication and service delivery.
| Finance (Vote 050) | To secure sound and sustainable management of the financial affairs of Greater Letaba Municipality by managing the budget and treasury office and advising and if necessary assisting the accounting officer and other directors in their duties and delegation contained in the MFMA. Ensuring that the Greater Letaba Municipality is 100% financially viable when it comes to Cost Coverage and to manage the Grant Revenue of the municipality so that no grant funding is foregone
| Community Services (Vote 028) | To co-ordinate Environmental Health Services, Sports Arts and culture, Education, Libraries, Safety and security, Environmental and Waste management, Health and Social development programmes as well as Disaster management to decrease community affected by disasters
| Infrastructure Development and Economic Planning (Votes 029 and 022) | To ensure that the service delivery requirements for roads are met and maintenance of water, sewerage and electricity are conducted for access to basic services as well as no less than an average of 100% MIG expenditure
To direct the Greater Letaba Municipality’s resources for advanced economic development and investment growth through appropriate town and infrastructure planning in order that an environment is created whereby all residents will have a sustainable income.
| Corporate Services (Vote 046 ) | To ensure efficient and effective operation of council services, human resources and management, legal services and the provision of high quality customer orientated administrative systems. Ensuring 100% compliance to the Skills Development Plan

## MTOD KPI's
KPA 1 MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT
KEY PERFORMANCE INDICATORS
OUTCOME NINE (OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING, PLANNING AND SUPPORT, OUTPUT 4: ACTIONS SUPPORTIVE OF THE HUMAN SETTLEMENT OUTCOMES)
Vote Nr | Strategic Objective | Programmes | Measurable Objectives | Performance measures | Baseline / Status | Budget 2013/2014 | 1st Quarter target | Progress to date | Challenges | Intervetions | Expenditure | Responsible Person
50 | Improved Quality of Life | Indigent Management | To ensure that all indigent groups are registered in the indigent register | Indigent registered (# of qualified indigent /# of indigent applicants) | 100% | Operational | 100% | 1712 of qualified indigents/3625 of indigent applications (47%) registered. | Information on indigents applications is not made available and accessible to pontential beneficials | To conduct awarness by way of posters, flyers and local radio stations | Operational | CFO
22 | Integrated Sustainable Development | IDP | To ensure that draft IDP, budget and PMS are done within the legislation framework. | Draft IDP, budget and PMS adopted by 31 March 2014 | Adopted by 31 May 2014 | Operational | n/a | n/a | None | n/a | Operational | INDEP/CFO/MM
22 | Integrated Sustainable Development | IDP | To adopt Final IDP, budget and PMS within the legislation framework. | Final IDP, budget and PMS adopted by 31 March 2014 | Adopted by 31 May 2014 | Operational | n/a | n/a | None | n/a | Operational | INDEP/CFO/MM
22 | Integrated Sustainable Development | IDP | To review, drive and monitor implementation of the IDP by 31 May 2014 | % achievement of milestones on IDP/Budget/PMS process plan. | 100% | Operational | 25% | 20% | Strategic planning was not conducted as per schedule | To conduct strategic planning by the second quarter | Operational | INDEP/MM
22 | Integrated and Sustainable Human Settlement | Spatial Planning | To ensure proper housing coordination to submit Database to COGHSTA by the 31 December 2013 | House demand database submitted within timeframe | Database submitted to COGHSTA by the 31 December 2013 | Operational | n/a | n/a | None | n/a | Operational | INDEP
22 | Integrated and Sustainable Human Settlement | Spatial Planning | To ensure proper land use management 30 June 2014 | % land use applications processed (# of applications processed / # of land use applications received) | 100% | Operational | 100% | 100% | Unavailability of land for development | Negotiating with owners and other stakeholders for release | Operational | INDEP
22 | Integrated and Sustainable Human Settlement | Annual Report | To compile the Draft Annual Report and submit to council by 31 December 2013 | Draft Annual Report adopted by Council on 31 December 2013 | Draft Annual Report adopted by Council on 31 December 2013 | Operational | n/a | n/a | None | n/a | Operational | MM/ All Directors
33 | Improved Governance and Organisational Excellence | Annual Report | To compile the Final Annual Report and submit to council by 31 January 2014 | Final Annual Report approved by council on 31 January 2014 | Final Annual Report approved by council on 31 January 2014 | Operational | n/a | n/a | None | n/a | Operational | MM / All Directors
33 | Improved Governance and Organisational Excellence | SDBIP | To ensure that the SDBIP is done within the legislated framework | SDBIP approved by Mayor 28 days after adoption of budget/ IDP/PMS | SDBIP approved by Mayor 28 days after adoption of budget/IDP/PMS | Operational | n/a | n/a | None | n/a | Operational | PMS/MM
54 | Improved Governance and Organisational Excellence | OPMS | To ensure annual implementation of the performance management system in the organisation | # Quarterly performance reports submitted to Council | 4 | Operational | 1 | 1 | None | n/a | Operational | PMS/MM
54 | Improved Governance and Organisational Excellence | EPMS | To ensure that S54 & S56 Managers sign the performance agreement within legislated framework. | # S54 & S56 staff with signed performance agreements | 5 | Operational | 5 | S54 & S56 performance agreements were signed | 2 x S56 positions are vacant | The two posts were advertised and one has been shortlisted | Operational | MM
54 | Improved Governance and Organisational Excellence | EPMS | To ensure implementation of the performance management system in the organisation | Annual formal assessments (S57) for 2012/2013 conducted | 1 | Operational | 1 | Annual formal Assessment will be done during the 2nd quarter of the current financial year after we receiving the AG report. | None | n/a | Operational | PMS/MM
54 | Improved Governance and Organisational Excellence | Internal Audit | To ensure functionality of Audit committee | # of meetings held | 4 | Operational | 1 | 1 Audit committee meeting was held | None | n/a | Operational | Internal Audit /MM
54 | Improved Governance and Organisational Excellence | Risk | To ensure functionality of Risk committee. | # of meetings held | 4 | Operational | 1 | Risk committee was established in the last previous FY and schedule of meetings was submitted to the chairperson for inputs.The Chairperson has already met the Risk Officer and Accounting Officer | None | n/a | Operational | Risk/MM
54 | Improved Governance and Organisational Excellence | CORPS | To ensure functionality of Council committees. | # of meetings held | 6 | Operational | 1 | 2 Community Services Councils committee meetings were held.1 Corporate and shared services meeting was held.1 Extended finance meeting was held.5 Infrastructure and development portfolio committees were held. | None | n/a | Operational | CORPS/MM
| Improved Governance and Organisational Excellence | CORPS | To ensure functionality of Exco committee | # of meetings held | 6 | Operational | 1 | 1 Exco meeting was held | None | n/a | Operational | CORPS/MM
54 | Improved Governance and Organisational Excellence | EPMS | To ensure implementation of the performance management system in the organisation | Mid Year formal assessment (S57) for 2013/2014 conducted | 1 | Operational | n/a | n/a | None | n/a | Operational | PMS/MM
54 | Improved Governance and Organisational Excellence | Internal Audit | To assess and evaluate the municipal performance information | # of performance audit reports issued | 4 | Operational | 1 | 1st quarter peformance audit report to be served in the 1st ordinary quarterly Council meeting. | None | n/a | Operational | Internal Audit
54 | Improved Governance and Organisational Excellence | Internal Audit | To develop the 3 year internal audit plan | % approval of internal audit plan and implementation. | 1 | Operational | 100% | Internal audit plan was approved with corrections recommeded by the Audit Committee. Recruitment and selection audit is at draft report stage and overtime audit is at execution stage. Performance audit and QFS audit to be finalised in the 2nd quarter. | None | n/a | Operational | MM
54 | Improved Governance and Organisational Excellence | Operation clean audit | To attain Clean Audit by ensuring compliance to all governance; financial management and reporting requirements by 2014 | # of Internal Audit issues resolved versus # of issues raised | 30 | Operational | 100% | Operational | none | n/a | Operational | All Directors/MM
54 | Improved Governance and Organisational Excellence | Operation clean audit | To attain Clean Audit by ensuring compliance to all governance; financial management and reporting requirements by 2014 | # of Auditor General issues resolved versus # of issues raised | 63 issues raised | Operational | 0 | Out of 63 queries, 49 were addressed which constitute 78% and the remaining ones will be determined by the outcome of the Audit report. | None | n/a | Operational | All Directors/MM
54 | Improved Governance and Organisational Excellence | Risk management | To ensure efffective implementation of risk mitigations actions June 2014. | # Risk issues implemented / resolved versus # of risks identified | 10 | Operational | 100% | Out of 52 operational risks identified,21 risks were addressed in the quarter under review | None | None | Operational | Risk/MM

## MTOD PROJECTS
KPA 1 MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT PROJECTS
OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING, PLANNING AND SUPPORT, OUTPUT 4: ACTIONS SUPPORTIVE OF THE HUMAN SETTLEMENT OUTCOMES
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project / Initiative | Budget 2013/2014 | Start Date | Completion Date | Milestones Qtr Ending Sept 13 | Progress to date | Challenges | Interventions | Expenditure | Project Owner
54 | Improved Governance and Organisational Excellence | Furniture & Equipment | To purchase 6 fax machines, 2 steel filing cabinets, 6 photocopy machines, 2 mobile units and 3 flip chartboards | Fax machines (6), steel filing cabinets (2), photocopy machines (6), mobile units (2) and flip chartboards (3) | 155000 | 01/10/2013 | 31/03/2014 | n/a | n/a | None | n/a | n/a | CORPS
54 | Improved Governance and Organisational Excellence | Furniture & Equipment | To purchase office furniture | Office furniture | 1200000 | 01/10/2013 | 30/06/2014 | n/a | n/a | None | n/a | n/a | CORPS
39 | Improved Governance and Organisational Excellence | Information Technology | To purchase colour printer 4, laptops 10 and computers 5 | Colour printer 4, laptops 10 and computers 5 | 300000 | 01/10/2013 | 30/06/2014 | n/a | n/a | None | n/a | n/a | CORPS
54 | Improved Governance and Organisational Excellence | Furniture & Equipment | To purchase 5 aqua coolers | Aqua coolers (5) and camera | 8000 | 01/01/2014 | 31/03/2014 | n/a | n/a | None | n/a | n/a | CORPS
54 | Improved Governance and Organisational Excellence | Property Services | To purchese filling cabinet for PMS Office | Filling Cabinet for PMS Office | 10000 | 01/01/2014 | 31/03/2014 | n/a | n/a | None | n/a | n/a | CORPS
54 | Improved Governance and Organisational Excellence | Property Services | Building of counter at registry office | Building a counter for registry | 20000 | 01/10/2013 | 31/03/2014 | n/a | n/a | None | n/a | n/a | CORPS
54 | Improved Governance and Organisational Excellence | Property Services | Purchasing of printer for registry, shredding machine, conventional tent, tables 2 and fax machine | Printer for registry, shredding machine, conventional tent (gazebo), tables 2 and fax machine | 78000 | 01/10/2013 | 31/03/2014 | n/a | n/a | None | n/a | n/a | CORPS
54 | Improved Governance and Organisational Excellence | Property Services | Purchasing of mobile filing cabinet | Mobile filing cabinet | 60000 | 01/10/2013 | 31/03/2014 | n/a | n/a | None | n/a | n/a | CORPS
54 | Improved Governance and Organisational Excellence | Property Services | To install mounted projectors for Mayor and MM's boardrooms; and Council Chamber | Projectors for boardrooms and Council Chamber | 100000 | 01/10/2013 | 31/03/2014 | n/a | n/a | None | n/a | n/a | CORPS
54 | Integrated Sustainable Development | IDP | To review the IDP | IDP Review | Operational | 01/07/2013 | 30/06/2014 | Adoption of IDP/BUDGET/PMS process plan.Conduct strategic planning session | The IDP/Budget/PMS process plan was adopted by Council. | Not adhering to the procurement process plan | The strategic planning session is scheduled for October 2013 | Operational | INDEP/PMS
54 | Improved Governance and Organisational Excellence | SDBIP | To review the SDBIP | SDBIP Review | Operational | 01/07/2013 | 30/06/2014 | n/a | n/a | None | n/a | Operational | MM
54 | Improved Governance and Organisational Excellence | Bursary Scheme | To fund good performing student from needy families | Bursary Scheme | 1056570 | 01/07/2013 | 30/06/2014 | Payment of costs | 31 of 32 student bursaries had been paid for (97%) | 1 student fees has not been paid in full due to outstanding documentation | In communication with the University | n/a | MM
54 | Improved Governance and Organisational Excellence | Risk Management | To train the risk committee | Risk Committee Training | 118272 | 01/07/2013 | 31/12/2013 | Preparation for the workshop | The risk committee was trained on the 25 June 2013 | None | n/a | n/a | MM
54 | Improved Governance and Organisational Excellence | Risk Management | To develop risk management startegy | Development and implementation of Risk Assessment Strategy | 59136 | 01/07/2013 | 31/12/2013 | Assess and evaluate current strategy to ensure relevance | n/a | None | n/a | n/a | MM
54 | Improved Governance and Organisational Excellence | OHS | To purchase and install signs and posters at offices | OHS Signs and posters | 50000 | 01/10/2013 | 31/03/2014 | n/a | n/a | None | n/a | n/a | CORPS
54 | Improved Governance and Organisational Excellence | OHS | Purchase and distribute safety clothing to employees | Protective Clothing | 40000 | 01/10/2013 | 31/03/2014 | n/a | Specification stage | None | n/a | n/a | CORPS
46 | Improved Human Resource | Skills Development | To develop the WSP by 30 June 2014 | Workplace Skills Plan | 300000 | 01/07/2013 | 30/06/2014 | Identification of gaps and collection of information | n/a | None | n/a | n/a | CORPS
39 | Improved Governance and Organisational Excellence | Information Technology | Networking of Kgapane, Senwamokgope and Mokwakwaila sub-offices | Networking of sub-offices | 250000 | 01/10/2013 | 31/12/2013 | n/a | n/a | None | n/a | n/a | CORPS
39 | Improved Governance and Organisational Excellence | Information Technology | Upgrading of Information Technology System | Network upgrade | 200000 | 01/10/2013 | 31/03/2014 | n/a | n/a | None | n/a | n/a | CORPS
39 | Improved Governance and Organisational Excellence | Information Technology | Develop maintenance Plan for all IT Systems | Maintenance Plan for all IT Systems | 100000 | 01/10/2013 | 31/03/2014 | n/a | n/a | None | n/a | n/a | CORPS
39 | Improved Governance and Organisational Excellence | Internal Audit | Purchase and install teamate Software (Internal Audit) | Teamate Software (Internal Audit) | 200000 | 01/10/2013 | 31/03/2014 | n/a | n/a | None | n/a | n/a | MM
39 | Improved Governance and Organisational Excellence | Human Resources | Purchase and Install bullet proof class at Customer Care office | security features at Customer Care office | 60000 | 01/10/2013 | 31/03/2014 | n/a | n/a | None | n/a | n/a | CORPS
39 | Improved Governance and Organisational Excellence | Human Resources | Purchasing and pasting of office signage and labels | Office signage and labelling | 60000 | 01/10/2013 | 31/03/2014 | n/a | n/a | None | n/a | n/a | CORPS
39 | Improved Governance and Organisational Excellence | Human Resources | To develop employees satisfaction survey | Employees satisfaction survey | Operational | 01/07/2013 | 30/06/2014 | Develop questionnaire | Operational | Operational | n/a | Operational | CORPS
39 | Improved Governance and Organisational Excellence | Human Resources | To develop ghost verification plan | Ghost verification | Operational | 01/10/2013 | 31/12/2013 | n/a | Operational | Operational | n/a | Operational | CORPS
39 | Improved Governance and Organisational Excellence | Human Resource | To review delegation of powers and functions | Review delegation of powers and functions | Operational | 01/10/2013 | 30/06/2014 | n/a | Operational | Operational | n/a | Operational | MM/ All Directors

## BSD PROJECTS
KPA 2 BASIC SERVICE DELIVERY AND INFRASTRUCTURE KEY PERFORMANCE INDICATORSPROJECTS OUTCOME NINE (OUTPUT 2: IMPROVING ACCESS TO BASIC SERVICES, OUTPUT 3: IMPLEMENTATION OF THE COMMUNITY WORK PROGRAMME)
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project / Initiative | Budget 2013/2014 | Start Date | Completion Date | Milestones Qtr Ending Sept 13 | Progress to date | Challenges | Interventions | Expenditure | Project Owner
54 | Access to Sustainable Basic Services | Property Services | To purchase 8 air conditioners by 30 June 2014. | Air Conditioners | 60000 | 01/01/2014 | 30/06/2014 | n/a | Ahead of target. Specifications have been submitted to SCM unit in the first quarter | None | n/a | n/a | INDEP/CFO/MM
54 | Access to Sustainable Basic Services | Property Services | Construction of security Gate at DLTC Modjadjiskloof by 31 March 2014 | Security Gate at DLTC Modjadjiskloof | 20000 | 01/10/2013 | 31/03/2014 | n/a | n/a | None | n/a | n/a | COMM
54 | Access to Sustainable Basic Services | Property Services | The renovation of Municipal Workshop by 30 June 2014 | Renovation of Municipal Workshop | 500000 | 01/01/2014 | 30/06/2014 | n/a | Ahead of target. Specifications have been submitted to SCM unit in the first quarter | None | n/a | n/a | INDEP
54 | Access to Sustainable Basic Services | Community Facilities | Construction of Rotterdam Community Hall by 30 June 2014 | Rotterdam Community Hall | 2400000 | 01/10/2013 | 30/06/2014 | n/a | Allocation of land for implementation of the project remains the challenge | None | n/a | n/a | INDEP
54 | Access to Sustainable Basic Services | Street Lighting | Erection of 16 highmass lights at Phooko, Moroatshehla, Thakgalang, Mapaana, Shamfana, Mmamokgadi, Malematja and Mamphakathi villages by 31 March 2014 | Highmass lights in villages | 4800000 | 01/10/2013 | 31/03/2014 | n/a | Ahead of target. Specifications have been submitted to SCM unit in the first quarter | None | n/a | n/a | INDEP
54 | Access to Sustainable Basic Services | Sports and Recreation | Construction of Ga-Kgapane Parks (Below Civic Centre and Mesopotamia) by 31 March 2014 | Construction of Ga-Kgapane Parks | 2600000 | 01/07/2013 | 31/03/2014 | Submission of specifications and advertisement for service providers | Specification submitted to SCM | None | n/a | n/a | COMM
31 | Access to Sustainable Basic Services | Sports and Recreation | Enhancement & Beautification of Modjadjiskloof Town Entrances by 31 March 2014 | Enhancement & Beautification of Town Entrances | 300000 | 01/07/2013 | 31/03/2014 | Obtain quotations from Architectures and start with designs | Specification submitted to SCM | None | n/a | n/a | COMM
39 | Access to Sustainable Basic Services | Vehicle Licencing and Test | Purchasing of Traffic signs by 31 December 2013 | Traffic Signs | 100000 | 01/07/2013 | 31/12/2013 | Develop specifications and submit to supply chain. | Specification submitted to SCM | None | n/a | n/a | COMM
39 | Access to Sustainable Basic Services | Vehicle Licencing and Test | Purchasing of Uniform for Traffic Interns by 31 December 2013 | Uniform for Traffic Interns | 100000 | 01/07/2013 | 31/12/2013 | Submission of specifications to SCM. Advertisement for service providers | Specification submitted to SCM | None | n/a | n/a | COMM
34 | Improved Local Economy | Sports and Recreation | To organise SAIMSA games by 31 December 2013 | SAIMSA games | 500000 | 01/07/2013 | 31/12/2013 | GLM soccer, netball and Pool teams to compete in SAIMSA games | GLM didn't compete in SAIMSA games | The committee failed to finalised the policy | Development of the policy | n/a | CORPS
31 | Access to Sustainable Basic Services | Sports and Recreation | Construction of 3 outdoor gyms at GaKgapane, Modjadjiskloof and Senwamokgope by 30 June 2014 | Outdoor gyms (3) | 1500000 | 01/10/2013 | 30/06/2014 | n/a | n/a | None | n/a | n/a | COMM
34 | Access to Sustainable Basic Services | Waste Management | To procure compactor for refuse collection by 31 March 2014 | Compactor | 500000 | 01/10/2013 | 31/03/2014 | n/a | n/a | None | n/a | n/a | COMM
34 | Access to Sustainable Basic Services | Waste Management | Construction of 3 x transfer stations by 30 June 2014 | Transfer stations | 1800000 | 01/07/2013 | 30/06/2014 | Develop specifications and submit to SCM | Specification submitted to SCM | None | n/a | n/a | COMM
34 | Access to Sustainable Basic Services | Waste Management | To procure 14 skip bins by 31 March 2014 | Skip bins (14) | 350000 | 01/10/2013 | 31/03/2014 | n/a | n/a | None | n/a | n/a | COMM
34 | Access to Sustainable Basic Services | Library Services | To procure versa trolleys by 31 March 2014 | Versa trolleys | 50000 | 01/10/2013 | 31/03/2014 | n/a | Specification submitted to SCM | None | n/a | n/a | COMM
34 | Access to Sustainable Basic Services | Waste Management | To procure skip truck by 31 March 2014 | Skip truck | 900000 | 01/10/2013 | 31/03/2014 | n/a | n/a | None | n/a | n/a | COMM
34 | Access to Sustainable Basic Services | Waste Management | To procure bakkie for waste management by 31 March 2014 | Waste bakkie | 250000 | 01/10/2013 | 31/03/2014 | n/a | n/a | None | n/a | n/a | COMM
34 | Access to Sustainable Basic Services | Waste Management | Construction of municipal landfill site by 30 June 2014 | Landfill site | 10000000 | 01/01/2014 | 30/06/2014 | n/a | n/a | None | n/a | n/a | COMM
29 | Access to Sustainable Basic Services | Road and Stormwater | To construct bridge at Ga-Kgapane Stadium by 30 June 2014 | Ga-Kgapane Stadium Bridge | 5800000 | 01/07/2013 | 30/06/2014 | Appoint consultant and completion of designs. | Consultants have been appointed and designs have been completed | None | n/a | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | To construct a bridge to Shawela graveyard by 30 June 2014 | Shawela Bridge | 5200000 | 01/07/2013 | 30/06/2014 | Appoint consultant and completion of designs. | Consultants have been appointed and designs have been completed | None | n/a | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | To purchase two (2) graders by 31 March 2014 | Graders | 5400000 | 01/10/2013 | 31/03/2014 | n/a | Ahead of target. Specifications have been submitted to SCM unit in the first quarter | None | n/a | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | To purchase water cart for roads maintenance by 31 March 2014 | Water Cart | 600000 | 01/10/2013 | 31/03/2014 | n/a | Ahead of target. Specifications have been submitted to SCM unit in the first quarter | None | n/a | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | To purchase TLB (Backhoe Loader) for roads maintenance by 31 March 2014 | TLB (Backhoe loader) | 682000 | 01/10/2013 | 31/03/2014 | n/a | Ahead of target. Specifications have been submitted to SCM unit in the first quarter | None | n/a | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | To purchase a tipper truck by 31 March 2014 | Tipper truck | 620000 | 01/10/2013 | 31/03/2014 | n/a | Ahead of target. Specifications have been submitted to SCM unit in the first quarter | None | n/a | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | To purchase bulldozer by 31 March 2014 | Bulldozer | 2600000 | 01/10/2013 | 31/03/2014 | n/a | Ahead of target. Specifications have been submitted to SCM unit in the first quarter | None | n/a | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Design of 2,2 km streets from gravel to paving blocks at Mothobeki by 31 March 2014 | Mothobeki Street Paving | 450000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to SCM | On target. Terms of reference have been developed and submitted to SCM unit | None | n/a | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Design of 2,2 km streets from gravel to paving blocks at Mamaila Phaphadi by 31 March 2014 | Mamaila Phaphadi Street Paving | 450000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to SCM | On target. Terms of reference have been developed and submitted to SCM unit | None | n/a | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Design of 1,1 km streets from gravel to paving blocks at Phooko Headkraalby 31 March 2014 | Phooko Headkraal Street Paving | 320000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to SCM | On target. Terms of reference have been developed and submitted to SCM unit | None | n/a | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Design of 2,2 km streets from gravel to paving blocks at Raphahlelo Headkraal by 31 March 2014 | Raphahlelo Street Paving | 450000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to SCM | On target. Terms of reference have been developed and submitted to SCM unit | None | n/a | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of streets from gravel to paving blocks at Jamela village for 1,8 km by 31 March 2014 | Jamela Street Paving | 3600000 | 01/07/2013 | 31/03/2014 | Appoint contractor to resume with construction work | Not on target. Tenders closed on 13 September 2013 and await evaluation. | There are delays in procurement processes. | Adherence to procurement plan | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of streets from gravel to paving blocks at Sedibeng village for 2,5 km by 31 March 2014 | Sedibeng Street Paving | 6000000 | 01/07/2013 | 31/03/2014 | Appoint contractor to resume with construction work | Not on target. Tenders closed on 13 September 2013 and await evaluation. | There are delays in procurement processes. | Adherence to procurement plan | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of streets from gravel to paving blocks at Sefofotse village for 1,8km by 31 March 2014 | Sefofotse Street Paving | 3600000 | 01/07/2013 | 31/03/2014 | Appoint contractor to resume with construction work | Not on target. Tenders closed on 13 September 2013 and await evaluation. | There are delays in procurement processes. | Adherence to procurement plan | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of streets from gravel to paving blocks at Rotterdam (Duvula) for 1,2km by 31 March 2014 | Rotterdam (Duvula) Street Paving | 3200000 | 01/07/2013 | 31/03/2014 | Appoint contractor to resume with construction work | Not on target. Tenders closed on 13 September 2013 and await evaluation. | There are delays in procurement processes. | Adherence to procurement plan | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of streets from gravel to paving blocks at Mamaila Kolobetona for 1,2 km by 31 March 2014 | Mamaila Kolobetona Street Paving | 3200000 | 01/07/2013 | 31/03/2014 | Appoint contractor to resume with construction work | Not on target. Tenders closed on 13 September 2013 and await evaluation. | There are delays in procurement processes. | Adherence to procurement plan | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of streets from gravel to paving blocks at Rotterdam (Mahonsi) for 0,7 km by 31 March 2014 | Rotterdam (Mahonsi) Street Paving | 2000000 | 01/07/2013 | 31/03/2014 | Appoint contractor to resume with construction work | Not on target. Tenders closed on 13 September 2013 and await evaluation. | There are delays in procurement processes. | Adherence to procurement plan | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of streets from gravel to paving blocks at Medingen for 2,0 km by 31 March 2014 | Medingen Street Paving | 5500000 | 01/07/2013 | 31/03/2014 | Appoint contractor to resume with construction work | Not on target. Tenders closed on 13 September 2013 and await evaluation. | There are delays in procurement processes. | Adherence to procurement plan | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of streets from gravel to paving blocks at Matswi for 1,8 km by 31 March 2014 | Matswi Street Paving | 4600000 | 01/07/2013 | 31/03/2014 | Appoint contractor to resume with construction work | Not on target. Tenders closed on 13 September 2013 and await evaluation. | There are delays in procurement processes. | Adherence to procurement plan | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | To improve access to existing taxi rank at Mokwakwaila for 1km by 30 June 2014 | Access road to Mokwakwaila Taxi Rank | 3100000 | 01/07/2013 | 30/06/2014 | Develop terms of reference and advertise for consultant | Not on target. Terms of reference were submitted to SCM for advertisement at end July 2013. | There are delays in procurement processes. | Adherence to procurement plan | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Construction of gabions at Uitzicht street, Modjadjiskloof by by 30 June 2014 | Modjadjiskloof Gabions | 1000000 | 01/07/2013 | 30/06/2014 | Develop terms of reference and advertise for consultant | Not on target. Terms of reference were submitted to SCM for advertisement in mid September 2013. | There are delays in procurement processes. | Adherence to procurement plan | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of Hill and Kerk Streets from gravel to tar for 0,8km by 30 June 2014 | Upgrading of Hill and Kerk Streets | 2800000 | 01/07/2013 | 30/06/2014 | Completion of designs for approval by Municipality. | On target. Designs have been completed and tender document submitted to SCM for advertisement for contractors | There are delays in procurement processes. | Adherence to procurement plan | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Construction of sidewalks at Ga-Kgapane streets for 6km by 30 June 2014 | Ga-Kgapane Sidewalks | 2500000 | 01/07/2013 | 30/06/2014 | Develop specifications and submit to SCM. Advertise for construction | Not on target. Terms of reference were submitted to SCM for advertisement at end July 2013. | There are delays in procurement processes. | Adherence to procurement plan | n/a | INDEP
34 | Access to Sustainable Basic Services | Vehicle licencing and testing | To purchase Traffic bakkie by 31 March 2014 | Traffic Bakkie | 250000 | 01/10/2013 | 31/03/2014 | n/a | n/a | None | n/a | n/a | COMM
34 | Access to Sustainable Basic Services | Vehicle licencing and testing | To purchase Traffic Sedan by 31 March 2014 | Traffic Sedan | 250000 | 01/10/2013 | 31/03/2014 | n/a | n/a | None | n/a | n/a | COMM
34 | Access to Sustainable Basic Services | Vehicle licencing and testing | To purchase 6 stop watches by 31 March 2014 | Stop Watches (6) | 5000 | 01/10/2013 | 31/03/2014 | n/a | n/a | None | n/a | n/a | COMM
34 | Access to Sustainable Basic Services | Vehicle licencing and testing | To procure road marking machine by 31 March 2014 | Road marking machine | 150000 | 01/10/2013 | 31/03/2014 | n/a | n/a | None | n/a | n/a | COMM
52 | Access to Sustainable Basic Services | Electricity Distribution | To install maximum demand metering by 31 March 2014 | Maximum demand metering | 1200000 | 01/07/2013 | 31/03/2014 | Advertisement for contractors | On target. The consulting engineers have been appointed on turn-key basis | None | n/a | n/a | INDEP
52 | Access to Sustainable Basic Services | Electricity Distribution | To upgrade electricty network at Modjadjiskloof to NER standard - NER Compliance by 30 June 2014 | Upgrading electricty network to NER standard | 1200000 | 01/07/2013 | 30/06/2014 | Develop specifications and submit to SCM. Advertise for construction | Not on target. Terms of reference were submitted to SCM for advertisement in mid September 2013. | There are delays in procurement processes. | Adherence to procurement plan | n/a | INDEP
52 | Access to Sustainable Basic Services | Electricity Distribution | Purchasing of bakkie for electricity maintenance by 31 March 2014 | Electricity Bakkie | 300000 | 01/10/2013 | 31/03/2014 | n/a | Ahead of target. Specifications have been submitted to SCM unit in the first quarter | None | n/a | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of streets from gravel to paving blocks at Thakgalang for 2,0 km by 31 March 2014 | Thakgalang Street Paving | 5400000 | 01/07/2013 | 31/03/2014 | Appoint contractor to resume with construction work | Not on target. Tenders closed on 13 September 2013 and await evaluation. | There are delays in procurement processes. | Adherence to procurement plan | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of streets from gravel to paving blocks at Rapitsi for 0,7 km by 31 March 2014 | Rapitsi Street Paving | 1800000 | 01/07/2013 | 31/03/2014 | Appoint contractor to resume with construction work | Not on target. Tenders closed on 13 September 2013 and await evaluation. | There are delays in procurement processes. | Adherence to procurement plan | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of streets from gravel to paving blocks at Sekgopo for 1,0 km by 31 March 2014 | Sekgopo Street Paving | 2700000 | 01/07/2013 | 31/03/2014 | Appoint contractor to resume with construction work | Not on target. Tenders closed on 13 September 2013 and await evaluation. | There are delays in procurement processes. | Adherence to procurement plan | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of streets from gravel to paving blocks at Mandela Park for 1,8 km by 31 March 2014 | Mandela Park Street Paving | 3600000 | 01/07/2013 | 31/03/2014 | Appoint contractor to resume with construction work | Not on target. Tenders closed on 13 September 2013 and await evaluation. | There are delays in procurement processes. | Adherence to procurement plan | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of streets from gravel to paving blocks at Modjadji Headkraal for 1,8 km by 31 March 2014 | Modjadji Headkraal Street Paving | 4900000 | 01/07/2013 | 31/03/2014 | Appoint contractor to resume with construction work | Not on target. Tenders closed on 13 September 2013 and await evaluation. | There are delays in procurement processes. | Adherence to procurement plan | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Design of 3.0 km Ga-Kgapane Streets from gravel to paving blocks by 31 March 2014 | Ga-Kgapane Streets Upgrading | 500000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to SCM | On target. Terms of reference have been developed and submitted to SCM unit | None | n/a | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Design of 1,8 km Senwamokgope Streets from gravel to paving blocks by 31 March 2014 | Senwamokgope Streets Upgrading | 500000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to SCM | On target. Terms of reference have been developed and submitted to SCM unit | None | n/a | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Design of 2 km Modjadji Valley Streets from gravel to paving blocks by 31 March 2014 | Modjadji Valley Streets Upgrading | 400000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to SCM | On target. Terms of reference have been developed and submitted to SCM unit | None | n/a | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Design of 1,2 km streets from gravel to paving blocks at Kuranta by 31 March 2014 | Kuranta Street Paving | 400000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to SCM | On target. Terms of reference have been developed and submitted to SCM unit | None | n/a | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Design of 2 km streets from gravel to paving blocks at Mokgoba by 31 March 2014 | Mokgoba Street Paving | 400000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to SCM | On target. Terms of reference have been developed and submitted to SCM unit | None | n/a | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Design of 2 km streets from gravel to paving blocks at Ratjeke by 31 March 2014 | Ratjeke Street Paving | 400000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to SCM | On target. Terms of reference have been developed and submitted to SCM unit | None | n/a | n/a | INDEP
29 | Access to Sustainable Basic Services | Community Facilities | Construction of market stalls at Maphalle by 31 March 2014 | Maphalle Market Stalls | 500000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to SCM | On target. Terms of reference have been developed and submitted to SCM unit | None | n/a | n/a | INDEP
29 | Access to Sustainable Basic Services | Community Facilities | Design of Library for contruction at Senwamokgope by 31 March 2014 | Senwamokgope Library | 250000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to SCM | On target. Terms of reference have been developed and submitted to SCM unit | None | n/a | n/a | INDEP
29 | Access to Sustainable Basic Services | Community Facilities | Design of Library for contruction at Sekgopo by 31 March 2014 | Sekgopo Library | 250000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to SCM | On target. Terms of reference have been developed and submitted to SCM unit | None | n/a | n/a | INDEP
29 | Access to Sustainable Basic Services | Community Facilities | Upgrading and renovation of Kgapane Stadium by 30 June 2014 | Ga-Kgapane Stadium | 1000000 | 01/07/2013 | 30/06/2014 | Advertisement for contractors | On target. Memorandum of request was approved by the MM. | None | n/a | n/a | INDEP
29 | Access to Sustainable Basic Services | Community Facilities | Construction of Lebaka Sports Complex phase III by 30 June 2014 | Lebaka Sports Complex | 9320000 | 01/07/2013 | 30/06/2014 | Review of designs and specifications | Ahead of target. Designs have been reviewed and in addition construction has resumed | None | n/a | n/a | INDEP
29 | Access to Sustainable Basic Services | Community Facilities | Construction of Sekgopo Sports complex phase III by 30 June 2014 | Sekgopo Sports complex | 12080000 | 01/07/2013 | 30/06/2014 | Review of designs and specifications | Ahead of target. Designs have been reviewed and in addition construction has resumed | None | n/a | n/a | INDEP
29 | Access to Sustainable Basic Services | Community Facilities | Construction of Shaamiriri Sports Complex phase III by 30 June 2014 | Shaamiriri Sports Complex | 7890000 | 01/07/2013 | 30/06/2014 | Review of designs and specifications | Not on target. Contractor is busy with phase 1 of the project. | There are delays in procurement processes. | Adherence to procurement plan | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Development of Intergrated Roads & Transport Plan by 30 June 2014 | Intergrated Roads & Transport Plan | 400000 | 01/07/2013 | 30/06/2014 | n/a | Ahead of target. Terms of reference have been submitted to SCM in the 1st quarter | None | n/a | n/a | INDEP
29 | Access to Sustainable Basic Services | Electricity Distribution | Development of Electriciry Master Plan by 30 June 2014 | Electricity Master Plan | 844800 | 01/07/2013 | 31/12/2013 | Submission of draft Electricity Master plan (EMP) | On target. Draft master plan was presented to the municipality. | None | n/a | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Repairing of two (2) graders standing at ELB by 31 March 2014 | Repairing of graders | 500000 | 01/07/2013 | 31/03/2014 | n/a | Ahead of target. Site visit was done to view the grader at ELB workshop in the 1st quarter. | None | n/a | n/a | INDEP

## LED PROJECTS
KPA 3 LOCAL ECONOMIC DEVELOPMENT PROJECTS OUTPUT 3: IMPLEMENTATION OF THE COMMUNITY WORK PROGRAMME
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project / Initiative | Budget 2013/2014 | Start Date | Completion Date | Milestones Qtr Ending Sept 13 | Progress to date | Challenges | Interventions | Expenditure | Project Owner
22 | Improved Local Economy | Planning and Development | Purchasing of land to expand development by 31 March 2014 | Purchasing of land | 12000000 | 01/07/2013 | 31/03/2014 | Development of terms of reference and submit to SCM | On target. Terms of reference have been developed and submitted to SCM unit | None | n/a | n/a | INDEP
22 | Improved Local Economy | Local Economic Development | Construction of paving at Tourism centre by 30 June 2014 | Paving at Tourism Information Centre | 250000 | 01/10/2013 | 30/06/2014 | n/a | In process to develop specifications | None | n/a | n/a | INDEP
22 | Improved Local Economy | Local Economic Development | Construction activities at Show Ground by 31 March 2014 | GLM Show Ground | 1000000 | 01/07/2013 | 31/03/2014 | Develop specifications and submit to SCM for advertisement | On target. Terms of reference have been developed and submitted to SCM unit | None | n/a | n/a | INDEP
22 | Improved Local Economy | Local Economic Development | Support on Youth Development Programme / project by 30 June 2014 | Youth Development Programme | 200000 | 01/07/2013 | 30/06/2014 | Support initiatives for Khumeloni Youth Development Programme | On target. Proposed initiatives were presented to the portfolio committee | None | n/a | n/a | INDEP
22 | Improved Local Economy | Planning and Development | To peg sites at Modjadjiskloof Extension 11 by 30 June 2014 | Pegging of Modjadjiskloof Extension 11 sites | 100000 | 01/07/2013 | 30/06/2014 | Development of terms of reference and submit to SCM | On target. Terms of reference have been developed and submitted to SCM unit | None | n/a | n/a | INDEP
22 | Improved Local Economy | Planning and Development | Rezoning and demarcation of parks at Ga-Kgapane by 30 June 2014 | Rezoning of Kgapane Parks | 350000 | 01/07/2013 | 30/06/2014 | Development of terms of reference and submit to SCM | On target. Terms of reference have been developed and submitted to SCM unit | None | n/a | n/a | INDEP
22 | Improved Local Economy | Local Economic Development | Feasibility Study of Potential LED projects by 30 June 2014 | Feasibility Study (LED) | 350000 | 01/07/2013 | 30/06/2014 | Development of terms of reference and submit to SCM | On target. Terms of reference have been developed and submitted to SCM unit | None | n/a | n/a | INDEP
22 | Improved Local Economy | Local Economic Development | Establish agro-processing initiatives and support by 30 June 2014 | Agro-processing projects | 316000 | 01/07/2013 | 30/06/2014 | n/a | No progress | None | n/a | n/a | INDEP
22 | Improved Local Economy | Local Economic Development | To do feasibility study by 31 December 2013 | Feasibility Study of Manokwe Caves | 250000 | 01/07/2013 | 31/12/2013 | Draft feasibility study complete and submitted to the municipality | On target. Draft report has been submitted to the municipality | None | n/a | n/a | INDEP
22 | Improved Local Economy | Planning and Development | To demarcate and peg sites at Goudplaas by 31 December 2013 | Demarcation of sites - Goudplaas | 400000 | 01/07/2013 | 31/12/2013 | Demarcation progress 50% complete | Not on target. Service provider is busy with contour mapping and boundary determination. | Late appointment of service providers | Adherence to procurement plan | n/a | INDEP
22 | Improved Local Economy | Planning and Development | To peg sites at Vrystaat Farm - Modjadjiskloof by 30 September 2013 | Site pegging (Vrystaat) | 200000 | 01/07/2013 | 30/09/2013 | Site pegging 100% complete | On target. Site pegging is complete | None | n/a | n/a | INDEP
22 | Improved Local Economy | Local Economic Development | To review the LED strategy by 31 December 2013 | Reveiw of LED strategy (MSIG) | 200000 | 01/07/2013 | 30/12/2013 | Draft LED Strategy complete and submitted to the municipality | Not on target. The service provider did not accept the appointment | Late appointment of service providers | Adherence to procurement plan | n/a | INDEP
22 | Improved Local Economy | Local Economic Development | Review of existing Spatial Development Framework (SDF) by 30 June 2014 | SDF Review | 400000 | 01/07/2013 | 30/06/2014 | Development of terms of reference and submit to SCM | On target. Terms of reference have been developed and submitted to SCM unit | None | None | n/a | INDEP
22 | Improved Local Economy | Local Economic Development | To attend and participate in Tourism Indaba by 30 June 2014 | Tourism Indaba | 150000 | 01/07/2013 | 31/06/2014 | Review of outcomes from previous Tourism Indaba event | The event was not attended and review was not necessary | None | None | n/a | INDEP
22 | Improved Local Economy | Enviromental Management | To organize and conduct environmental programme within the municipality by 30 June 2014 | Environmental Programmes | 274000 | 01/07/2013 | 30/06/2014 | Coordinate and conduct enviromental related events and campaigns (1 per quarter) | Coordinate and conduct enviromental related events and campaigns (1 per quarter) | 2 enviromental awareness campaighns conducted | None | n/a | COMM
34 | Improved Local Economy | Sports and Recreation | To organise the rainmaking ceremony by 31 December 2013 | Rain making ceremony | 100000 | 01/07/2013 | 31/12/2013 | Attend to preparatory meetings | Attend to preparatory meetings | 2 meetings were held | None | n/a | COMM
34 | Improved Local Economy | Sports and Recreation | To organise the Wolkberg sports day by 31 March 2014 | Wolkberg Sports day | 100000 | 01/07/2013 | 31/03/2014 | Development of Implementation plan | Development of Implementation plan | 1 meeting was held and plan developed | None | n/a | COMM
34 | Improved Local Economy | Sports and Recreation | To organise and host various sport codes by 31 March 2014 | Sports Activities | 300000 | 01/07/2013 | 31/03/2014 | Development of Implementation plan | Development of Implementation plan | 1 meeting was held and plan developed | None | n/a | COMM
34 | Improved Local Economy | Sports and Recreation | To organise event for cultural activities by 30 June 2014 | Cultural Activities | 100000 | 01/07/2013 | 30/06/2014 | n/a | n/a | Plan been developed and 1 cultural activity was held | None | n/a | COMM
34 | Improved Local Economy | Sports and Recreation | To organise Choral Music Competition by 31 March 2014 | Coral Music Competition | 80000 | 01/07/2013 | 31/03/2014 | Develop implementation plan and advertisement to invite participants | Develop implementation plan and advertisement to invite participants | 1 meeting was held and plan developed | None | n/a | COMM

## MFMV KPI
KPA 4 MUNICIPAL FINANCIAL VIABILITY KEY PERFORMANCE INDICATORS OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY
Vote Nr | Strategic Objective | Progranmes | Measurable Objectives | Performance measures | Baseline / Status | Budget 2013/2014 | 1st Quarter target | Progress to date | Challenges | Interventions | Expenditure | Responsible Person
50 | Sustainable Financial Institution | Budget and Reporting | To ensure that financial information is supplied to relevant authorities within timeframe | Financial information supplied to relevant office by 10 June 2014 | Information was submitted by 10 June 2014 | Operational | n/a | n/a | None | n/a | Operational | CFO
50 | Sustainable Financial Institution | Budget and Reporting | To ensure that quartely financial statements are prepared within timeframe | Preparation of Quartely financial statements and submitted to the relevant office | 100% | Operational | 100% | In progress | Delay on the completion of trial balance to enable preparation of quarterly financial statements | Service provider is appointed in assisting and capacitating the finance officials to prepare quarterly financial statements on a caseware | Operational | CFO
50 | Sustainable Financial Institution | Supply Chain Management | To effectively manage the financial affairs of the municipality | %Payment of service provider within 30 days. | 100% | Operational | 100% | 100% | None | n/a | Operational | CFO
50 | Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality | % capital budget spent as approved by Council | 100% | Operational | 25% | 4% of the amount spent | Majority of projects are in the planning stage | Proper implementation of procurement plan | Operational | CFO/INDEP/MM
50 | Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality | % MIG expenditure | 100% | 46950000 | 25% | Expenditure is at 20% | Majority of projects are in the planning stage | Proper implementation of procurement plan | n/a | CFO/INDEP/MM
50 | Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality | % FMG expenditure | 100% | 1550000 | 25% | 13% of the amount spent | Low spending caused by FMG activities not targeted in the 1st quarter | Adherence to SDBIP | n/a | CFO/INDEP/MM
50 | Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality | % MSIG expenditure | 100% | 890000 | 25% | No spending | None spending is caused by MSIG projects which have been scheduled from second quarter as per procurement plan | Adherence to SDBIP | n/a | CFO/INDEP/MM

## MFMV PROJECTS
KPA 4 MUNICIPAL FINANCIAL VIABILITY PROJECTS OUTCOME NINE (OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY)
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project / Initiative | Budget 2013/2014 | Start Date | Completion Date | Milestones Qtr Ending Sept 13 | Progress to date | Challenges | Interventions | Expenditure | Project Owner
50 | Sustainable Financial Institution | Indigent Management | To register qualifying indigents 30 June 2014 | Updating of Indigent Register | Operational | 01/07/2013 | 30/06/2014 | Collection of information on indigent households and update the register | 1712 Qualified and still in the process of adjudicating other indigent applications | Information on indigents applications is not made accessible to pontential beneficials | To conduct awarness by way of posters, flyers and local radio stations | Operational | CFO
50 | Sustainable Financial Institution | Revenue Management | Review of Revenue Enhancement Strategy 30 June 2014 | Revenue Enhancement Strategy | 106000 | 01/07/2013 | 30/06/2014 | n/a | n/a | None | n/a | n/a | CFO
50 | Sustainable Financial Institution | Revenue Management | To update household billing system information 30 June 2014 | Data cleansing | 106000 | 01/07/2013 | 30/06/2014 | Update households information on billing system by end of quarter | Request Information form has been developed in previours year is in the process of being distrubted to households | A certain number of households may not submit request information form. | To conduct awarness by way of posters, flyers and local radio stations | n/a | CFO
50 | Sustainable Financial Institution | Asset Management | To monitor the process of unbundling and make progress report by 31 March 2014 | Unbundling of Infrastructure Assets to update the asset register | 200000 | 01/10/2013 | 31/03/2014 | n/a | n/a | None | n/a | n/a | CFO
50 | Sustainable Financial Institution | Supply Chain Management | Purchasing of the Automated Procurement Software by 30 June 2014 | Automated Procurement Software | 250000 | 01/10/2013 | 30/06/2014 | n/a | n/a | None | n/a | n/a | CFO
50 | Sustainable Financial Institution | Supply Chain Management | Linking the Assets to the GIS software by 31 March 2014 | Linking the Assets to the GIS software | 150000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to the bid specification committee. | Delay in the process of developing specification | In process of developing Specification | n/a | n/a | CFO
50 | Sustainable Financial Institution | Asset Management | Updating of valuation roll by 31 March 2014 | Valuation Roll | 159600 | 01/07/2013 | 31/03/2014 | Conduct assessment of supplementary valuation roll. | Conducted only if there is a need for properties to be valued | None | n/a | n/a | CFO
50 | Sustainable Financial Institution | Asset Management | To purchase two (2) Small Bakkie for water reading by 31 March 2014 | Small Bakkie | 400000 | 01/10/2013 | 31/03/2014 | n/a | n/a | None | n/a | n/a | CFO
50 | Sustainable Financial Institution | Asset Management | To purchase Sedan by 31 March 2014 | Sedan | 200000 | 01/10/2013 | 31/03/2014 | n/a | n/a | None | n/a | n/a | CFO
50 | Sustainable Financial Institution | Office furnisher | To procure printers (2) - Salary Section & Revenue Section by 31 March 2014 | Printers (2) - Salary Section & Revenue Section | 400000 | 01/10/2013 | 31/03/2014 | n/a | n/a | None | n/a | n/a | CFO
50 | Sustainable Financial Institution | Auxillary Services | Supply and delivery of fuel by 31 December 2013 | Fuel supply | 1600000 | 01/10/2013 | 31/12/2013 | Develop specifications for appointment of service providers | In process of developing specification | Delay in the tender processes | Bench-marking with other stakeholders | n/a | CFO

## GGPP KPI's
KPA 5 GOOD GOVERNANCE AND PUBLIC PARTICIPATION KEY PERFORMANCE INDICATORS OUTCOME 9 (OUTPUT 5: DEEPEN DEMOCRACY THROUGH A REFINED WARD COMMITTEE MODEL, OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY)
Vote Nr | Strategic Objective | Programmes | Measurable Objectives | Performance measures | Baseline / Status | Budget 2013/2014 | 1st Quarter target | Progress to date | Challenges | Intervention | Expenditure | Responsible Person
54 | Improved Governance and Organisational Excellence | Ward Committee | To ensure full participation of ward committees | # ward committees evaluated per month | 29 | Operational | 1 | 1 Ward committee meeting per month out of 29 wards was held. | None | n/a | Operational | MM/CORPS
54 | Improved Governance and Organisational Excellence | Ward Committee |  | % complaints attended (# of community complaints received/ # of complaints atteneded to). | 100% | Operational | 100% | 97 complaints were received via presidential and Premiern hotline.100% were resolved | None | n/a | Operational | MM
54 | Improved Governance and Organisational Excellence | Local Imbizos | To ensure community participation | # of local imbizos held by the Mayor | 4 | 1000000 | 1 | No local imbiso was held | Clashes with the MEC event. | Postponed to the next Quarter of the current financial year | n/a | MM
54 | Improved Governance and Organisational Excellence | Local Imbizos | To ensure community participation | % public participation events publicised on the newspaper and website) (# for public participation events publicised in the newspapers and website | 100% | Operational | 100% | 2 News letters were published | None | n/a | Operational | MM
54 | Improved Governance and Organisational Excellence | Traditional Leaders | To establish a good relationship with traditional leaders | # traditional leaders invited to take part in council | 9 | Operational | 10 | All traditional leaders are invited to Council meetings and other activities | None | n/a | Operational | MM
54 | Improved Governance and Organisational Excellence | Communication | To promote effective and efficient communication | # of articles issued to the media on Mayoral events. | 1 | Operational | 1 | 4 articles issued to the media on Mayoral events | None | n/a | Operational | Ass-Director (Mayor's office)/MM
54 | Improved Governance and Organisational Excellence | Communication | To promote effective and efficient communication | # of newslatters issued | 4 | Operational | 1 | n/a | Not adhering to the procurement process plan | Appointment of service provider | Operational | Ass-Director (Mayor's office)/MM
54 | Improved Governance and Organisational Excellence | Communication | To promote effective and efficient communication | # of meetings held by the Communicators Forum | 4 | Operational | 1 | 1 meeting was held by the communicators Forum | None | n/a | Operational | Ass-Director (Mayor's office)/MM
54 | Improved Governance and Organisational Excellence | Legal | To ensure proper contract management | % appointed service providers with Service Level Agreement (# of service providers appointed/# of service providers with service level agreement) | 100% | Operational | 100% | 100% | None | n/a | Operational | CORPS/MM
46 | Improved Human Resource | Skills Development | To ensure effective implementation of the WSP | % employees trained as per the WSP | 100% | Operational | 25% | n/a | n/a | n/a | Operational | CORPS
46 | Improved Human Resource | OHS | To ensure a health and safe working environment | # of wellness campaign conducted per quarter | 4 | Operational | 1 | No wellness campaign was conducted | The invited stakeholders from Health Department were committed and not available on the scheduled date | Postponed to the next Quarter of the current financial year | Operational | CORPS

## GGPP PROJECTS
KPA 5 GOOD GOVERNANCE AND PUBLIC PARTICIPATION PROJECTS OUTPUT 5: DEEPEN DEMOCRACY THROUGH A REFINED WARD COMMITTEE MODEL, OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY)
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project / Initiative | Budget 2013/2014 | Start Date | Completion Date | Milestones Qtr Ending Sept 13 | Progress to date | Challenges | Interventions | Expenditure | Project Owner
40 | Improved Governance and Organisational Excellence | Furniture and Equipments | To procure recording system/ video camera 31 March 2014 | Recording System/ Video Camera | 20000 | 01/10/2013 | 31/03/2014 | n/a | n/a | None | n/a | n/a | CORPS
40 | Improved Governance and Organisational Excellence | Furniture and Equipments | To procure (2) council vehicles by 31 March 2014 | Council Vehicles | 600000 | 01/10/2013 | 31/03/2014 | n/a | n/a | None | n/a | n/a | CORPS
54 | Improved Governance and Organisational Excellence | Property Services | Interior design and decoration of the Council Chamber and foyer including purchasing of podium by 31 March 2014 | Decoration of Council Chamber (Including the foyer and podium) | 1505000 | 01/07/2013 | 31/03/2014 | Develop specifications and submit to SCM. Advertise for appointment of service providers | In process of developing specification | Not adhering to the procurement process plan | Bench-marking with other stakeholders | n/a | CORPS