## COVER
GREATER LETABA MUNICIPALITY
ADJUSTED SERVICE DELIVERY AND BUDGET
IMPLEMENTATION PLAN
2015/16

## INDEX
Table of Contents
Introduction | 3
Legislation | 3
Methodology and Contents | 4
Strategic Vision, Mission and Strategy Map | 5
Votes and Operational Objectives | 6
Municipal Financial projections | 7
Municipal Transformation and Organisational Development KPI's | 12
Municipal Transformation and Organisational Development Projects | 16
Basic Service Delivery KPI's | 18
Basic Service Delivery Projects | 19
Municipal Financial Viability KPI's | 31
Municipal Financial Viability Projects | 33
Good Governance and Public Participation KPI's | 34
Good Governance and Public Participation Projects | 37
Approval | 39

## INTR AND LEGISLATION
Introduction | The development, implementation and monitoring of a Service Delivery and Budget Implementation Plan (SDBIP) is required by the Municipal Finance Management Act (MFMA). In terms of Circular 13 of National Treasury, “the SDBIP gives effect to the Integrated Development Plan (IDP) and budget of the municipality and will be possible if the IDP and budget are fully aligned with each other, as required by the MFMA.” As the budget gives effect to the strategic priorities of the municipality it is important to supplement the budget and the IDP with a management and implementation plan. The SDBIP serves as the commitment by the Municipality, which includes the administration, council and community, whereby the intended objectives and projected achievements are expressed in order to ensure that desired outcomes over the long term are achieved and these are implemented by the administration over the next twelve months.
The SDBIP provides the basis for measuring performance in service delivery against quarterly targets and implementing the budget based on monthly projections. Circular 13 further suggests that “the SDBIP provides the vital link between the mayor, council (executive) and the administration, and facilitates the process for holding management accountable for its performance. The SDBIP is a management, implementation and monitoring tool that will assist the mayor, councillors, municipal manager, senior managers and community.” The purpose of the SDBIP is to monitor the execution of the budget, performance of senior management and achievement of the strategic objectives set by council. It enables the municipal manager to monitor the performance of senior managers, the mayor to monitor the performance of the municipal manager, and for the community to monitor the performance of the municipality.
In the interests of good governance and better accountability, the SDBIP should therefore determine and be aligned with the performance agreements of the municipal manager and senior managers. The development, implementation and monitoring of a Service Delivery and Budget Implementation Plan (SDBIP) is required by the Municipal Finance Management Act (MFMA). In terms of Circular 13 of National Treasury, “the SDBIP gives effect to the Integrated Development Plan (IDP) and budget of the municipality and will be possible if the IDP and budget are fully aligned with each other, as required by the MFMA.”
Legislation | According to the Municipal Finance Act (MFMA) the definition of a SDBIP is: 'service delivery and budget implementation plan' means a detailed plan approved by the mayor of a municipality in terms of section 53 (1) (c) (ii) for implementing the municipality's delivery of municipal services and its annual budget, and which must indicate- (a) projections for each month; (i) revenue to be collected by source; (ii) operational and capital expenditure by vote; (b) service delivery targets and performance indicators for each quarter. Section 53 of the MFMA stipulates that the Mayor should approve the SDBIP within 28 days after the approval of the budget. The Mayor must also ensure that the revenue and expenditure projections for each month and the service delivery targets and performance indicators as set out in the SDBIP are made public within 14 days after their approval.
The following National Treasury prescriptions as minimum requirements that must form part of the SDBIP are applicable to the Municipality : (1) Monthly projections of revenue to be collected by source. (2) Monthly projections of expenditure (operating and capital) and revenue for each vote. (3) Quarterly projections of service delivery targets and performance indicators for each vote. (4) Ward information for expenditure and service delivery. (5) Detailed capital works plan broken down per ward for three years. * Section 1 of the MFMA defines a “vote” as: a) One of the main segments into which a budget of a municipality is divided for the appropriation of money for the different departments or functional areas of the municipality; and b) which specifies the total amount that is appropriated for the purposes of the department or functional area concerned.
Section 28 of the Municipal Finance Management Act deals with adjustments budgets. In terms of the Act, an adjustments budget is intended to do the following: Sub-Section 2 a) Must adjust the revenue and expenditure estimates downwards if there is material under-collection of revenue during the current year b) May appropriate additional revenues that have become available over and above those anticipated in the annual budget, but only to revise or accelerate spending programmes already budgeted for c) May, within a prescribed framework, authorise unforeseeable and unavoidable expenditure recommended by the mayor of the municipality d) May authorise the utilisation of projected savings in one vote towards spending under another vote e) May authorise the spending of funds that were unspent at the end of the past financial year where the under-spending could not reasonably have been foreseen at the time to include projected roll-overs when the annual budget for the current year was approved by the council f) May correct any errors in the annual budget; and g) May provide for any other expenditure within a prescribed framework.

## METHODOLOGY AND CONTENT
Methodology and Content | National Treasury directives are clear on the contents and methodology to derive at the SDBIP. As a first step, the IDP objectives need to be quantified and related into key performance indicators. The budget is aligned to the objectives, projects and activities to enable the SDBIP to serve as monitoring tool for service delivery. The SDBIP is described as a layered plan. The top layer deals with consolidated service delivery targets and time frames. Top Management is held accountable for the implementation of the consolidated projects and Key Performance Indicators. From the consolidated information, top management is expected to develop the next level of detail by breaking up outputs into smaller outputs and then linking and assigning responsibility to middle-level and junior managers.
The SDBIP of the Greater Letaba Municipality consists of strategic objectives derived from the IDP that are aligned with the strategic intent of the organisation. Strategic indicators with targets are set to measure the objectives. The Municipal Manager takes responsibility for the strategic indicators and objectives which will form part of his/her Performance Agreement and Plan. Projects and activities are aligned to the indicators with quarterly targets, time-frame and budget assigned to each. The Strategic Indicators give rise to the institutional indicators for which the Directors will take responsibility. These indicators will form part of the Performance Agreements and Plans of Senior Managers (Directors). Indicators are assigned quarterly targets and responsibilities to monitor performance. Derived from this, the next layer is developed, whereby the details with responsibilities for the next level of management is outlined and forms part of the Lower SDBIP. This lower SDBIP is a management tool for the S57 Managers and need not be made public and is a separate document for each internal department. The SDBIP serves as a management, implementation and monitoring tool that will assist the Mayor, Councilors, Municipal Manager and Directors in delivering services to the community

## STRATEGY
Vision and Mission | The strategic vision of the organisation sets the long term goal the Municipality wants to achieve. The vision of Greater Letaba Municipality is: "To be an outstanding agro-processing and eco-cultural tourism hub". The strategic mission speaks about what the purpose of Greater Letaba Municipality is: The mission of Greater Letaba Municipality is to ensure an effective, efficient and economically viable municipality through: Provision of accountable, transparent, consultative and co-operative governance. Improving the quality of life through economic development and poverty alleviation. Provision of sustainable services. Ensuring a safe and healthy environment.
Strategy map | The Strategy Map depicts the strategic objectives on how Greater Letaba Municipality will be able to become an outstanding agro-processing and eco-cultural tourism hub while providing sustainable and affordable services to all. These objectives were positioned in terms of the Balanced Scorecard Perspectives being: Learning and Growth; Institutional Processes; Financial results and Community Satisfaction. All operational outputs (projects, initiatives and process) as contained within the SDBIP are aligned to the attainment of one or more of these objectives.

## OPERATIONAL STRATEGIES
Votes and Operational objectives | Votes | Objectives and Targets
| Municipal Manager Office (Vote 0040) | To lead, direct and manage a motivated and inspired administration and account to the Greater Letaba Municipal Council as Accounting Officer for long term municipal sustainability to achieve a good creditor rating within the requirements of the relevant legislation and whereas the following sections within the department, i.e. HIV/Aids, Youth, Disabled and Gender Desk, Communication and Internal Auditing is managed for integration, economic growth, marginalised poverty alleviation, efficient, economic and effective communication and service delivery.
| Finance (Vote 0050) | To secure a sound and sustainable management of the financial affairs of Greater Letaba Municipality by managing the budget and treasury office and advising and if necessary assisting the Accounting Officer and the Directors in their duties and delegation contained in the MFMA. Ensuring that the Greater Letaba Municipality is 100% financially viable when it comes to cost coverage and to manage the grant revenue of the municipality so that no grant funding is foregone
| Community Services (Vote 0028) | To co-ordinate Environmental Health Services, Sports Arts and Culture, Education, Libraries, Safety and Security, Environmental and Waste management, Health and Social development programmes as well as Disaster management to decrease community affected by disasters
| Infrastructure Development and Economic Planning (Votes 0029 and 0022) | To ensure that the service delivery requirements for roads are met and maintenance of water, sewerage and electricity are conducted for access to basic services as well as no less than an average of 100% MIG expenditure
To direct the Greater Letaba Municipality’s resources for advanced economic development and investment growth through appropriate town and infrastructure planning in order that an environment is created whereby all residents will have a sustainable income.
| Corporate Services (Vote 0046 ) | To ensure efficient and effective operation of council services, human resources and management, legal services and the provision of high quality customer orientated administrative systems. Ensuring 100% compliance to the Skills Development Plan.

## Finance projections
Monthly Projections of Revenue for Each Source
Sources of Revenue | 2015 Monthly Projections R'00 | [5 empty] | 2016 Monthly Projections
| Jul. | Aug. | Sep. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | Apr. | May | June
Property rates | 961 | 739 | 730 | 728 | 728 | 734 | 328 | 306 | 374 | 375 | 328 | 328
Service charges-electricity revenue | 848 | 480 | 440 | 868 | 636 | 641 | 1862 | 2104 | 2400 | 2200 | 2001 | 2332
Services Charges- refuse revenue | 337 | 336 | 336 | 337 | 338 | 338 | 385 | 401 | 356 | 375 | 352 | 398
Rental of Facilities and Equipment | 6 | 12 | 4 | 16 | 7 | 73 | 21 | 20 | 31 | 18 | 14 | 15
Interest earned-external investments | 277 | 287 | 302 | 298 | 0 | 652 | 341 | 329 | 342 | 302 | 332 | 322
Intersest Earned- Outstanding Debtors | 660 | 670 | 477 | 622 | 543 | 677 | 701 | 654 | 424 | 715 | 525 | 629
Dividends received | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | - | 0
Fines | 10 | 20 | 14 | 20 | 19 | 23 | 39 | 29 | 36 | 47 | 49 | 48
Licenses and Permits | 254 | 233 | 246 | 1007 | [352] | 1059 | 686 | 549 | 479 | 621 | 589 | 505
Agency services | 173 | 162 | 100 | 0 | [91] | 0 | 296 | 275 | 215 | 190 | 250 | 253
Transfers recognised- operational | 87219 | 389 | 395 | 223 | 55705 | 201 | 849 | 989 | 62850 | 953 | 1865 | 1716
Other Revenue | [2087] | 323 | 285 | 149 |  | 207 | 945 | 846 | 651 | 789 | 900 | 1022
Transfers recognised- Capital | 2106 | 6908 | 4652 | 4491 | 3741 | 4163 | 4562 | 9780 | 10500 | 9758 | 7894 | 11033
Total Revenue by Source | 92851 | 10559 | 7981 | 8759 | 61717 | 8768 | 11015 | 16282 | 78658 | 16343 | 15099 | 18601
Monthly Projections of Expenditure (Operating, Capital and Revenue) by vote : First Quarter | bar: 2015 Monthly Projections R'00 Jul. to 2016 Monthly Projections Apr.
Expenditure and Revenue by Vote | 2015 Monthly Projections R'00 Jul.: 2015-07-01; 2015 Monthly Projections R'00 Oct.: 2015-08-01; 2016 Monthly Projections Jan.: 2015-09-01; 2016 Monthly Projections Apr.: Evidence required
| Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex
Executive and Council | _ | 2895 |  | _ | 3003 |  | _ | 3150 | 20 | Financial reports
Budget and Treasury | 24019 | 1652 |  | 30000 | 1800 |  | 31000 | 1236 | 393 | Financial reports
Corporate Services | _ | 1900 |  | _ | 2145 | 150 | _ | 2450 |  | Financial reports
Planning and Development | 2015 Monthly Projections R'00 Jul.: _; 2015 Monthly Projections R'00 Aug.: 850; 2015 Monthly Projections R'00 Oct.: _; 2015 Monthly Projections R'00 Nov.: 1200; 2016 Monthly Projections Jan.: _; 2016 Monthly Projections Feb.: 1452; 2016 Monthly Projections Apr.: Financial reports
Community Services | 2015 Monthly Projections R'00 Jul.: _; 2015 Monthly Projections R'00 Aug.: 230; 2015 Monthly Projections R'00 Oct.: _; 2015 Monthly Projections R'00 Nov.: 216; 2016 Monthly Projections Jan.: _; 2016 Monthly Projections Feb.: 241; 2016 Monthly Projections Apr.: Financial reports
Housing | 2015 Monthly Projections R'00 Jul.: _; 2015 Monthly Projections R'00 Aug.: 45; 2015 Monthly Projections R'00 Oct.: _; 2015 Monthly Projections R'00 Nov.: 36; 2016 Monthly Projections Jan.: _; 2016 Monthly Projections Feb.: 29; 2016 Monthly Projections Apr.: Financial reports
Public Safety | _ | 158 |  | _ | 168 |  | _ | 149 | 320 | Financial reports
Sports and Recreation | _ | 495 |  | _ | 500 |  | _ | 515 | 1500 | Financial reports
Waste Water Management |  | 47 | _ | _ | 54 | _ | _ | 49 | _ | Financial reports
Waste Management | 2015 Monthly Projections R'00 Jul.: 357; 2015 Monthly Projections R'00 Aug.: 47; 2015 Monthly Projections R'00 Oct.: 357; 2015 Monthly Projections R'00 Nov.: 500; 2016 Monthly Projections Jan.: 357; 2016 Monthly Projections Feb.: 521; 2016 Monthly Projections Apr.: Financial reports
Road Transport | 671 | 485 | 3400 | 671 | 1985 | 8500 | 671 | 2000 | 5640 | Financial reports
Electricity | 2015 Monthly Projections R'00 Jul.: 1400; 2015 Monthly Projections R'00 Aug.: 1875; 2015 Monthly Projections R'00 Oct.: 1400; 2015 Monthly Projections R'00 Nov.: 1485; 2016 Monthly Projections Jan.: 1400; 2016 Monthly Projections Feb.: 1354; 2016 Monthly Projections Apr.: Financial reports
Total by Vote | 26447 | 12282 | 3400 | 26447 | 13091 | 8650 | 26447 | 13145 | 7873 | Financial reports
Monthly Projections of Expenditure (Operating, Capital and Revenue) by vote : Second Quarter | bar: 2015 Monthly Projections R'00 Jul. to 2016 Monthly Projections Apr.
Expenditure and Revenue by Vote | 2015 Monthly Projections R'00 Jul.: 2015-10-01; 2015 Monthly Projections R'00 Oct.: 2015-11-01; 2016 Monthly Projections Jan.: 2015-12-01; 2016 Monthly Projections Apr.: Evidence required
| Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex
Executive and Council | 2015 Monthly Projections R'00 Jul.: _; 2015 Monthly Projections R'00 Aug.: 3828; 2015 Monthly Projections R'00 Oct.: _; 2015 Monthly Projections R'00 Nov.: 4000; 2016 Monthly Projections Jan.: _; 2016 Monthly Projections Feb.: 3520; 2016 Monthly Projections Apr.: Financial reports
Budget and Treasury | 2015 Monthly Projections R'00 Jul.: 31590; 2015 Monthly Projections R'00 Aug.: 2000; 2015 Monthly Projections R'00 Oct.: 30975; 2015 Monthly Projections R'00 Nov.: 2500; 2016 Monthly Projections Jan.: 30547; 2016 Monthly Projections Feb.: 1256; 2016 Monthly Projections Apr.: Financial reports
Corporate Services | _ | 2641 | 40 | _ | 2100 |  | _ | 2800 | 500 | Financial reports
Planning and Development | 2015 Monthly Projections R'00 Jul.: _; 2015 Monthly Projections R'00 Aug.: 985; 2015 Monthly Projections R'00 Oct.: _; 2015 Monthly Projections R'00 Nov.: 1256; 2016 Monthly Projections Jan.: _; 2016 Monthly Projections Feb.: 1061; 2016 Monthly Projections Apr.: Financial reports
Community Services | _ | 148 |  | _ | 200 | 800 | _ | 235 |  | Financial reports
Housing | 2015 Monthly Projections R'00 Jul.: _; 2015 Monthly Projections R'00 Aug.: 39; 2015 Monthly Projections R'00 Oct.: _; 2015 Monthly Projections R'00 Nov.: 36; 2016 Monthly Projections Jan.: _; 2016 Monthly Projections Feb.: 51; 2016 Monthly Projections Apr.: Financial reports
Public Safety | 2015 Monthly Projections R'00 Jul.: _; 2015 Monthly Projections R'00 Aug.: 162; 2015 Monthly Projections R'00 Oct.: _; 2015 Monthly Projections R'00 Nov.: 234; 2016 Monthly Projections Jan.: _; 2016 Monthly Projections Feb.: 200; 2016 Monthly Projections Apr.: Financial reports
Sports and Recreation | _ | 486 |  | _ | 524 |  | _ | 589 | 6540 | Financial reports
Waste Water Management | _ | 46 | _ | _ | 52 | 2400 | _ | 48 | _ | Financial reports
Waste Management | 357 | 504 |  | 357 | 499 | 3000 | 357 | 552 |  | Financial reports
Road Transport | 671 | 2100 | 8900 | 671 | 1784 | 12000 | 671 | 2000 | 13580 | Financial reports
Electricity | 1400 | 1200 | 600 | 1400 | 1175 | 1540 | 1400 | 1230 |  | Financial reports
Total by Vote | 26447 | 14139 | 9540 | 26447 | 14360 | 19740 | 26447 | 13541 | 20620
Monthly Projections of Expenditure (Operating, Capital and Revenue) by vote : Third Quarter | bar: 2015 Monthly Projections R'00 Jul. to 2016 Monthly Projections Apr.
Expenditure and Revenue by Vote | 2015 Monthly Projections R'00 Jul.: 2016-01-01; 2015 Monthly Projections R'00 Oct.: 2016-02-01; 2016 Monthly Projections Jan.: 2016-03-01; 2016 Monthly Projections Apr.: Evidence required
| Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex
Executive and Council | _ | 2856 |  | _ | 4265 | 500 | _ | 3460 |  | Financial reports
Budget and Treasury | 2015 Monthly Projections R'00 Jul.: 20600; 2015 Monthly Projections R'00 Aug.: 985; 2015 Monthly Projections R'00 Oct.: 20541; 2015 Monthly Projections R'00 Nov.: 1001; 2016 Monthly Projections Jan.: 20655; 2016 Monthly Projections Feb.: 2500; 2016 Monthly Projections Apr.: Financial reports
Corporate Services | 2015 Monthly Projections R'00 Aug.: 3500; 2015 Monthly Projections R'00 Sep.: 40; 2015 Monthly Projections R'00 Nov.: 2731; 2016 Monthly Projections Feb.: 2734; 2016 Monthly Projections Apr.: Financial reports
Planning and Development | 2015 Monthly Projections R'00 Aug.: 1426; 2015 Monthly Projections R'00 Nov.: 1050; 2016 Monthly Projections Feb.: 875; 2016 Monthly Projections Apr.: Financial reports
Community Services | 2015 Monthly Projections R'00 Aug.: 300; 2015 Monthly Projections R'00 Nov.: 325; 2015 Monthly Projections R'00 Dec.: 2500; 2016 Monthly Projections Feb.: 235; 2016 Monthly Projections Mar.: 5800; 2016 Monthly Projections Apr.: Financial reports
Housing | 2015 Monthly Projections R'00 Aug.: 50; 2015 Monthly Projections R'00 Nov.: 54; 2016 Monthly Projections Feb.: 36; 2016 Monthly Projections Apr.: Financial reports
Public Safety | 2015 Monthly Projections R'00 Aug.: 245; 2015 Monthly Projections R'00 Nov.: 142; 2016 Monthly Projections Feb.: 110; 2016 Monthly Projections Apr.: Financial reports
Sports and Recreation | 2015 Monthly Projections R'00 Aug.: 600; 2015 Monthly Projections R'00 Nov.: 1250; 2015 Monthly Projections R'00 Dec.: 8531; 2016 Monthly Projections Feb.: 1010; 2016 Monthly Projections Apr.: Financial reports
Waster Water Management | _ | 60 | _ | _ | 55 | _ | _ | 42 | _ | Financial reports
Waste Management | 357 | 541 |  | 357 | 564 | 3260 | 357 | 500 |  | Financial reports
Road Transport | 671 | 1875 | 8900 | 671 | 1920 | 4896 | 671 | 2235 | 5800 | Financial reports
Electricity | 1400 | 1500 | 600 | 1400 | 1607 |  | 1400 | 1800 |  | Financial reports
Total by Vote | 26447 | 13938 | 9540 | 26447 | 14965 | 26891 | 26447 | 15537 | 11600
Monthly Projections of Expenditure (Operating, Capital and Revenue) by vote : Fourth Quarter | bar: 2015 Monthly Projections R'00 Jul. to 2016 Monthly Projections Apr.
Expenditure and Revenue by Vote | 2015 Monthly Projections R'00 Jul.: 2016-04-01; 2015 Monthly Projections R'00 Oct.: 2016-05-01; 2016 Monthly Projections Jan.: 2016-06-01; 2016 Monthly Projections Apr.: Evidence required
| Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex
Executive and Council | 2015 Monthly Projections R'00 Jul.: _; 2015 Monthly Projections R'00 Aug.: 4600; 2015 Monthly Projections R'00 Oct.: _; 2015 Monthly Projections R'00 Nov.: 3828; 2016 Monthly Projections Jan.: _; 2016 Monthly Projections Feb.: 4534; 2016 Monthly Projections Apr.: Financial reports
Budget and Treasury | 2015 Monthly Projections R'00 Jul.: 25500; 2015 Monthly Projections R'00 Aug.: 300; 2015 Monthly Projections R'00 Oct.: 27500; 2015 Monthly Projections R'00 Nov.: 3800; 2016 Monthly Projections Jan.: 22762; 2016 Monthly Projections Feb.: 4846; 2016 Monthly Projections Apr.: Financial reports
Corporate Services | 2015 Monthly Projections R'00 Aug.: 3456; 2015 Monthly Projections R'00 Sep.: 1000; 2015 Monthly Projections R'00 Nov.: 4700; 2015 Monthly Projections R'00 Dec.: 700; 2016 Monthly Projections Feb.: 3547; 2016 Monthly Projections Mar.: 2220; 2016 Monthly Projections Apr.: Financial reports
Planning and Development | 2015 Monthly Projections R'00 Aug.: 745; 2015 Monthly Projections R'00 Nov.: 875; 2016 Monthly Projections Feb.: 816; 2016 Monthly Projections Apr.: Financial reports
Community Services | 2015 Monthly Projections R'00 Aug.: 231; 2015 Monthly Projections R'00 Nov.: 347; 2015 Monthly Projections R'00 Dec.: 6000; 2016 Monthly Projections Feb.: 363; 2016 Monthly Projections Mar.: 7411; 2016 Monthly Projections Apr.: Financial reports
Housing | 2015 Monthly Projections R'00 Aug.: 75; 2015 Monthly Projections R'00 Nov.: 69; 2016 Monthly Projections Feb.: 81; 2016 Monthly Projections Apr.: Financial reports
Public Safety | 2015 Monthly Projections R'00 Aug.: 201; 2015 Monthly Projections R'00 Nov.: 187; 2016 Monthly Projections Feb.: 181; 2016 Monthly Projections Apr.: Financial reports
Sports and Recreation | 2015 Monthly Projections R'00 Aug.: 800; 2015 Monthly Projections R'00 Sep.: 2354; 2015 Monthly Projections R'00 Nov.: 750; 2015 Monthly Projections R'00 Dec.: 6541; 2016 Monthly Projections Feb.: 1060; 2016 Monthly Projections Mar.: 5095; 2016 Monthly Projections Apr.: Financial reports
Waste Water Management | _ | 49 | _ | _ | 60 | _ | _ | 63 | _ | Financial reports
Waste Management | 2015 Monthly Projections R'00 Jul.: 357; 2015 Monthly Projections R'00 Aug.: 600; 2015 Monthly Projections R'00 Oct.: 357; 2015 Monthly Projections R'00 Nov.: 785; 2016 Monthly Projections Jan.: 357; 2016 Monthly Projections Feb.: 917; 2016 Monthly Projections Apr.: Financial reports
Road Transport | 671 | 2300 | 6000 | 671 | 2785 | 4580 | 671 | 2784 | 13940 | Financial reports
Electricity | 2015 Monthly Projections R'00 Jul.: 1400; 2015 Monthly Projections R'00 Aug.: 2000; 2015 Monthly Projections R'00 Oct.: 1400; 2015 Monthly Projections R'00 Nov.: 1988; 2016 Monthly Projections Jan.: 1400; 2016 Monthly Projections Feb.: 2296; 2016 Monthly Projections Apr.: Financial reports
Total by Vote | 26447 | 15357 | 9354 | 26447 | 20173 | 17821 | 26447 | 21489 | 28666

## MTOD KPI's
KPA 1 MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT
KEY PERFORMANCE INDICATORS
OUTCOME NINE (OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING, PLANNING AND SUPPORT, OUTPUT 4: ACTIONS SUPPORTIVE OF THE HUMAN SETTLEMENT OUTCOMES)
Vote Nr | Strategic Objective | Municipal Programmes | Measurable Objectives | Key Performance measures/ Performance Indicator | KPI Unit of measure | Baseline / Status | Annual Target (30/06/2016) | Budget 2015/16 | 1st Quarter (1 Jul-30 Sept 2015) | 2nd Quarter (1 Oct -31 Dec 2015) | 3rd Quarter (1 Jan 31 Mar 2016) | 4th Quarter (1 Apr- 3 Jun 2016) | Responsible Person | Evidence requires
| Improved Governance and Organisational Excellence | Human Resource Management | To ensure that the reviewed organiztional structure is approved by council by 31/05/2016 | To approve the Organisational structure by 31 May 2016 | Date | 31/05/2015 | Council Approve Organizational structure by 31 May 2016 | Operational | N/A | N/A | N/A | Council Approved Organizational structure by 31 May 2016 | Director Corp | Council Approved Organizational structure, Council Resolution
| Improved Governance and Organisational Excellence | Human Resource Management | Reducing the vacancy rate within the financial year | # of vacant positions to be filled by 30 June 2016 | Number | 12 Positions filled | Fill 40 Positions 30 June 2016 | Operational | N/A | 30 Positions filled | N/A | 10 Positions filled | Director Corp | Appointment letters
| Integrated Sustainable Development | IDP | Approval of the IDP/Budget/PMS process by 31 July 2015 | To approve 2015/16 IDP/Budget/ PMS Process Plan by council by 31 July 2016 | Date | 31/07/2014 | Approve 2015/16 IDP/Budget/PMS Process Plan by 31 July 2016 | Operational | Approval of 2015/16 IDP/Budget/PMS Process Plan by 31 July 2016 | N/A | N/A | N/A | Director INDEP | Council Approved IDP/ Budget/ PMS Process plan, Council Resolution
| Integrated Sustainable Development | IDP | Approval of the Draft 2016/17 IDP by 31 March 2016 | To approve Draft 2016/17 IDP by 31 March 2016 | Date | 31/03/2015 | Approve 2016/17 IDP by 31 March 2016 | Operational | N/A | N/A | Approval of 2016/17 IDP by 31 March 2016 | N/A | Director INDEP | Council approved Draft IDP and resolution, Council Resolution
| Integrated Sustainable Development | IDP | Approval of the Final 2016/17 IDP by council within the financial year | To approve Final 2016/17 IDP by Council 31 May 2016. | Date | 31/05/2015 | Approve final 2016/17 IDP by 31 May 2016 | Operational | N/A | N/A | N/A | Approval of final 2016/17 IDP by 31 May 2016 | Director INDEP | Council approved IDP and resolution, Council Resolution
| Improved Governance and Organisational Excellence | PMS | To ensure that SDBIP is finalised by 30 June 2016 | To approve final 2016/17 SDBIP by the Mayor within 28 days after adoption of the final Budget and IDP by 30 June 2016. | Date | 28/06/2015 | Approve final 2016/17 SDBIP by the Mayor within 28 days after adoption of the Budget and IDP by 30 June 2016. | Operational | N/A | N/A | N/A | Approval of final 2016/17 SDBIP by the Mayor within 28 days after adoption of the Budget and IDP by 30 June 2016. | Municipal Manager | Signed SDBIP by the Mayor
| Improved Governance and Organisational Excellence | PMS | To ensure quarterly reporting and compliance within the financial year | # of Quarterly performance reports compiled. By 30 June 2016. | Number | 4 Quarterly performance reports compiled | Compile 4 Quarterly performance reports by 30 June 2016 | Operational | 1 Quarterly performance reports compiled | 1 Quarterly performance reports compiled | 1 Quarterly performance reports compiled | 1 Quarterly performance reports compiled | Municipal Manager | Council approved Quarterly reports
| Improved Governance and Organisational Excellence | PMS | To ensure that S54 & 56 Managers sign the performance agreements within 30 days after adoption of the final SDBIP. | To Sign performance agreements by Sec 54 & 56 Managers by 31 July 2015 | Date | 07/07/2014 | Sign Performance Agreements for Se 54 & 56 Managers by 31 July 2015. | Operational | Performance Agreements signed for Se 54 & 56 Managers by 31 July 2015. | N/A | N/A | N/A | Municipal Manager | Signed Performance Agreements for Sec 54 & 56 Managers
| Improved Governance and Organisational Excellence | PMS | To ensure quartely assessments for S54 & 56 Managers is conducted within 30 days after the end of the quarter. | # of Individual performance assessments conducted for Sec 54 & 56 Managers in 2015/16 financial year by 30 June 2016 | Number | 0 | Conduct 2 Individual performnace by 30 June 2016 | Operational | 1 Individual performnace conducted | N/A | 1 Individual performnace conducted | N/A | Municipal Manager | Performance Assessments for Sec 54 & 56 Managers report
| Improved Governance and Organisational Excellence | PMS | To ensure municipal reporting and compliance within the financial year | To submit Annual 2014/15 Institutional Performance report to CoGHSTA, Provincial Treasury and National Treasury by 30 August 2015. | Date | 30/08/2014 | Submit Annual Institutional Performance Repor by 30 August 2015. | Operational | Submission of 2014/15 Annua Institutional Performance Repor by 30 August 2015. | N/A | N/A | N/A | Municipal Manager | Dated proof of submission to CoGHSTA, Provincial and National Treasury
| Improved Governance and Organisational Excellence | PMS | To ensure municipal reporting and compliance within the financial year | To submit 2015/16 Mid-Year report to CoGHSTA, Provincial and National Treasury by 25 January 2016 | Date | 25/01/2015 | Submit 2015/16 Mid-year report to CoGHSTA, Provincial Treasury and National Treasury by 25 January 2016. | Operational | N/A | N/A | Submission of 2015/16 Mid-year report to CoGHSTA, Provincial Treasury and National Treasury by 25 January 2016. | N/A | Municipal Manager | Dated proof of submission to CoGHSTA, Provincial and National Treasury
| Improved Governance and Organisational Excellence | PMS | To ensure municipal reporting and compliance | To table 2014/15 Annual Report in Council by 31 January 2016 | Date | 31/01/2015 | Table 2014/15 Annual report in Council by 31 January 2016. | Operational | N/A | N/A | Tabling of 2014/15 Annual report in Council by 31 January 2016. | N/A | Municipal Manager | Council approved Annual report, Council resolution
| Improved Governance and Organisational Excellence | PMS | To ensure municipal reporting and compliance within the financial year | To table Oversight report on the 2014/15 Annual Report in Council by 31 March 2016 | Date | 31/03/2015 | Tabling of Oversight report on the 2014/15 Annual Report in Council by 31 March 2016. | Operational | N/A | N/A | Tabling of Oversight report on the 2014/15 Annual Report in Council by 31 March 2016. | N/A | Municipal Manager | Council approved Oversight report on the Annual report, Council resolution
| Improved Governance and Organisational Excellence | PMS | To ensure municipal reporting and compliance within the financial year | To publish Oversight report in the newspaper & website within 7 days of adoption by 07 April 2016. | Date | 10/04/2015 | Publish the Oversight report in the Newspaper & Website within 7 days of adoption by 07 April 2016. | Operational | N/A | N/A | N/A | Publishing of the Oversight report in the Newspaper & Website within 7 days of adoption by 07 April 2016. | Municipal Manager | Council approved Annual report , Council resolution
| Improved Governance and Organisational Excellence | PMS | To ensure implementation of the performance management system in the organisation within the financial year. | To approve Performance management policy for officials lower than sec 54 & 56 by 30 June 2016 | Date | New Indicator | Approve Performance Management Policy for officials lower than sec 54 & 56 Managers by 30 June 2016 | Operational | N/A | N/A | N/A | Approval of Performance Management Policy for officials lower than sec 54 & 56 Managers by 30 June 2016 | Municipal Manager | Council approved PMS policy for all municipal officials, council resolution
| Improved Governance and Organisational Excellence | PMS | To ensure municipal reporting and compliance within the financial year | To approve the reviewed 2015/16 SDBIP in Council by 31 March 2016 | Date | 31/03/2015 | Approve reviewed 2015/16 SDBIP in Council by 31 March 2016. | Operational | N/A | N/A | Approval of the reviewed 2015/16 SDBIP in Council by 31 March 2016. | N/A | Municipal Manager | Reviewed 2015/16 SDBIP, Council resolution
| Improved Governance and Organisational Excellence | Legal Services | To improve effecience and effictiveness of municipal administration within the financial year | % developed Service Level Agreements within 30 days after the appointment of Service provider by 30 June 2016 (# of SLA s developed/ # of Appointments made) | Percentage | New Indicator | 100% (# of SLA s developed/ # of Appointments made) | Operational | 100% (# of SLA s developed/ # of Appointments made) | 100% (# of SLA s developed/ # of Appointments made) | 100% (# of SLA s developed/ # of Appointments made) | 100% (# of SLA s developed/ # of Appointments made) | Director Corp | Dated signed Service Level Agreements and Appointment letters
| Improved Governance and Organisational Excellence | Internal Audit | To conduct quarterly assessment on municipal performance within the financial year | # of performance audit reports compiled and issued to the Accounting Officer by 30 June 2016. | Number | 1 Performance audit reports compiled and issued to the Accounting Officer | Compile and issue 4 Performance audit reports by 30 June 2016 | Operational | 1 Performance audit reports compiled and issued to the Accounting Officer | 1 Performance audit reports compiled and issued to the Accounting Officer | 1 Performance audit reports compiled and issued to the Accounting Officer | 1 Performance audit reports compiled and issued to the Accounting Officer | Municipal Manager | Performance Audit report tabled,Council resolution
| Improved Governance and Organisational Excellence | Internal Audit | Functionality of Audit within the financial year | To develop AG Audit action plan for 2014/15 by 31 January 2016 | Date | 31/01/2015 | Develop AG Audit Action plan for 2014/15 by 31 January 2016 | Operational | N/A | N/A | Development of AG Audit Action plan for 2014/15 by 31 January 2016 | N/A | Municipal Manager | Council approved audit action plan for 2014/15, Council resolution
| Improved Governance and Organisational Excellence | Internal Audit | Functionality of Audit within the financial year | To develop Internal Audit action plan 2015/16 31 January 2016 | Date | 31/01/2015 | Develop Internal Audit plan for 2015/16 by 30 June 2016 | Operational | N/A | N/A | Development of Internal Audit plan for 2015/16 by 30 June 2016 | N/A | Municipal Manager | Approved 2015/16 Internal Audit Plan
| Improved Governance and Organisational Excellence | Internal Audit | To attain Clean Audit by ensuring compliance to all governance; financial management and reporting requirements by 30 June 2016 | % of internal audit issues resolved (# of Internal Audit issues resolved / # of issues raised) | Percentage | 90% Internal audit issues resolved | Resolve 100% internal audit issues by 30 June 2016 (# of Internal Audit issues resolved / # of issues raised) | Operational | 25% internal audit issues resolved (# of Internal Audit issues resolved / # of issues raised) | 50% internal audit issues resolved (# of Internal Audit issues resolved / # of issues raised) | 75% internal audit issues resolved (# of Internal Audit issues resolved / # of issues raised) | 100% internal audit issues resolved (# of Internal Audit issues resolved / # of issues raised) | Municipal Manager | Resolved IA register/plan, POE submitted
| Improved Governance and Organisational Excellence | Internal Audit | To attain Clean Audit by ensuring compliance to all governance; financial management and reporting requirements by 30 June 2016 | % of AG issues resolved (# of Auditor General issues resolved / # of issues raised) | Percentage | 90% issues resolved | Resolve 100% AG issues by 30 June 2016 (# of Auditor General issues resolved / # of issues raised) | Operational | N/A | N/A | 50% AG issues resolved (# of Auditor General issues resolved / # of issues raised) | 100% AG issues resolved (# of Auditor General issues resolved / # of issues raised) | Municipal Manager | Resolved AG issues and POE 's submitted
| Improved Governance and Organisational Excellence | Risk management | To ensure efffective implementation of risk mitigations actions 30 June 2016. | % of Risk issues resolved (# Risk issues implemented / resolved / # of risks identified) | Percentage | 85% Risk issues resolved | Resolve 100% Risk issues by 30 June 2016 (# Risk issues implemented / resolved / # of risks identified) | Operational | 25% Risk issues resolved (# Risk issues implemented / resolved / # of risks identified) | 50% Risk issues resolved (# Risk issues implemented / resolved / # of risks identified) | 75% Risk issues resolved (# Risk issues implemented / resolved / # of risks identified) | 100% Risk issues resolved (# Risk issues implemented / resolved / # of risks identified) | Municipal Manager | Resolved Risk issues and POE submitted

## MTOD Projects
2015/16 CAPITAL WORKS PLAN SUMMARY OF CAPITAL AND OPERATIONAL PROJECTS PER RESPONSIBLE MANAGER
Vote Nr | Region | Key Performance Area | Strategic Objective | Programme | Measurable Objective/ Performance Indicator | Project Name | Start Date | Completion date | Project Owner | Source of funding | Annual Target (30/06/16) | Budget | AdjustedBudget | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | Evidence required
39 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | To Purchase 4 Printers (Revenue, Assets and SCM) by 30 June 2016 | 4 Printers | 01/07/2015 | 30/06/2016 | Director Corp | GLM | Purchase 4 Printers for Revenue, Assets & SCM by 30 June 2016 | 40000 | 0 | Removed during budget adjustement in order to cater for rolled over projects |  |  |  | Delivery note
39 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | To Purchase 2 Printers (Salary & Revenue Section) by 30 June 2016. | 2 Printers | 01/07/2015 | 30/06/2016 | Director Corp | GLM | Purchase 4 Printers for Salary & Revenue by 30 June 2016 | 300000 | 0 | Removed during budget adjustement in order to cater for rolled over projects |  |  |  | Delivery note
39 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | To Purchase 1 All in One (Fax, Scan and Print) for budget office by 30 June 2016 | All in One Printer | 01/07/2015 | 30/06/2016 | Director Corp | GLM | Purchase 1 All in one (Fax, Scan and Print) for Budget Office by 30 June 2016 | 10000 | 0 | Removed during budget adjustement in order to cater for rolled over projects |  |  |  | Delivery note
39 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | To Purchase 1 Advance Scanner (Huge MB) by 30 June 2016 | Advance Scanner (Huge) | 01/07/2015 | 30/06/2016 | Director Corp | GLM | To Purchase 1 Advance Scanner (Huge MB) by 30 June 2016 | 40000 | 0 | Removed during budget adjustement in order to cater for rolled over projects |  |  |  | Delivery note
41 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | To Purchase office Furniture (8 Tables and 8 High back chairs and 4 visitors chairs by 30 June 2016 | Office Furniture | 01/07/2015 | 30/06/2016 | Director Corp | GLM | Purchase Furniture (8 Tables and 8 High back chairs and 4 visitors chairs ) for Head Office by 30 June 2016 | 500000 | 165000 | N/A | Develop and submit specification to SCM for advertisement | Advertisement and Appointment of Service Provider | Office Furniture (8 Tables and 8 High back chairs and 4 visitors chairs )purchased and delivered | Delivery note
41 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | To upgrade Telephone Management System by 31 March 2016 | Telephone Management System | 01/07/2015 | 31/03/2016 | Director Corp | GLM | Upgrade Telephone Management System by 30 June 2016 | 150000 | 0 | Removed during budget adjustement in order to cater for rolled over projects |  |  |  | Delivery note
39 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | To Implement Disaster Recovery Plan by 30 June 2016 | Disaster Recovery Plan | 01/07/2015 | 30/06/2016 | Director Corp | GLM | Implement Disaster Recovery Plan | 1000000 | 350000 | N/A | Develop and submit specification to SCM for advertisement | Advertisement and Appointment of Service Provider | Disaster Recovery Plan Implemented | Completion certificate
39 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | To Purchase 15 Laptops by 30 June 2016 | Purchase of Laptop | 01/07/2015 | 30/06/2016 | Director Corp | GLM | Purchase 15 Laptops for IT Section by 30 June 2016. | 400000 | 600000 | N/A | Develop and submit specification to SCM for advertisement | Advertisement and Appointment of Service Provider | 15 Laptops purchased and delivered | Delivery note
39 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | To Purchase 20 Desktops by 30 June 2016 | Purchasing of Desktops | 01/07/2015 | 30/06/2016 | Director Corp | GLM | Purchase 20 Laptops for IT by 30 June 2016 | 200000 | 0 | Removed during budget adjustement in order to cater for rolled over projects |  |  |  | Delivery note
39 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | To Purchase and Install Uninterupted Power Supply by 30 June 2016 | Uninterrupted Power Supply | 01/07/2015 | 30/06/2016 | Director Corp | GLM | Install Uninterupted Power supply by 30 June 2016 | 150000 | 150000 | N/A | Develop and submit specification to SCM for advertisement | Advertisement and Appointment of Service Provider | Uninterupted Power supply Installed | Delivery note
39 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | To purchase Traffic System Upgrade by 30 June016 | Traffic System Upgrade | 01/07/2015 | 30/06/2016 | Director COMM | GLM | Purchase and Install Traffic System purchased by 30 June 2016 | 100000 | 70000 | Develop and submit specification to SCM for advertisement | Advertisement and appointment of Service Provider | Traffic System purchased and Installed | N/A | Delivery note
39 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | To purchase and Install Brail Printer Software by 31 March 2016 | Brail Printer System | 01/07/2015 | 30/06/2016 | Director Corp | GLM | Purchase and Install Brail Printer Software by 30 June 2016 | 100000 | 86100 | Develop and submit specification to SCM for advertisement | Advertisement and appointment of Service Provider | Brail Printer Software purchased and Installed | N/A | Delivery note & Installation certificate
39 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | To purchase server room door by 30 June 2016 | Server room door | 01/07/2015 | 30/06/2016 | Director Corp | GLM | Purchase and Install Server room door by 30 June 2016 | 0 | 50000 | N/A | N/A | Develop and submit specification to SCM for advertisement | Server door installed | Delivery note
39 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | To purchase and Install of Blade server Software by 30 June 2016 | Blade server | 01/07/2015 | 31/03/2016 | Director Corp | GLM | Purchase and Install Blade server by 30 June 2016 | 0 | 350000 | N/A | N/A | Develop and submit specification to SCM for advertisement | Blade server purchsed and installaed | Delivery note & Installation certificate
39 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | To purchase and Install Alli-Cad software by 31 March 2016 | Alli-Cad Software | 01/07/2015 | 31/03/2016 | Director Corp | GLM | Purchase and Install Alli-Cad Software by 30 June 2016 | 100000 | 0 | Removed during budget adjustement in order to cater for rolled over projects |  |  |  | Delivery note & Installation certificate
39 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | To purchase and Install Call Log System by 30 June 2016 | Call Log System | 01/07/2015 | 30/06/2016 | Director Corp | GLM | Purchase and Install Call Log System by June 2016 | 100000 | 100000 | Submit specifications to SCM | Advertisement and appointment of Service Provider | Call Log System purchased and Installed | N/A | Delivery note & Installation certificate
41 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | To purchase and Install 10 Air Conditioners by 30 June 2016 | Air Conditioners | 01/07/2015 | 30/06/2016 | Director Corp | GLM | Purchase and Install 10 Air Conditioners by 30 June 2016 | 50000 | 50000 | Develop and submit specification to SCM for advertisement | Advertisement and appointment of Service Provider | 10 Air Conditioners purchased and Installed | N/A | Delivery note & Installation certificate
41 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | To purchase a Recording Machine by 30 June 2016 | Recording Machine | 01/07/2015 | 31/03/2016 | Director Corp | GLM | Purchase a recording machine by 30 June 2016 | 20000 | 0 | Removed during budget adjustement in order to cater for rolled over projects |  |  |  | Delivery note
41 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Assets Management | To purchase and Delivery of 2 Vehicles for Registry and Senwamokgope by 30 June 2016 | 2 Vehicles for Registry and Senwamokgope | 01/07/2015 | 31/03/2016 | Director Corp | GLM | Purchse 2 Vehicles for Registry(Main Office) and Senwamokgope sub office by 30 June 2016 | 200000 | 0 | Removed during budget adjustement in order to cater for rolled over projects |  |  |  | Delivery note
41 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | To purchase a Refrigerator by 31 March 2016 | Refrigerator | 01/07/2015 | 31/03/2016 | Director Corp | GLM | Purchase a Refrigirator by 30 June 2016 | 5000 | 0 | Removed during budget adjustement in order to cater for rolled over projects |  |  |  | Delivery note
41 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | To purchase 20 Mobile Filling Unit by 31 March 2016 | Mobile Filing Unit | 01/07/2015 | 31/03/2016 | Director Corp | GLM | Purchase 20 Mobilr filling Unit by 31 March 2016 | 200000 | 0 | Removed during budget adjustement in order to cater for rolled over projects |  |  |  | Delivery note
41 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | To purchase 2 Aqua Cooler Bottles by 31 March 2016 | Aqua Cooler Bottles | 01/07/2015 | 31/03/2016 | Director Corp | GLM | Purchase 2 Aqua Cooler Bottles by 31 March 2016 | 4000 | 0 | Removed during budget adjustement in order to cater for rolled over projects |  |  |  | Delivery note
41 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | To purchase 2 Aqua Cooler by 31 March 2016 | Aqua Cooler | 01/07/2015 | 31/03/2016 | Director Corp | GLM | Purchase 2 Aqua Cooler by 31 March 2016 | 8000 | 0 | Removed during budget adjustement in order to cater for rolled over projects |  |  |  | Delivery note
41 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | To purchase 1 Shredding Machine by 31 March 2016 | Shredding Machine | 01/07/2015 | 31/03/2016 | Director Corp | GLM | Purchase 1 Shredding Machine by 31 March 2016 | 5000 | 0 | Removed during budget adjustement in order to cater for rolled over projects |  |  |  | Delivery note
41 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | To purchase 1 Microwave machine by 31 March 2016 | Microwave machine | 01/07/2015 | 31/03/2016 | Director Corp | GLM | Purchase 1 Microwave machine by 31 March 2016 | 1500 | 0 | Removed during budget adjustement in order to cater for rolled over projects |  |  |  | Delivery note
32 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | To purchase Steel Fence and Gate for Senwamokgope sub-office by 31 March 2016 | Steel Fence and Gate | 01/07/2015 | 31/03/2016 | Director Corp | GLM | Purchase Steel Fence and Gate for Senwamokgope by 31 March 2016 | 20000 | 0 | Removed during budget adjustement in order to cater for rolled over projects |  |  |  | Delivery note
41 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | To purchase 1 Counter (Security Burglar) Registry by 31 March 2016 | Counter for Registry (Security Burglar) | 01/07/2015 | 31/03/2016 | Director Corp | GLM | Purchase 1 Counter (Security burglar) by 31 March 2016 | 15000 | 0 | Removed during budget adjustement in order to cater for rolled over projects |  |  |  | Delivery note
41 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | To purchase 2 URNS for Mokwakwaila and Kgapane by 31 March 2016 | URNS 2 (Mokwakwaila and Kgapane) | 01/07/2015 | 31/03/2016 | Director Corp | GLM | Purchase 2 URNS for Mokwakwaila & Kgapane by 31 March 2016 | 1200 | 0 | Removed during budget adjustement in order to cater for rolled over projects |  |  |  | Delivery note
41 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | To purchase 1 Picture Camera by 30 June 2016 | Picture Camera | 01/07/2015 | 30/06/2016 | Director Corp | GLM | Purchase Picture Camera for Legal by 30 June 2016 | 15000 | 15000 | N/A | Submit specifications to SCM | Advertisement and Appointment of Service Provider | Picture Camera Purchased and delivered | Delivery note
41 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Property Services | To renovate main entrance (Registry and Corps) Foyer | Foyer to the main Interior Design (Registry and Corps) | 01/07/2015 | 31/03/2016 | Director Corp | GLM | Complete renovation of the foyer to Registry & Corps | 150000 | 0 | Removed during budget adjustement in order to cater for rolled over projects |  |  |  | Delivery note

## BSD KPI's
KPA 2 : BASIC SERVICE DELIVERY INDICATORS OUTPUT 2: IMPROVING ACCESS TO BASIC SERVICES, OUTPUT 3: IMPLEMENTATION OF THE COMMUNITY WORKS PROGRAMME
Vote Nr | Strategic Objective | Programme | Measurable Objective | KPI Unit of measure/ Performance Indicator | Baseline / Status | Annual Target (30/06/15) | Budget 2014/2015 | 1st Quarter (1 Jul-30 Sept 2015) | 2nd Quarter (1 Oct -31 Dec 2015) | 3rd Quarter (1 Jan 31 Mar 2016) | 4th Quarter (1 Apr- 3 Jun 2016) | Responsible Person | Evidence required
| Integrated and Sustainable Human Settlement | Spatial Planning | To submit housing demand database to COGHSTA by 31 December 2015 | To submit Housing demand database to CoGHSTA by 31 December 2015 | Database submitted to COGHSTA by the 31 December 2014 | Submit Housing database to CoGHSTA by 31 December 2015 | Operational | N/A | Submission of Housing database to CoGHSTA by 31 December 2015 | N/A | N/A | Director INDEP | Dated proof of submiision to CoGHSTA
| Integrated and Sustainable Human Settlement | Spatial Planning | To ensure that land use applications are processed within 90 days of receipt. | % of land use applications processed (# of applications received / # of land use applications processed) within 90 days of receipt by 30 June 2016. | 80% applications processed | Process applications 100% (# of applications received / # of land use applications processed) within ta financial year | Operational | 100% applications processed (# of applications received / # of land use applications processed) | 100% applications processed (# of applications received / # of land use applications processed) | 100% applications processed (# of applications received / # of land use applications processed) | 100% applications processed (# of applications received / # of land use applications processed) | Director INDEP | Dated register recording land use applications & Land use applications feedback letters
| Access to Sustainable Basic Services | Waste management | Provision of waste removal within the financial year | # of HH with access to refuse removal at least once a week by 30 June 2016. | 4654 HH with access to refuse removal at least once a week | 4654 HH with access to refuse removal at least once a week within a financial year | Operational | 4654 HH with access to refuse removal at least once a week | 4654 HH with access to refuse removal at least once a week | 4654 HH with access to refuse removal at least once a week | 4654 HH with access to refuse removal at least once a week | Director COMM | Rooster/ waste management reports
| Access to Sustainable Basic Services | Electricity | To ensure provision of electricity services | # of HH with access to electricity by 30 June 2016. | 56905HH with access to electricity | 56905HH with access to electricity by 30 June 2016 | Operational | N/A | N/A | N/A | 56905HH with access to electricity | Director INDEP | Electricity/ Finance reports/ Confirmation from Eskom
| Access to Sustainable Basic Services | Waste management | Provision of waste removal within the financial year | To construct Landfill site at Maphalle by 30 June 2016. | Designs for Maphalle Land fill site completed | Complete Maphalle Landfill site Project by 30 June 2016. | R 1 000 000 (Capital) | Specifications submitted to SCM for advertisement | Appointment of service provider | Construction of Guard house, way bridge and , Office block completed and development of 2 dumping cell. | Maphalle Landfill site Project completed by 30 June 2016. | Director COMM | Payment certificates
| Access to Sustainable Basic Services | Roads | To ensure access to municipal roads within the financial year | # of Km of gravel roads upgraded to paving | 75km upgraded by 30 June 2016. | Upgrade 54.4 km,upgraded, Completion stage : project completed and handed-over to the municipality by 30 June 2016 | Capital | Develop specification and submit to SCM unit for advertisement | Advertise and appoint service provider for construction of street paving projects | Layer works completed for 50km | Completion stage : project completed and handed-over to the municipality. | Director INDEP | Handover reports / Practical completion certificate

## BSD Projects
2015/16 CAPITAL WORKS PLAN SUMMARY OF CAPITAL AND OPERATIONAL PROJECTS PER RESPONSIBLE MANAGER
Vote Nr | Region | Key Performance Area | Strategic Objective | Programme | Measurable Objective/ Performance Indicator | Project Name | Start Date | Completion date | Project Owner | Source of funding | Annual Target (30/06/16) | Budget | Adjusted Budget | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | Evidence required
29 | Ward 3 | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | To Construct Storm water channels at Ga-Kgapane by 31 March 2016 | Construction of Ga-Kgapane Storm water channels | 01/07/2015 | 31/03/2016 | Director INDEP | GLM | Complete construction of storm water channels at Ga-Kgapane by 31 March 2016 | 2400000 | 0 | Removed during budget adjustement in order to cater for rolled over projects
29 | Head Office | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | To Purchase pedestrian roller by 31 March 2016 | Pedestrian roller | 01/07/2015 | 31/03/2016 | Director INDEP | GLM | Purchase a pedestrian by 31 March 2016 | 120000 | 0 | Removed during budget adjustement in order to cater for rolled over projects
29 | Head Office | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | To Purchase walker compactor by 31 March 2016 | Purchasing of walker compactor | 01/07/2015 | 31/03/2016 | Director INDEP | GLM | Purchase a Walker compactor by 31 March 2016 | 50000 | 0 | Removed during budget adjustement in order to cater for rolled over projects
29 | Ward 30 | Basic Service Delivery | Access to Sustainable Basic Services | Roads | To Rehabilitate Modjadjiskloof street for 2km by 30 June 2016 | Rehabilitation of Modjadjiskloof street | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Rehabilitate Modjajdiskloof street for 2km. by 30 June 2016 (Project completed) | 4000000 | 4000000 | Develop specification and submit to SCM unit for procurement | Advertise and appoint service provider for Rehabilitation of Modjadjiskloof Street | Layer works completed for 2km | Project Completed | Progress report, Completion certificate
29 | Ward 3 | Basic Service Delivery | Access to Sustainable Basic Services | Roads | To Rehabilitate street at Ga-Kgapane for 2km by 30 June 2016 | Rehabilitation of Ga-Kgapane street | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Rehabilitate Ga-Kgapane street for 2km by 30 June 2016 (Project completed) | 4000000 | 9094539 | Develop specification and submit to SCM unit for advertisement | Advertise and appoint service provider for construction of Rehabilitation of Ga-Kgapane street | Layer works completed for 2km | Project Completed | Progress report, Completion certificate
29 | Ward 12 | Basic Service Delivery | Access to Sustainable Basic Services | Roads | To Plan and Design a street paving (for 1.8km) for Itieleng-Sekgosese by 30 June 2016 | Itieleng- Sekgosese Street Paving (Consultants) | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete Designs for Itieleng-Sekgosese street to pave by 30 June 2016 (Project completed) | 5300000 | 450000 | Advertise tender to appoint contractors | Appoint service provider for construction of Itieleng- Sekgosese Street Paving | Earthworks completed and layer works completed for 1km | Project Completed | Progress report, Completion certificate
29 | Ward 22 | Basic Service Delivery | Access to Sustainable Basic Services | Roads | To Upgrade Refilwe street from gravel to concrete paving blocks for 1.8km by 30 June 2016 | Refilwe Street Paving | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Upgrade Refilwe street to pave for 1.8km by 30 June 2016 (Project completed) | 5300000 | 7353800 | Advertise tender to appoint contractors | Appoint service provider for construction of Refilwe Street Paving | Earthworks completed and layer works completed for 1km | Project Completed | Progress report, Completion certificate
29 | Ward 7 | Basic Service Delivery | Access to Sustainable Basic Services | Roads | To Upgrade Mmamakata Raseleka street paving from gravel to concrete paving blocks f for 1.8km by 30 June 2016 | Mmamakata Raselaka Street Paving | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Upgrade Mmamakata Raselaka street to pave for 1.8km by 30 June 2016 (Project completed) | 5300000 | 7558500 | Advertise tender to appoint contractors | Appoint service provider for construction of Mmamakata Raselaka Street Paving | Earthworks completed and layer works completed for 1km | Project Completed | Progress report, Completion certificate
29 | Ward 14 | Basic Service Delivery | Access to Sustainable Basic Services | Roads | To plan and design a street paving (for 1.8km) at Lemondokop by 30 June 2016 | Lemondokop Street Paving (Consultatnts) | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete Designs for Lemondokop street paving by 30 June 2016 | 5000000 | 450000 | Advertise tender to appoint contractors | Appoint service provider for construction of Lemondokop Street Paving | Earthworks completed and layer works completed for 1km | Project Completed | Progress report, Completion certificate
29 | Ward 10 | Basic Service Delivery | Access to Sustainable Basic Services | Roads | To Upgrade Sekgopo street from gravel to concrete paving for 1.8km by 30 June 2016 | Sekgopo street paving | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Upgrade Sekgopo street to pave for 1.8km by 30 June 2016 (Project completed) | 700000 | 700000 | Develop terms of reference and submit to SCM for advertisement | Advertise and appoint service providers for planning of Goedplaas Community Hall project | Appoint service provider. Technical report and preliminary designs submitted | Designs completed and advertise for construction | Completion certificate
29 | Ward 16 | Basic Service Delivery | Access to Sustainable Basic Services | Roads (MIG) | To upgrade Sephukubye street from gravel to concrete paving blocks for 1.8km by 30 June 2016 | Sephukhubje Street Paving | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | Upgrade Sephukubye street to pave for 1.8km by 30 June 2016 (Project completed) | 4210240 | 7178214 | Advertise tender to appoint contractors | Appoint service provider for construction of Sephukhubje Street Paving | Earthworks completed and layer works completed for 1km | Project Completed | Progress report, Completion certificate
29 | Ward 7 | Basic Service Delivery | Access to Sustainable Basic Services | Roads (MIG) | To Upgrade Seatlaleng street from gravel to concrete paving blocks for 1.8km by 30 June 2016 | Seatlaleng Street Paving | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | Upgrade Seatlaleng street to pave for 1.8km by 30 June 2016 | 6000000 | 4580000 | Advertise tender to appoint contractors | Appoint service provider for construction of Seatlaleng Street Paving | Earthworks completed and layer works completed for 1km | Project Completed | Progress report, Completion certificate
29 | Ward 21 | Basic Service Delivery | Access to Sustainable Basic Services | Roads (MIG) | To Upgrade Mohlaking street from gravel to concrete paving blocks for 1.8km by 30 June 2016 | Mohlakong Street paving | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | Upgrade Mohlakong street to pave for 1.8km by 30 June 2016 (Project completed) | 6000000 | 5637754 | Advertise tender to appoint contractors | Appoint service provider for construction of Mohlakong Street paving | Earthworks completed and layer works completed for 1km | Project Completed | Progress report, Completion certificate
29 | Ward 21 | Basic Service Delivery | Access to Sustainable Basic Services | Roads (MIG) | To Upgrade Matshelapata street from gravel to concrete paving blocks for 1.8km by 30 June 2016 | Matshelapata Street Paving | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | Upgrade Refilwe street to pave for 1.8km by 30 June 2016 (Project completed) | 6000000 | 5395061 | Advertise tender to appoint contractors | Appoint service provider for construction of Matshelapata Street Paving | Earthworks completed and layer works completed for 1km | Project Completed | Progress report, Completion certificate
29 | Ward 20 | Basic Service Delivery | Access to Sustainable Basic Services | Roads (MIG) | To Upgrade Shawela street from gravel to concrete paving blocks for 1.8km at Shawela by 30 June 2016 | Shawela Street Paving | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | Upgrade Shawela street to pave for 1.8km by 30 June 2016 (Project completed) | 6000000 | 5240360 | Advertise tender to appoint contractors | Appoint service provider for construction of Shawela Street Paving | Earthworks completed and layer works completed for 1km | Project Completed | Progress report, Completion certificate
29 | Ward 10 | Basic Service Delivery | Access to Sustainable Basic Services | Roads (MIG) | To Upgrade Sekgopo-Maboying street from gravel to concrete paving blocks for 1.8km by 30 June 2016 | Sekgopo-Maboying Street Paving | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | Upgrade Sekgopo Maboying street to pave for 1.8km by 30 June 2016 (Project completed) | 6000000 | 6068805 | Advertise tender to appoint contractors | Appoint service provider for construction of Sekgopo-Maboyini Street Paving | Earthworks completed and layer works completed for 1km | Project Completed | Progress report, Completion certificate
29 | Ward 27 | Basic Service Delivery | Access to Sustainable Basic Services | Roads (MIG) | To Upgrade Thlothlokwe street from gravel to concrete paving blocks for 1.8km by 30 June 2016 | Thlothlokwe street paving | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | Upgrade Thlothlokwe street to pave for 1.8km by 30 June 2016 (Project completed) | 6000000 | 3584534 | Advertise tender to appoint contractors | Appoint service provider for construction of Thlothlokwe street paving | Earthworks completed and layer works completed for 1km | Project Completed | Progress report, Completion certificate
29 | Ward 25 | Basic Service Delivery | Access to Sustainable Basic Services | Roads (MIG) | To Upgrade shamfana street from gravel to concrete paving blocks for 1.8km by 30 June 2016 | Shamfana Street Paving | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | Upgrade Shamfana street to pave for 1.8km by 30 June 2016 (Project completed) | 6000000 | 3400000 | Advertise tender to appoint contractors | Appoint service provider for construction of Shamfana Street Paving | Earthworks completed and layer works completed for 1km | Project Completed | Progress report, Completion certificate
29 | Ward | Basic Service Delivery | Access to Sustainable Basic Services | Roads (MIG) | To Upgrade Kherobeng street from gravel to concrete paving blocks for 1.8km by 30 June 2016 | Kherobeng Street Paving | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | Upgrade Kherobeng street to pave for 1.8km by 30 June 2016 (Project completed) | 6000000 | 2849440 | Advertise tender to appoint contractors | Appoint service provider for construction of Kherobeng Street Paving | Earthworks completed and layer works completed for 1km | Project Completed | Progress report, Completion certificate
20 | Ward | Basic Service Delivery | Access to Sustainable Basic Services | Transport | To Plan and design a taxi rank for Khosotupa by 30 June 2016 | Khosutupa Taxi Rank | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete Designs for Khosuthupa taxi rank by 30 June 2016 (Project completed) | 2000000 | 2000000 | Advertise tender to appoint contractors | Appoint service provider for design and planning of Khosutupa Taxi Rank | Steel structure and toilets completed. Paving complete for 100 square meters | Project Completed | Progress report, Completion certificate
20 | Ward 18 | Basic Service Delivery | Access to Sustainable Basic Services | Transport | To Construct taxi rank at Wholesale by 30 June 2016 | Wholesale Taxi Rank | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete construction for Wholesale Taxi rank( project completed) | 2000000 | 2000000 | Advertise tender to appoint contractors | Appoint service provider for design and planning of Wholesale Taxi Rank | Steel structure and toilets completed. Paving complete for 100 square meters | Project Completed | Progress report, Completion certificate
20 | Ward 8 | Basic Service Delivery | Access to Sustainable Basic Services | Transport | To Construct taxi rank at Mamphakati by 30 June 2016 | Mamphakati Taxi Rank | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete construction of Mamphakathi Taxi rank by 30 June 2016 (Project completed) | 2000000 | 1997600 | Advertise tender to appoint contractors | Appoint service provider for design and planning of Mamphakati Taxi Rank | Steel structure and toilets completed. Paving complete for 100 square meters | Project Completed | Progress report, Completion certificate
20 | Ward 3 | Basic Service Delivery | Access to Sustainable Basic Services | Transport | To Rehabilite Ga-Kgapane Taxi rank, paving extention and storage tank by 30 June 2016 | Ga-Kgapane Taxi Rank, Extention and Storage tank | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Rehabilitate Ga-Kgapane Taxi Rank by 30 June 2016 (project complete) | 480000 | 480000 | Develop specification and submit to SCM unit for advertisement | Avertise and appoint service provider for construction of Ga-Kgapane Taxi Rank | Earthworks, layer works and kerbing completed | Project Completed | Progress report, Completion certificate
14 | Ward 6 | Basic Service Delivery | Access to Sustainable Basic Services | Community services | To Construct Library at Shotong by 30 June 2016 | Shotong Library | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete construction of Shotong library by 30 June 2016 | 2600000 | 0 | Removed during budget adjustement in order to cater for rolled over projects
14 | Ward 28 | Basic Service Delivery | Access to Sustainable Basic Services | Community services | To Construct Library at Rotterdam by 30 June 2016 | Rotterdam Library | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete construction of Library at Rotterdam by 30 June 2016 | 2600000 | 0 | Removed during budget adjustement in order to cater for rolled over projects
32 | Ward 21 | Basic Service Delivery | Access to Sustainable Basic Services | Community services (MIG) | To Construct Library at Mokwakwaila by 30 June 2016 | Mokwakwaila Library | 01/07/2015 | 30/06/2016 | Director COMM | MIG | Complete construction for Mokwakwaila Library by 30 June 2016 (Project completed ) | 1000000 | 1141378 | Advertise tender to appoint contractors | Advertise for construction of Mokwakwaila library | Foundations completed and building at roof level | Project Completed | Completion certificate
32 | Ward 11 | Basic Service Delivery | Access to Sustainable Basic Services | Community services | To Construct a Community Hall at Matshwi by 30 June 2016 | Matshwi Community Hall | 01/07/2015 | 30/06/2016 | Director COMM | GLM | Complete construction for Matshwi Community Hall by 30 June 2016 (Project completed) | 2400000 | 1915000 | Advertise tender to appoint contractors | Appoint service provider for construction of Matshwi Community Hall | Foundations completed and building at roof level | Project Completed | Completion certificate
32 | Ward 26 | Basic Service Delivery | Access to Sustainable Basic Services | Community services | To Construct a Community Hall Mohlele by 30 June 2016 | Mohlele Community Hall | 01/07/2015 | 30/06/2016 | Director COMM | GLM | Complete construction for Mohlele Community Hall by 30 June 2016 (Project completed) | 2400000 | 2064000 | Advertise tender to appoint contractors | Appoint service provider for construction of Mohlele Community Hall | Foundations completed and building at roof level | Project Completed | Completion certificate
32 | Ward 17 | Basic Service Delivery | Access to Sustainable Basic Services | Community services | To Construct a Community Hall Mamaila-Kolobetona by 30 June 2016 | Mamaila - Kolobetona Community Hall | 01/07/2015 | 30/06/2016 | Director COMM | GLM | Complete construction for Mamaila kolobetona Community hall by 30 June 2016 (Project completed) | 2400000 | 2682000 | Advertise tender to appoint contractors | Appoint service provider for construction of Mamaila - Kolobetona Community Hall | Foundations completed and building at roof level | Project Completed | Completion certificate
32 | Ward 17 | Basic Service Delivery | Access to Sustainable Basic Services | Community services | To Construct a Community Hall Rotterdam by 30 June 2016 | Rotterdam Community Hall (Rolled Over) | 01/07/2015 | 30/06/2016 | Director COMM | GLM | Complete construction for Rotterdam Community Hall by 30 June 2016 (Project completed) | 2153554 | 3000000 | Advertise tender to appoint contractors | Appoint service provider for construction of Rotterdam Community Hall | Foundations completed and building at roof level | Project Completed | Completion certificate
32 | Ward 25 | Basic Service Delivery | Access to Sustainable Basic Services | Community services | To Construct a Community Hall Shamfana by 30 June 2016 | Shamfana Community Hall | 01/07/2015 | 30/06/2016 | Director COMM | GLM | Complete construction for Shamfana Community Hall by 30 June 2016 (Project completed) | 2400000 | 2400000 | Advertise tender to appoint contractors | Appoint service provider for construction of Shamfana Community Hall | Foundations completed and building at roof level | Project Completed | Completion certificate
32 | Ward 2 | Basic Service Delivery | Access to Sustainable Basic Services | Community services | To Construct a Community Hall Ward 2 by 30 June 2016 | Ward 2 Community Hall | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete construction of Ward 2 Community by 30 June 2016 (Project completed) | 2400000 | 2400000 | Advertise tender to appoint contractors | Appoint service provider for construction of Ward 2 Community Hall | Foundations completed and building at roof level | Project Completed | Completion certificate
32 | Ward 5 | Basic Service Delivery | Access to Sustainable Basic Services | Community services | To Construct a Community Hall Ward 5 by 30 June 2016 | Ward 5 Community Hall | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete construction for Ward 5 Community Hall by 30 June 2016 (Project completed) | 2400000 | 2400000 | Advertise tender to appoint contractors | Appoint service provider for construction of Ward 5 Community Hall | Foundations completed and building at roof level | Project Completed | Completion certificate
32 | Ward 29 | Basic Service Delivery | Access to Sustainable Basic Services | Contribution from MIG | To Plan and design a community hall forGoedplass by 30 June 2016 | Goedplaas Community Hall | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | Complete construction for Goedplaas Community Hall by 30 June 2016 (Project completed) | 270000 | 135000 | Develop terms of reference and submit to SCM for advertisement | Advertise and appoint service providers for planning of Goedplaas Community Hall project | Appoint service provider. Technical report and preliminary designs submitted | Designs completed and advertise for construction | Technical / Design report
32 | Ward 12 | Basic Service Delivery | Access to Sustainable Basic Services | Contribution from MIG | To Plan and design a community hall for Thakgalane by 30 June 2016 | Thakgalane Community Hall | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | Complete Designs for Thakgalane Community Hall by 30 June 2016 (Project completed) | 270000 | 135000 | Develop terms of reference and submit to SCM for advertisement | Advertise and appoint service provider for planning of Thakgalane Community Hall project | Appoint service provider. Technical report and preliminary designs submitted | Designs completed and advertise for construction | Technical / Design report
32 | Ward 24 | Basic Service Delivery | Access to Sustainable Basic Services | Contribution from MIG | To Plan and design a community hall for Ntata by 30 June 2016 | Ntata Community Hall | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | Complete Designs for Ntata Community Hall by 30 June 2016 (Project completed) | 271000 | 135500 | Develop terms of reference and submit to SCM for advertisement | Advertise and appoint service provider for planning of Ntata Community Hall project | Appoint service provider. Technical report and preliminary designs submitted | Designs completed and advertise for construction | Technical / Design report
32 | Ward 21 & 12 | Basic Service Delivery | Access to Sustainable Basic Services | Community services | To Purchase 2000 Chairs and 10 Tables for Mokwakwaila and Senwamokgope Community Halls by 30 June 2016 | 2000 Chairs and 10 Tables for Mokwakwaila and Senwamokgope Community Halls | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Purchase 2000 Chairs and 10 Tables for Mokwakwaila and Senwamokgope Community Hall by 30 June 2016 (Project completed) | 100000 | 100000 | N/A | Develop, Submit terms of references to SCM. | Advertise and appoint service provider | 2000 chairs and 10 Tables puchased for Mokwakwaila and Senwamokgope Community halls | Delivery note
34 | Ward 27 | Basic Service Delivery | Access to Sustainable Basic Services | Community Services | To Construct a Sports Complex at Mamanyoha by 30 June 2016 | Mamanyoha Sports Complex | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete construction Mamanyoha Sports Complex by 30 June 2016 (Project completed) | 6414503 | 500000 | Advertise tender to appoint contractors | Appoint service provider for construction of Mamanyoha Sports Complex | Fencing, earthworks, toilets and change-rooms completed | Project Completed | Completion certificate
34 | Ward 28 | Basic Service Delivery | Access to Sustainable Basic Services | Community Services | To Construct a Sports Complex at Rotterdam by 30 June 2016 | Rotterdam Sports Complex | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete construction for Rotterdam Sports Complex by 30 June 2016 (Project completed) | 6414503 | 6414503 | Advertise tender to appoint contractors | Appoint service provider for construction of Rotterdam Sports Complex | Fencing, earthworks, toilets and change-rooms completed | Project Completed | Completion certificate
34 | Ward 1 & 6 | Basic Service Delivery | Access to Sustainable Basic Services | Community Services | To plan and design a sports complex for Madumeleng/Shotong by 30 June 2016 | Madumeleng/Shotong Sports Complex | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete Designs for Madumeleng/ Shotong Sports complex by 30 June 2016 (Project completed) | 500000 | 500000 | Develop terms of reference and submit to SCM for advertisement | Advertise and appoint service provider for planning of Madumeleng/Shotong Sports Complex project | Appoint service provider. Technical report and preliminary designs submitted | Designs completed and advertise for construction | Technical / Design report
34 | Ward 12 | Basic Service Delivery | Access to Sustainable Basic Services | Community Services | To Plan and design a Sports Complex for Thakgalane by 30 June 2016 | Thakgalane Sports Complex | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete Designs for Thakgalane Sports Complex by 30 June 2016 (Project completed) | 500000 | 500000 | Develop terms of reference and submit to SCM for advertisement | Advertise and appoint service provider for planning of Thakgalane Sports Complex project | Appoint service provider. Technical report and preliminary designs submitted | Designs completed and advertise for construction | Technical / Design report
71 | Ward 29 | Basic Service Delivery | Access to Sustainable Basic Services | Electricity | To Upgrade electricity infrastructure at Modjadjiskloof for compliance with NER by 31 March 2016 | Upgrade of Electricity to NER Standards in Modjajdiskloof | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Upgrade Electricity to NERSA standards in Modjadjiskloof by 30 June 2016(Project completed) | 1000000 | 5000000 | Develop specification and submit to SCM unit for advertisement | Advertise contractors for upgrading of electricity network | Appoint contractors for the upgrading of electricity | Commence with upgrading and complete the project | Completion certificate
71 | Ward 29 | Basic Service Delivery | Access to Sustainable Basic Services | Street Lighting | To install Energy Efficient Street light in Modjadjiskloof by 31 March 2016 | Energy Efficient Street light in Modjajdiskloof | 01/07/2015 | 31/03/2016 | Director INDEP | GLM | Install Energy efficient street lights in Modjajdiskloof by 30 June 2016 (Project completed) | 500000 | 640000 | Removed during budget adjustement in order to cater for rolled over projects | Advertise contractors for installing Energy street light | Appoint contractors for the installing Energy street light | Commence with upgrading and complete the project | Completion certificate
71 | Ward 29 | Basic Service Delivery | Access to Sustainable Basic Services | Electricity | To install Prepaid Meters in Mokgoba Village by 30 June 2016. | Prepaid meters in Mokgoba village | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Install Prepaid meters in Mokgoba villageby 30 June 2016(Project completed) | 640000 | 500000 | N/A | Develop specification and submit to SCM unit for advertisement | Advertise and appoint Service Provider and Installation commences | Project completed | Progress report
28 | Head Office | Basic Service Delivery | Access to Sustainable Basic Services | Traffic and Licensing | To Purchase Road Block Trailer and Equipment by 30 June 2016. | Road Block Trailer and Equipment | 01/07/2015 | 30/06/2016 | Director COMM | GLM | Purchase Road Block Trailer and Equipment by 30 June 2016(Project completed) | 250000 | 250000 | N/A | Develop specification and submit to SCM unit for advertisement | Advertise and appoint Service Provider | Road Block Trailer purchased | Delivery note
28 | Ward 29 | Basic Service Delivery | Access to Sustainable Basic Services | DLTC | To Purchase and Install Strong Room in Modjadjiskloof by 30 June 2016. | Strong room Modjadjiskloof DLTC | 01/07/2015 | 30/06/2016 | Director COMM | GLM | Purchase and Install Strong room in Modjajdiskloof by 30 June 2016 (Project completed) | 250000 | 250000 | N/A | Develop specification and submit to SCM unit for advertisement | Advertise and appoint of Service Provider | Strong room purchased and installed | Completion certificate
28 | Ward | Basic Service Delivery | Access to Sustainable Basic Services | DLTC | To relocate the DLTCto Senwamokgope Sub Office by 30 June 2016 | Relocation of DLTC tto Senwamokgope | 01/07/2015 | 30/06/2016 | Director COMM | GLM | Relocate DLTC to Senwamokgope by 30 June 2016 (Project completed) | 250000 | 600000 | N/A | Develop specification and submit to SCM unit for advertisement | Advertise and appoint service provider | DLTC relocated to Senwamokgope Sub Office | Completion certificate
28 | Ward 29 | Basic Service Delivery | Access to Sustainable Basic Services | DLTC | To Purchase and Install Cublicles and Bullet proof Glass for the DLTC by 30 June 2016. | Cubicle and Bullet proof Glass for DLTC in Modjajdiskloof | 01/07/2015 | 30/06/2016 | Director COMM | GLM | Purchase and Install Cubicle and Bullet proof glass for DLTC by 30 June 2016 (Project completed) | 250000 | 730000 | N/A | Develop and submit specification to SCM for advertisement | Advertise and appoint service provider | Cubicle and bullet proof Purchased and Installed | Completion certificate
28 | Ward 29 | Basic Service Delivery | Access to Sustainable Basic Services | DLTC | To Complete the Construction of Modjadjiskloof DLTC by 30 June 2016. | Completion of Modjadjiskloof DLTC | 01/07/2015 | 30/06/2016 | Director COMM | GLM | Complete construction for Modjajdiskloof DLTC by 30 June 2016 (Project completed) | 250000 | 450000 | N/A | Develop and submit specification to SCM for advertisement | Advertise and appoint service provider | Modjadjiskloof DLTC completed | Completion certificate
31 | Ward 20 | Basic Service Delivery | Access to Sustainable Basic Services | Waste Management | To Contruct the landfill site at Maphalle village by 30 March 2016. | Maphalle Landfill Site | 01/07/2015 | 30/06/2016 | Director COMM | GLM | Complete Construction for Maphalle Landfill site by 30 June 2016 (Project completed) | 3000000 | 1000000 | N/A | Advertise and appoint service provider for construction | Commence with contruction activities for landfill site | Project Completed | Completion certificate
31 | Ward 29 | Basic Service Delivery | Access to Sustainable Basic Services | Waste Management | To Rehabilite the Old Modjadjiskloof Dumping Site by 30 June 2016. | Modjadjiskloof Dumping site | 01/07/2015 | 30/06/2016 | Director COMM | GLM | Rehabilitate Modjadjiskloof dumping site by 30 June 2016 (Project completed) | 2500000 | 2500000 | N/A | Develop and submit specification to SCM for advertisement | Advertise and appoint service provider | Old Modjadjiskloof Dumping site rehabilitated | Completion certificate
31 | Head Office | Basic Service Delivery | Access to Sustainable Basic Services | Waste Management | To purcahse Swivel Bins by 30 March 2016. | Swivel Bins (7) | 01/07/2015 | 31/03/2016 | Director COMM | GLM | Purchase 7 Swivel bins by 30 March 2016 | 150000 | 0 | Removed during budget adjustement in order to cater for rolled over projects
31 | Head Office | Basic Service Delivery | Access to Sustainable Basic Services | Waste Management | To purchase 10 Skips Bins by 30 June 2016. | Skips Bins (10) | 01/07/2015 | 30/06/2016 | Director COMM | GLM | Purchase (10) Skips Bins by 30 June 2016 | 250000 | 250000 | N/A | Develop and submit specification to SCM for advertisement | Advertsiment and appointment of Service Provider | Skips Bins Purchased | Delivery note
34 | Ward 3 | Basic Service Delivery | Access to Sustainable Basic Services | Parks and Recreation | To Upgrade Ga-Kgapane Parks Below Civic Centre by 30 June 2016 | Ga-Kgapane Parks Below Civic centre | 01/07/2015 | 30/06/2016 | Director COMM | GLM | Upgrade Ga-Kgapane Parks Below civic centre by 30 June 2016 | 300000 | 0 | Removed during budget adjustement in order to cater for rolled over projects
34 | Head Office | Basic Service Delivery | Access to Sustainable Basic Services | Parks and Recreation | To purchase 7 Chain Saws by 30 June 2016 | Chain Saws | 01/07/2015 | 30/06/2016 | Director COMM | GLM | Purchase 7 Chain Saws by 30 June 2016 | 92000 | 60000 | N/A | N/A | Develop and submit specification to SCM for advertisement | Advertise and appoint service provider. Chain Saws purchased and delivered. | Delivery note
34 | Head Office | Basic Service Delivery | Access to Sustainable Basic Services | Sports, Art and Recreation | To purchase Electric Lawn Mower by 31 March 2016 | Electric Lawn Mower | 01/07/2015 | 31/03/2016 | Director COMM | GLM | Purchase Electric Lawn Mower by 31 March 2016 | 20000 | 0 | Removed during budget adjustement in order to cater for rolled over projects
18 | Head Office | Basic Service Delivery | Access to Sustainable Basic Services | Sports, Art and Recreation | To Purchase a Car Trailer by 30 June 2016. | Car Trailer | 01/07/2015 | 30/06/2016 | Director COMM | GLM | Purchase Car Trailer by 30 June 2016 | 30000 | 30000 | N/A | N/A | Develop and submit specification to SCM for procurement | Car Trailer purchased and delivered | Delivery note
34 | Head Office | Basic Service Delivery | Access to Sustainable Basic Services | Sports, Art and Recreation | To Purchase a Drive on Lawn Mower by 30 June 2016. | Drive on Lawn Mower | 01/07/2015 | 30/06/2016 | Director COMM | GLM | Purchase Drive on Lawn Mower by 30 June 2016 | 150000 | 150000 | N/A | N/A | Develop and submit specification to SCM for advertisement | Drive on Lawn Mower purchased and delivered | Delivery note
34 | Ward 29 | Basic Service Delivery | Access to Sustainable Basic Services | Sports, Art and Recreation | To enhance and Beautification of Town Entrances by 30 June 2016. | Town Entrances Beautification | 01/07/2015 | 30/06/2016 | Director COMM | GLM | Complete project for Town Entrances enhancement and Beautification by 30 June 2016 (project completed) | 200000 | 200000 | N/A | Develop and submit specification to SCM for advertisement | Advertisement and appointment of service provider | Town entrances beautification project completed | Completion certificate
38 | Ward 3 | Basic Service Delivery | Access to Sustainable Basic Services | Community Services | To conduct earthworks for Ga-Kgapane new cemetery (Rolled Over) by 30 June 2016. | Ga-Kgapane new Cemetery earthworks | 01/07/2015 | 30/06/2016 | Director COMM | GLM | Conduct Earthworks for Ga-Kgapane new cemetery by 30 June 2016 (Project completed) | 401142 | 140000 | Develop and submit specification to SCM for advertisement | Advertisement and appointment of service provider | Fencing and 280m of concrete beam completed | Project Completed | Completion certificate
38 | Ward | Basic Service Delivery | Access to Sustainable Basic Services | Community Services | To Fence the new cemetery at Ga-Kgapane by 30 June 2016 | Ga-Kgapane New Cemetery Fencing | 01/07/2015 | 30/06/2016 | Director COMM | GLM | Complete Fencing of the new cemetery at Ga-Kgapane by 30 June 2016 (Project completed) | 1000000 | 1000000 | Develop and submit specification to SCM for advertisement | Advertisement and appointment of service provider | Fencing and 280m of concrete beam completed | Project Completed | Completion certificate
18 | Head Office | Basic Service Delivery | Access to Sustainable Basic Services | Community Services | To purchase Disaster Emergency lights by 30 June 2016. | Emergency Disaster Lights | 01/07/2015 | 30/06/2016 | Director COMM | GLM | Purchase Emergency Disaster Lights by 30 June 2016 (Project completed) | 20000 | 20000 | Develop and submit specification to SCM for procurement | Disaster Emergency Lights purchased and delivered | N/A | N/A | Delivery note
39 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | To Purchase and Install Civil Designer Software by 30 June 2016. | Civil Designer Software | 01/07/2015 | 31/03/2016 | Director Corp | GLM | Purchase ans Install Civil Designer software by 30 June 2016 | 100000 | 0 | Removed during budget adjustement in order to cater for rolled over projects
58 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Property services | To Refurbish Municipal Workshop and Stores by 30 June 2016. | Municipal Workshop and Stores | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Refurbish Municipal Workshop and Stores by 30 une 2016 (Project complete) | 500000 | 1100000 | Develop and Submit Specifications to SCM for advertisement | Advertisement for refurbishment of Municipal Workshop refurbished. | Appointment of service provider and commence with refurbishment. | Project Completed | Completion certificate
71 |  | Basic Service Delivery | Access to Sustainable Basic Services | Electricity | To Erect highmast lights at Maapana and Mamphakathi (rolled over) village by 30 June 2016 | Maapana and Mamphakathi Highmast Lights | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Erect Maapana and Mamphakathi Highmast lights by 30 June 2016 (Project Complete) | 401000 | 600000 | N/A | N/A | Appointment of Service provider to erect the Highmast | Highmasts erected | Completion certificate
71 |  | Basic Service Delivery | Access to Sustainable Basic Services | Electricity | To Erect highmast lights at Abel, Mamokgadi, Morwatshehla, Shamfana(rolled over) village by 30 June 2016 | Abel, Mamokgadi, Morwatshehla, Shamfana High Mast | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Erect Abel, Mamokgadi, Morwatshehla and Shamfana Highmast lights by 30 June 2016 (Project Complete) | 298000 | 600000 | N/A | N/A | Appointment of Service provider to erect the Highmast | Highmasts erected | Completion certificate
71 |  | Basic Service Delivery | Access to Sustainable Basic Services | Electricity | To Erect highmast lights at Madibeng Medingen (rolled over) village by 30 June 2016 | Madibeng Medingen High masts lights | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Erect Madibeng Medingen Highmast lights by 30 June 2016 (Project Complete) | 298000 | 1500000 | N/A | N/A | Appointment of Service provider to erect the Highmast | Highmasts erected | Completion certificate
71 |  | Basic Service Delivery | Access to Sustainable Basic Services | Electricity | To Erect highmast lights in Mamaila Kolobetona, Hlabeleng, Tshabela Mmatswale, Itieleng and Thamisa villages(rolled over) village by 30 June 2016 | Mamaila Kolobetona, Hlabeleng, Tshabela Mmatswale, Itieleng and Thamisa High Masts | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Erect Mamaila Kolobetona, Hlabeleng, Tshabela Mmatswale, Itieleng and Tshamisa H Highmast lights by 30 June 2016 (Project Complete) | 2000000 | 2400000 | N/A |  | Appointment of Service provider to erect the Highmast | Highmasts erected | Completion certificate
29 | Ward 29 | Access to Sustainable Basic Services | Stormwater | Storm water | To Design and construct 110m stormwater management channels in Modjadjiskloof by 30 June 2016 | Modjadjiskloof- Channels | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete Designs for Stromwater channels in Modjajdiskloof by 30 June 2016 (Project completed) | 2000000 | 2400000 | Develop and submit terms of reference for Modjadjiskloof Channels to SCM for advertisement | Advertisement of Modjadjiskloof Stormwater Management project on the newspaper and municipal website | Appoint consultants for Modjadjiskloof Stormwater Management project | 110m long Modjadjiskloof Stormwater Management project at construction stage. Excavations complete | Completion certificate
29 |  | Basic Service Delivery | Access to Sustainable Basic Services | Waste Water Management | To Design and construct 488m wide low level bridges at Thabanarshwana by 30 June 2016 | Low Level Bridges( Thabanatshwana ) | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete Designs for wide low level bridge at Thabanatshwana by 30 June 2016 (Project completed) | 1386956 | 1390000 | Submit specifications of low level bridges to SCM for advertisement | Advertise the Tender, Adjudication and Evaluations processes completed | Appointment of service provider and commence with Contsruction. | 488m wide Low Level Bridges at Thabanatshwane and Shamfana villages completed | Completion certificate
29 |  | Basic Service Delivery | Access to Sustainable Basic Services | Waster Water Management | To Design and construct 488m wide low level bridges at Shamfana by 30 June 2016 | Shamfana Low Level bridge | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete Designs for low level bridge at Shamafana by 30 June 2016 (Project completed) | 251301 | 252000 | Submit specifications of low level bridges to SCM for advertisement | Advertise the Tender, Adjudication and Evaluations processes completed | Appointment of service provider and commence with Contsruction. | 488m wide Low Level Bridges at Shamfana villages completed | Progress report, Payment Certificates
29 |  | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | To contruct side walks at Kgapane street by 30 June 2016. | Kgapane Side Walks | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete construction for Kgapane side walks project by 30 June 2016 (Project completed) | 1349069 | 1666022 | Submit specifications for Side walks to SCM for advertisement | Advertise the Tender, Adjudication and Evaluations processes completed | Appointment of service provider and commence with Contsruction. | Kgapane side walks project completed | Progress report, Payment Certificates
29 | Ward 29 | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | To Contruct side walks at Modjajdiskloof streets by 30 June 2016. | Modjadjiskloof Side walks | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete construction for Modjajdiskloof side walks by 30 June 2016 (Project completed) | 1443054 | 2821200 | Submit specifications for Side walks to SCM for advertisement | Advertise the Tender, Adjudication and Evaluations processes completed | Appointment of service provider and commence with Contsruction. | Modjadjiskloof side walks project completed | Progress report, Payment Certificates
29 |  | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | To Contruct an access road at the Existing Mokwakwaila Taxi Rank by 30 June 2016. | Mokwakwaila Taxi Rank (Access road) | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete construction for Mokwakwaila Taxi rank access road by 30 June 2016 (Project completed) | 2748245 | 3100000 | Submit specifications for Side walks to SCM for advertisement | Advertise the Tender, Adjudication and Evaluations processes completed | Appointment of service provider and commence with Contsruction. | Access road at taxi rank side walks project completed | Progress report, Payment Certificates
29 | Ward 10 | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | To supply and Install 480 cubic mtrs gabions at Sekgopo by 30 June 2016. | Sekgopo Gabions | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Supply and Install gabions in Sekgopo by 30 June 2016 (Project completed) | 1089222 | 1200000 | Develop and submit specifications for Sekgopo gabions to SCM to advertise | Advertisement for constructing 480 cubic mtrs gabions at Sekgopo | Appoint service provider for construction of Sekgopo gabions | 480 cubic mtrs Sekgopo gabions complete | Progress report, Payment Certificates
29 |  | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | To Upgrade Medingen street from gravel to concrete paving blocks for 2.0km by 30 June 2016 | Medingen street paving | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Upgrade Medingen street to pave for 2.0km by 30 June 2016 (Project completed) | 152900 | 9500000 | Complete designs for Medingen Street paving and submit to SCM for advertisement | Advertise for construction of Medingen Street paving | Appoint contractors and commence with construction of Medingen Street paving e | Layer works for 2.0km of the paving at MedingenStreet paving complete | Progress report, Payment Certificates
29 |  | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | To Upgrade Sefofotse street from gravel to concrete paving blocks for 1.8km by 30 June 2016 | Sefofotse street paving | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Upgrade Sefofotse street to pave for 1.8km by 30 June 2016 (Project completed) | 4601339 | 1790438 | Complete designs for Sefofotse Street paving and submit to SCM for advertisement | Advertise for construction of Sefofotse Street paving | Appoint contractors and commence with construction of Sefofotse Street paving e | Layer works for 1.8 km of the paving at Sefofotse Street paving i complete | Progress report, Payment Certificates
29 | Ward 29 | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | To Upgrade Hill & Kerk street from gravel to concrete Tar for 0.8km by 30 June 2016 | Hill & Kerk street upgrade | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Upgrade Hill & Kerk street for 0.8km by 30 June 2016 (Project completed) | 4379891 | 4320000 | Complete designs for Hill & Kerk street tarring and submit to SCM for advertisement | Advertise for construction of Hill & Kerk tarring | Appoint contractors and commence with construction of Hill & Kerk Street tarring | Layer works for 0.8km of the paving at Hill & Kerk Street tarring complete | Progress report, Payment Certificates
29 |  | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | To Upgrade Matshwi street from gravel to concrete paving blocks for 1.8km by 30 June 2016 | Matshwi street paving | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Upgrade Matshwi street to pave for 1.8km by 30 June 2016 (Project completed) | 84128 | 1000000 | Complete designs for Matshwi street paving and submit to SCM for advertisement | Advertise for construction of Matshwi Street paving | Appoint contractors and commence with construction of Matshwi Street paving | Layer works for 1.8 km of the paving at Matshwi Street paving icomplete | Progress report, Payment Certificates
29 |  | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | To Upgrade Mothobekgi street from gravel to concrete paving blocks for 1.8km by 30 June 2016 | Mothobekgi street paving | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Upgrade Mothobekgi street to pave for 1.8km by 30 June 2016 (Project completed) | 6992793 | 7000000 | Complete designs for Mothobeki Paving and submit to SCM for advertisement | Advertise for construction of Mothobeki village street paving | Appoint contractors and commence with construction of Mothobeki village | Layer works for 1.8 km of the paving at Mothobeki complete | Progress report, Payment Certificates
29 |  | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | To Upgrade Mmaila Phaphadi street from gravel to concrete paving blocks for 1.8km by 30 June 2016 | Mamaila Phaphadi street paving | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Upgrade Mamaila Phaphadi street to pave for 1.8km by 30 June 2016(Project completed) | 4744289 | 4744289 | Complete designs for Mamaila Phaphadi paving and submit to SCM for advertisement | Advertise for construction of Mamaila Phaphadi village streets paving | Appoint contractors and commence with construction of Mamaila Phaphadi village streets | Layer works for 1.8 km of the paving at Mamaila Phaphadi complete | Progress report, Payment Certificates
29 |  | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | To Upgrade Raphahlelo street from gravel to concrete paving blocks for 1.8km by 30 June 2016 | Raphahlelo Head Kraal paving- roll over (Consultants) | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Upgrade Raphahlelo street for 1.8km by 30 June 216 (Project completed) | 2853215 | 3373171 | Complete designs for Raphahlelo Head Kraal paving and submit to SCM for advertisement | Advertise for construction of Raphahlelo Head Kraal paving | Appoint contractors and commence with construction of Raphahlelo Head Kraal paving | Layer works for 1.8 km of the paving at Raphahlelo Head Kraal paving complete | Progress report, Payment Certificates
29 | Head Office | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | To Purchase and Deliver 2 Tonner Truck with quarter canopy by 30 June 2016. | 2 Toner Truck with quarter canopy | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Purchase 2 Toner Truck with quarter canopy by 30 June 2016 | 320000 | 320000 | Develop, submit specifications for 2-tonner truck to SCM to advertise | Advertisement for purchasing a 2-tonner truck with quarter canopy | Appoint supplier for delivery of a 2-tonner truck with quarter canopy | 2-tonner truck with quarter canopy purchased | Delivery note
29 |  | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | To contruct Market stalls at Maphalle by 30 June 2016. | Maphalle market stalls | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete cnstruction for Market stalls at maphalle by 30 June 2016 (Project completed) | 1197198 | 1400000 | Develop and submit terms of reference to SCM for advertisement of Maphalle Market stalls | Advertise for appointment of professional service provider to design and construct Maphalle Market stalls | Appoint service provider for design and construction of Maphalle Market stalls | Design and construction of Maphalle Market stalls to completion | Progress report, Payment Certificates
29 |  | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | To Upgrade Phooko Head Kraal street from gravel to concrete paving blocks for 1.8km by 30 June 2016 | Phooko head Kraal Paving phase II | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Upgrade Raphahlelo street to pave 1.8km by 30 June 2016 (Project completed) | 2115225 | 3000000 | Complete designs for Phooko Head Kraal paving and submit to SCM for advertisement | Advertise for construction of Phooko Head Kraal Streets paving | Appoint contractors and commence with construction of Phooko Head Kraal Streets | Layer works for 1.8 km of the paving at Phooko Head Kraal complete | Progress report, Payment Certificates
29 | Ward 29 | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | To Contruct gabions at Uitzicht street , Modjadjiskloof by 30 June 2016. | Modjadjiskloof Gabions | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete construction of Gabions in Modjajdiskloof by 30 June 2016 (Project completed) | 1200000 | 1200000 | Develop and submit specifications for Modjadjiskllof gabions to SCM to advertise | Advertisement for constructing 480 cubic mtrs gabions at Modjadjiskllof | Appoint service provider for construction of Modjadjiskllof gabions | 480 cubic mtrs Modjadjiskllof gabions complete | Progress report, Payment Certificates
29 |  | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | To Upgrade Modjadji Ivory Route Phase 1 street from gravel to concrete paving blocks for 1.8km by 30 June 2016 | Modjadji Ivory Route Phase 1 | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Upgrade Modjajdi Ivory Route Phase 1 street 1.8km by 30 June 2016 (Project completed) | 700000 | 700000 | Complete designs for PModjajdi Ivory Route Phase 1 and submit to SCM for advertisement | Advertise for construction of Modjajdi Ivory Route Phase 1 | Appoint contractors and commence with construction of Modjajdi Ivory Route Phase 1 | Layer works for 1.8 km of the paving at Modjajdi Ivory Route Phase 1 | Progress report, Payment Certificates
29 | Ward | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | To Upgrade Rotterdam Mahunisi street from gravel to concrete paving blocks for 0.7km by 30 June 2016 | Rotterdam Mahunisi street paving | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Upgrade Rotterdam Mahunisi street to pave for 1.8km by 30 June 2016 (Project completed) | 28478 | 28500 | Complete designs for Rotterdam Mahunisi street paving and submit to SCM for advertisement | Advertise for construction of Rotterdam Mahunisi street paving | Appoint contractors and commence with construction of Rotterdam Mahunisi street paving | 0.7 km of street paving at Rotterdam Mahunisi street paving | Progress report, Payment Certificates
28 |  | Basic Service Delivery | Access to Sustainable Basic Services | Property services | To Construct Testing room for Learners licesense in Modjajdiskloof by 30 June 2016. | Testing Room for leaners licenses in Modjajdiskloof | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete Contsruction of Testing rooms for leaners s licenses in Modjadjiskloof by 30 June 2016 | 231717 | 259000 | Submit specifications for Testing room for Leaners s License to SCM for advertisement | Advertise the Tender, Adjudication and Evaluations processes completed | Appointment of service provider and commence with Contsruction. | Testing Room for Leaners s Licenses project completed | Progress report, Payment Certificates
29 |  | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | To Upgrade Kuranta street from gravel to concrete paving blocks for 1.2km by 30 June 2016 | Kuranta street paving | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | Upgrade Kuranta street to pave for 1.2km by 30 June 2016 (Project completed) | 888865 | 1488865 | Complete designs for Kuranta paving and submit to SCM for advertisement | Advertise for construction of Kuranta Streets paving | Appoint contractors and commence with construction of Kuranta Streets | 1.2 km of street paving at Kuranta complete | Progress report, Payment Certificates
29 |  | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | To Upgrade Ratjeke street from gravel to concrete paving blocks for 1.8km by 30 June 2016 | Ratjeke street paving | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | Upgrade Ratjeke street to pave for 1.8km by 30 June 2016 (Project completed) | 1080624 | 1080624 | Complete designs for Ratjeke street paving and submit to SCM for advertisement | Advertise for construction of Ratjeke Streets paving | Appoint contractors and commence with construction of Ratjeke Streets | 1.8 km of street paving at Ratjeke streets completed | Progress report, Payment Certificates
29 | Ward 29 | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | To Upgrade Mokgoba street from gravel to concrete paving blocks for 2km by 30 June 2016 | Mokgoba upgrading of streets | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | Upgrade Mokgoba street to pave for 1.6km by 30 June 2016(Project completed) | 5166356 | 5166356 | Complete designs for Mokgoba paving and submit to SCM for advertisement | Advertise for construction of Mokgoba Streets paving | Appoint contractors and commence with construction of Mokgoba Streets | 2 km of street paving at Mokgoba streets completed | Progress report, Payment Certificates
29 |  | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | To Upgrade Modjadji Valley street from gravel to concrete paving blocks for 2km by 30 June 2016 | Modjadji Valley upgrading of streets | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | Upgrade Modjajdi Valley street to pave for 2km by 30 June 2016 (Project completed) | 4380945 | 4380945 | Complete designs for Modjadji Valley paving and submit to SCM for advertisement | Advertise for construction of Modjadji Valley Streets paving | Appoint contractors and commence with construction of Modjadji Valley Streets | 2 km of street paving at Modjadji Valley complete | Progress report, Payment Certificates
29 | Ward 12 | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | To Upgrade Senwamokgope street from gravel to concrete paving blocks for 1.8km by 30 June 2016 | Senwamokgope street paving | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | Upgrade Senwamokgope street to pave for 1.8km by 30 June 2016 (Project completed) | 2588264 | 2588264 | Complete designs for Senwamokgope paving and submit to SCM for advertisement | Advertise for construction of Senwamokgope Streets paving | Appoint contractors and commence with construction of Senwamokgope Streets | Layer works for 1.8 km and 0.9 km of paving blocks at Senwamokgope complete | Progress report, Payment Certificates
29 | Ward 3 | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | To Construct a Stadium at Kgapane Township by 30 June 2016 | Kgapane Stadium | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | Complete Construction of Kgapane Stadium by 30 June 2016 (Project completed) | 822112 | 3828603 | N/A | Submit specifications for Kgapane Stadium to SCM and advertise | Advertisement and appoint for contractor to construct Kgapane Stadium | Complete upgrading of Ga-Kgapane Stadium | Progress report, Payment Certificates
| Ward 12 | Basic Service Delivery | Access to Sustainable Basic Services | Community services | To Construct a Library at Senwamokgope by 30 June 2016 | Senwamokgope Library | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | Complete Designs for Senwamokgope Library by 30 June 2016 (Project completed) | 744074 | 744074 | Complete designs for Senwamokgope Library and submit to SCM for advertisement | Advertise for construction of Senwamokgope library | Appoint contractors for construction of Senwamokgope library | Brick wall and roof for 400m2 Senwamokgope library completed | Progress report, Payment Certificates
| Ward 10 | Basic Service Delivery | Access to Sustainable Basic Services | Community services | To Construct a Library at Sekgopo by 30 June 2016 | Sekgopo Library | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | Complete Designs for Sekgopo Library by 30 June 2016 (Project completed) | 498571 | 498517 | Complete designs for Sekgopo Library and submit to SCM for advertisement | Advertise for construction of Sekgopo library | Appoint contractors for construction of Sekgopo library | Brick wall and roof for 4000m2 Sekgopo library completed | Progress report, Payment Certificates
Note on N2: Refiloe Malungane:

## LED KPI's
KPA 3 : LOCAL ECONOMIC DEVELOPMENT
KEY PERFORMANCE INDICATORS
OUTCOME 9: IMPLEMENTATION OF THE COMMUNITY WORK PROGRAMME
Vote Nr | Strategic Objective | Municipal Programmes | Measurable Objectives | Key Performance measures/ Performance Indicator | KPI Unit of measure | Baseline / Status | Annual Target (30/06/2016) | Budget 2015/16 | 1st Quarter (1 Jul-30 Sept 2015) | 2nd Quarter (1 Oct -31 Dec 2015) | 3rd Quarter (1 Jan 31 Mar 2016) | 4th Quarter (1 Apr- 3 Jun 2016) | Responsible Person | Evidence requires
| Improved Governance and Organisational Excellence | Improved local economy | To ensure Promotion of local economy within the financial year | # of jobs created through municipal s Capital Projects activies by 30 June 2016. | Number | 656 Jobs created | Create 800 Jobs by 30 June 2016 | Operational | 200 Jobs created | 200 Jobs created | 200 Jobs created | 200 Jobs created | Director INDEP | EPWP reports
| Improved Governance and Organisational Excellence | Improved local economy | To ensure Promotion of local economy within the financial year | # of SMME s supported through Sypply Chain Management by 30 June 2016. | Number | New Indicator | Support 120 SMME s by 30 June 2016 | Operational | 30 SMME s supported | 30 SMME s supported | 30 SMME s supported | 30 SMME s supported | CFO | Proof for SMME s supported
| Integrated Sustainable Development | Improved local economy | To ensure Promotion of local economy within the financial year | # of EPWP reports generated and submitted to Council by 30 June 2016. | Number | 12 EPWP reports generated | Generate 12 EPWP reports by 30 June 2016 | Operational | 3 EPWP reports generated | 6 EPWP reports generated | 9 EPWP reports generated | 12 EPWP reports generated | Director INDEP | EPWP reports
| Integrated Sustainable Development | Improved local economy | To ensure Coordination of Agriculture forums within the financial year | # of Agriculture Forums coordinated by 30 June 2016. | Number | 3 Agriculture forums coordinated | Coordinate 4 Agriculture forums by 30 June 2016 | Operational | 1 Agriculture forum coordinated | 1 Agriculture forum coordinated | 1 Agriculture forum coordinated | 1 Agriculture forum coordinated | Director INDEP | Agenda, Minutes & Attendance register
| Integrated Sustainable Development | Marketing/ Branding | To Market municipal initiatives within the financial year | # of Marketing initiatives conducted by 30 June 2016. | Number | 4 Marketing iniatives conducted | Conduct 4 Marketing iniatives by 30 june 2016 | Operational | 1 Marketing iniatives conducted | 1 Marketing iniatives conducted | 1 Marketing iniatives conducted | 1 Marketing iniatives conducted | Director INDEP | proof for marketing initiated

## LED Projects
Vote Nr | Region | Key Performance Area | Strategic Objective | Programme | Measurable Objective/ Performance Indicator | Project Name | Start Date | Completion date | Project Owner | Source of funding | Annual Target (30/06/16) | Budget | Adjusted Budget | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | Evidence required
32 | Ward 10 | Basic Service Delivery | Access to Sustainable Basic Services | Community Services | To Construct Sekgopo Youth Centre by 30 June 2016 | Sekgopo Youth Centre | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete construction of Sekgopo Youth centre by 30 June 2016 | 2250000 | 0 | Removed during budget adjustement in order to cater for rolled over projects
|  | Local Economic Development | Access to Sustainable Basic Services | Community Services | To Construct Ga-Kgapane Youth Centre by 30 June 2016 | Ga-Kgapane Youth Centre | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete construction for Ga-Kgapane Youth Centre by 30 June 2016 | 2250000 | 2 871 00 | Advertise tender to appoint contractors | Appoint contractor to construct Ga-Kgapane Youth Centre | Fencing and foundation completed. Building at roof level | Project Completed | Completion certificate
32 | Ward 3 | Local Economic Development | Access to Sustainable Basic Services | Community Services | To Construct Roerfontein Youth Centre by 30 June 2016 | Roerfontein Youth Centre | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete construction for Roerfontein Youth centre by 30 June 2016 | 2250000 | 2250000 | Advertise tender to appoint contractors | Appoint contractor to construct Roerfontein Youth Centre | Fencing and foundation completed. Building at roof level | Project Completed | Completion certificate
32 | Ward 21 | Local Economic Development | Access to Sustainable Basic Services | Community Services | To Construct Mokwakwaila Youth Centre by 30 June 2016 | Mokwaikwaila Youth Centre | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete construction of Mokwakwaila Youth Centre by 30 June 2016 | 2250000 | 0 | Removed during budget adjustement in order to cater for rolled over projects
32 | Ward 1 | Local Economic Development | Access to Sustainable Basic Services | Community Services | To Construct Madumeleng Old Age Facility by 30 June 2016 | Madumeleng Old Age Facility | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete construction of Madumeleng old age facility by 30 June 2016 | 1800000 | 0 | Removed during budget adjustement in order to cater for rolled over projects
32 | Ward 3 | Local Economic Development | Access to Sustainable Basic Services | Community Services | To Construct Roerfontein Old Age Centre by 30 June 2016 | Roerfontein Old Age Facility centre | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete contsruction for Roerfontein Old Facility centre by 30 June 2016 | 1800000 | 1800000 | Advertise tender to appoint contractors | Appoint contractor to construct Roerfontein Old Age Center | Fencing and foundation completed. Building at roof level | Project Completed | Completion certificate
32 | Ward 3 | Local Economic Development | Access to Sustainable Basic Services | Community Services | To Construct Ga-Kgapane Old Age Facility by 30 June 2016 | Ga-Kgapane Old Age Facility | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete construction of Ga-Kgapane old age facility by 30 June 2016 | 1800000 | 0 | Removed during budget adjustement in order to cater for rolled over projects
32 |  | Local Economic Development | Access to Sustainable Basic Services | Planning and Development | To design and construct fence and admin block at the new show ground by 30 June 2015 | GLM Show Ground (Phase 1) | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete Designs for GLM show by 30 June 2016 | 6000000 | 1000000 | Develop and submit specification to SCM for advertisement | Advertisement and appointment of Service Provider | Appoint Architectures for professional services. | GLM show completed | Completion certificate
| Ward | Local Economic Development | Access to Sustainable Basic Services | Planning and Development | To complete designs for Manokwe cave | Manokwe Cave | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete Designs for Manokwe Cave by 30 June 2016 | 0 | 400000 | Develop and submit specification to SCM for advertisement | Advertisement and appointment of Service Provider | Appoint Architectures for professional services. | Designs for Manokwe Cave completed | Completion certificate
Note on O2: Refiloe Malungane:

## MFMV KPI
KPA 4 MUNICIPAL FINANCIAL VIABILITY KEY PERFORMANCE INDICATORS OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY
Vote Nr | Strategic Objective | Progranmes | Measurable Objectives | Measurable Objective/ Performance Indicator | KPI Unit of measure | Baseline / Status | Annual Target (30/06/15) | Budget 2014/2015 | 1st Quarter (1 Jul-30 Sept 2015) | 2nd Quarter (1 Oct -31 Dec 2015) | 3rd Quarter (1 Jan 31 Mar 2016) | 4th Quarter (1 Apr- 3 Jun 2016) | Responsible Person | Evidence required
| Sustainable Financial Institution | Revenue | To ensure improvement in revenue collection within the financial year | % in revenue collected by 30 June 2016 | Percentage | revenue collection | Improve by 100% in revenue collection within the financial year | Operational | 25% in revenue collection | 50% in revenue collection | 75% in revenue collection | 100% in revenue collection | CFO | Financial reports
| Sustainable Financial Institution | Expenditure Management | Provision of free basic services within the financial year | # of HH receiving free basic services by 30 June 2016 | Number | 835 HH received free basic service | Provide free basic services for 1500 within the financial year | Operational | N/A | N/A | N/A | 1500 HH receiving free basic services | CFO | Updated Indigent register
| Sustainable Financial Institution | Budget and Reporting | To ensure that quartely financial statements are prepared within 14 days after the end of each quarter. | # of quarterly financial statements submitted to Provincial Treasury | Number | 4 financial statements submitted | Submit 4 Financial statements within the financial year | Operational | 1 Financial statement submitted | 1 Financial statement submitted | 1 Financial statement submitted | 1 Financial statement submitted | CFO | Dated proof of submission Financial Statements
| Sustainable Financial Institution | Budget and Reporting | To ensure compliance with legislation within the financial year | To approve Draft 2016/17 Budget by Council on 31 March 2016 | Date | 31/03/2015 | Approve Draft Budget by Council on 31 March 2016 | Operational | N/A | N/A | Approval of Draft Budget by Council on 31 March 2016 | N/A | CFO | Council approved Draft Budget, Council Resolution
| Sustainable Financial Institution | Budget and Reporting | To ensure compliance with legislation within the financial year | To approve Final 2016/17 Budget by council by 31 May 2016 | Date | 31/05/2015 | Approve Final 2016/17 Budget by Council on 31 May 2016 | Operational | N/A | N/A | N/A | Approval of Final 2016/17 Budget by Council on 31 May 2016 | CFO | Council Approved Final Budget, Council Resolution
| Sustainable Financial Institution | Budget and Reporting | To ensure compliance with legislation within the financial year | To approve 2016/17 21 Budget related policies by 31 March 2016 | Date | 31/05/2015 | Approve 2016/17 21 budget related policies by Council on 31 March 2016 | Operational | N/A | N/A | N/A | Approval of budget related policies by Council on 31 March 2016 | CFO | Council Approved Budget related policies, Council Resolution
| Sustainable Financial Institution | Revenue Management | To ensure compliance with legislation within the financial year | To develop, review and adopt Revenue Enhancement Strategy by 30 June 2016 | Document |  | Adopt the Revenue Enhancement Strategy by 30 June 2016. | 30/06/2016 | Gathering of information on the Revenue Enhancemen Stratefy | Coalition of information on the Revenue Enhancement Strategy. | Finalise the Draft Revenue Enhancement Strategy | Adoption by Council of the Revenue Enhancement Strategy by 30 June 2016. | CFO | Council Approved Revenue Enhancement Strategy, Council Resolution
| Sustainable Financial Institution | Budget and Reporting | To ensure compliance with legislation within the financial year | To approve 2015/16 Adjustment budget in council by 28 February 2016 | Date | 28/02/2015 | Approve 2015/16 Adjustement budget in Council by 28 February | Operational | N/A | N/A | Approval of 2015/16 Adjustement budget in Council by 28 February | N/A | CFO | Council approved adjustment budget, Council Resolution
| Sustainable Financial Institution | Budget and Reporting | To ensure compliance with legislation within the financial year | To submit Unaudited financial statements by 31/08/2015 | Date | 30/08/2014 | Submit Unaudited Financial Statements by 31 August 2015. | Operational | Submission of Unaudited Financial Statements by 31 August 2015. | N/A | N/A | N/A | CFO | Dated proof of submission of Unaudited AFS
| Sustainable Financial Institution | Budget and Reporting | To ensure compliance with legislation within the financial year | # of Sec 32 Register developed and updated by 30 June 2016. | Number | New Indicator | Develop and update 12 Sec 32 register by 30 June 2016. | Operational | 3 Sec 32 registers developed and updated | 3 Sec 32 registers developed and updated | 3 Sec 32 registers developed and updated | 3 Sec 32 registers developed and updated | CFO | Dated proof of Sec 32 register
| Sustainable Financial Institution | Budget and Reporting | To ensure compliance with legislation within the financial year | To approve Finance 4 by-laws by 31 May 2016 | Date | New Indicator | Approve 4 Finance by-laws by 31 May 2016. | Operational | N/A | N/A | n/a | Approval of 4 Finance by-laws by 31 May 2016. | CFO | Council approved finance by-laws, Council Resolution
| Sustainable Financial Institution | Budget and Reporting | To ensure compliance with legislation within the financial year | # of Finance report compiled within the 2015/16 financial year. | Number | 12 Finance compliance report submitted | Submit 12 Finance compliance reports by 30 June 2016 | Oerational | 3 Finance compliance report submitted | 3 Finance compliance report submitted | 3 Finance compliance report submitted | 3 Finance compliance report submitted | CFO | Financial reports
| Sustainable Financial Institution | Budget and Reporting | To ensure compliance with legislation within the financial year | To submit monthly Sec 71 reports to Provincial treasury within 10 working days by 30 June 2016. | Date | Within 10 working days | Submit monthly Sec 71 reports to Provincial treasury within 10 working days by 30 June 2016. | Operational | Sec 71 reports submitted to Provincial Treasury within 10 working days | Sec 71 reports submitted to Provincial Treasury within 10 working days | Sec 71 reports submitted to Provincial Treasury within 10 working days | Sec 71 reports submitted to Provincial Treasury within 10 working days | CFO | Dated proof of submission
| Sustainable Financial Institution | Supply Chain Management | To Improve financial viability within the financial year | To appoint Supply Chain Structures( Bid Specifications, Evaluation and Bid Specification Committee) Bid Adjudication by 30 June 2016. | Date | 31/07/2014 | Appoint Supply Chain Structures ( Bid Specifications, Evaluation and Bid Specification Committee) by 31 July 2016. | Operational | Appointment of Supply Chain Structures ( Bid Specifications, Evaluation and Bid Specification Committee) by 31 July 2016. | N/A | N/A | N/A | Municipal Manager | Appointment Letters
| Sustainable Financial Institution | Supply Chain Management | To ensure payment of service providers within 30 days of the submission of invoices. | To pay invoices wiithin 30 days of receipt from the supplier within the financial year | Days | Invoices was paid within 30 days of receipt. | Payment of invoices within 30 days of receipt from the supplier within the financial year | Operational | Payment of invoices within 30 days of receipt from the supplier | Payment of invoices within 30 days of receipt from the supplier | Payment of invoices within 30 days of receipt from the supplier | Payment of invoices within 30 days of receipt from the supplier | CFO | Dated proof of payment
| Sustainable Financial Institution | Assets Management | To ensure compliance with legislation within the financial year | # Assets verifications conducted in line with GRAP standards by 30 June 2016. | Number | 2 Assets verifications conducted | Conduct 2 Assets verifications by 30 June 2016 | Operational | 1 Assets verifications conducted | 1 Assets verifications conducted | 1 Assets verifications conducted | 1 Assets verifications conducted | CFO | Quarterly Assets verification reports
| Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality within the financial year | % capital budget spent as approved by Council by 30 June 2016. | Percentage | 70% Budget spent | Spend 100% budget allocated R 148 079 662 , by 30 June 2016 | Capital | 25% Capital Budget R 37 019 915 spent | 50% Capital Budget R 74 039 831 spent | 75% Capital Budget R 111 059 746 spent | 100% budget spent R 148 079 662 | CFO | Financial reports & Payment certfificates
| Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality within the financial year | % MIG expenditure spent by 30 June 2016. | Percentage | 79.53% Budget spent | Spend 100% budget allocated, R 79 402 000, by 30 June 2016 | Capital | 25% MIG expenditure spent R 19 850 500 | 50% MIG expenditure spent R 39 701 000 | 75% MIG expenditure spent R 59 551 500 | 100% budget spent R 79 402 000 | CFO/ INDEP | Financial reports & Payment certfificates
| Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality within the financial year | % FMG expenditure spent by 30 June 2016. | Percentage | 90% Budget spent | Spend 100% budget allocated R 1 983 195, by 30 June 2016 | Operational | 25% FMG Expenditure spent R 495 798 | 50% FMG Expenditure spent R 991 597 | 75% FMG Expenditure spent R 1 487 396 | 100% budget spent R 1 983 195 | CFO | Financial reports & Payment certfificates
| Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality within the financial year | % MSIG expenditure spent 30 June 2016. | Percentage | 100% budget spent | Spend 100% budget allocated, R 930 000 by 30 June 2016 | Operational | 25% MSIG expenditure spent R 232 500 | 50% MSIG expenditure spent R 465 000 | 75% MSIG expenditure spent R 697 500 | 100% budget spent R 930 000 | CFO | Financial reports & Payment certfificates
| Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality within the financial year | % EPWP expenditure spent 30 June 2016. | Percentage | 100% budget spent | Spend 100% budget allocated, R 1 489 000, by 30 June 2016 | Operational | 25% EPWP expenditure spent R 372 250 | 50% EPWP expenditure spent R 744 500 | 75% EPWP expenditure spent R 1 116 750 | 100% budget spent R 1 489 000 | CFO/ INDEP | Financial reports & Payment certfificates
| Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality within the financial year | % FBS expenditure spent 30 June 2016. | Percentage | 100% budget spent | Spend 100% budget allocated R 392 732, by 30 June 2016 | Operational | 25% FBS expenditure spent R 98 183 | 50% FBS expenditure spent R 196 366 | 75% FBS expenditure spent R 294 549 | 100% budget spent R 392 732 | CFO | Financial reports & Payment certfificates

## MFMV Project
2015/16 CAPITAL WORKS PLAN SUMMARY OF CAPITAL AND OPERATIONAL PROJECTS PER RESPONSIBLE MANAGER
Vote Nr | Region | Key Performance Area | Strategic Objective | Programme | Measurable Objective/ Performance Indicator | Project Name | Start Date | Completion date | Project Owner | Source of funding | Annual Target (30/06/16) | Budget | Adjusted Budget | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | Evidence required
50 | Head Office | Municipal Transformation and Development | Sustainable Financial Institution | Office Management | To purchase Money Counting Machine by 31 March 2016 | Money Counting 1 Machine | 01/07/2015 | 31/03/2016 | CFO | GLM | Purchase Money Counting Machine by 31 March 2016 | 3000 | 0 | Removed during budget adjustement in order to cater for rolled over projects
50 | Head Office | Municipal Transformation and Development | Sustainable Financial Institution | Information Technology | To purchase and Install Cash Power System by 30 June 2016 | Cash Power System | 01/07/2015 | 30/06/2016 | CFO | GLM | Purchace and Install Cash Power system by 30 June 2016 | 150000 | 20000 | N/A | Submit specifications to SCM | Advertisement and appointment of Service Provider | Cash Power system purchased and Installed | Completion certificate & Installation Certificate
50 | Head Office | Municipal Transformation and Development | Sustainable Financial Institution | Property | To Construct New Tanks, pumps and shades (rolled over) by 30 June 2016 | New Tanks, pumps and shades | 01/07/2015 | 30/06/2016 | CFO | GLM | Complete Construction for New Tanks, Pumps and shadesby 30 June 2016 | 1000000 | 3850000 | Conduct environmental impact assessment | Contruction of new tanks and pumps | Contruction of new tanks and pumps | Project completed | Completion certificate

## GGPP KPI's
KPA 5 : GOOD GOVERNANCE AND PUBLIC PARTICIPATION KEY PERFORMANCE INDICATORS OUTCOME 9 (OUTPUT 5: DEEPEN DEMOCRACY THROUGH A REFINED WARD COMMITTEE MODEL, OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY)
Vote Nr | Strategic Objective | Programmes | Measurable Objectives | Performance measures/ Indicator | KPI Unit of measure | Baseline | Annual Target (30/06/2016) | Budget 2015/2016 | 1st Quarter (1 Jul-30 Sept 2015) | 2nd Quarter (1 Oct -31 Dec 2015) | 3rd Quarter (1 Jan 31 Mar 2016) | 4th Quarter (1 Apr- 3 Jun 2016) | Responsible Person | Evidence required
| Improved Governance and Organisational Excellence | Council | To ensure functionality of Council committee within the financial year. | # of Council Meetings held by 30 June 2016. | Number | 11 Council meetings held | Hold 4 Council meetings within the financial year | Operational | 1 Council meetings held | 1 Council meetings held | 1 Council meetings held | 1 Council meetings held | Director Corp | Agenda, Minutes & attandance register
| Improved Governance and Organisational Excellence | Council | To ensure functionality of EXCO committee within the financial year. | # of EXCO meetings held by 30 June 2016. | Number | 11 EXCO meetings held | Hold 4 EXCO meetings within the financial year | Operational | 4 EXCO meetings held | 4 EXCO meetings held | 4 EXCO meetings held | 4 EXCO meetings held | Director Corp | Agenda, Minutes & attandance register
| Improved Governance and Organisational Excellence | Committees | To ensure functionality of Council committee within the financial year. | # of Ward Committee reports submitted to the Office of the Speaker by 30 June 2016. | Number | 348 ward committee reports submitted | Submit 348 ward committee reports to Office of the Speaker by 30 June 2016 | Operational | 87 ward committee reports submitted to Office of the Speaker | 87 ward committee reports submitted to Office of the Speaker | 87 ward committee reports submitted to Office of the Speaker | 87 ward committee reports submitted to Office of the Speaker | Manager (Mayors Office) | Agenda, Minutes & attandance register
| Improved Governance and Organisational Excellence | Committees | To ensure functionality of Council within the financial year | # of MPAC meetings held by 30 June 2016. | Number | 14 MPAC meetings held | Hold 12 MPAC meetings within the financial year | Operational | 3 MPAC meetings held | 3 MPAC meetings held | 3 MPAC meetings held | 3 MPAC meetings held | Manager (Mayors Office) | Agenda, Minutes & attandance register
| Improved Governance and Organisational Excellence | Human Resource management | To ensure functionality of Council within the financial year | # of LLF meetings held by 30 June 2016. | Number | 6 LLF meetings held | Hold 12 LLF meetings within the financial year | Operational | 3 LLF meetings held | 3 LLF meetings held | 3 LLF meetings held | 3 LLF meetings held | Director Corp | Agenda, Minutes & attandance register
| Improved Governance and Organisational Excellence | Labour Relations | To ensure functionality of Municipality within the financial year | % in implementation of LLF resolutions by 30 June 2016(# of resolutions taken/ # of resoltions resolved and sign off). | Percentage | 60% of resolutions implemented | Implement 100% in LLF resolutions within the financial year (# of resolutions taken/ # of resolutions implemented). | Operational | 100% resolutions implemented (# of resolutions taken/ # of resoltions implemented). | 100% resolutions implemented (# of resolutions taken/ # of resoltions implemented). | 100% resolutions implemented (# of resolutions taken/ # of resoltions implemented). | 100% resolutions implemented (# of resolutions taken/ # of resoltions implemented). | Director Corp | LLF resolution register & Minutes
| Improved Governance and Organisational Excellence | Public Participation | To ensure public involvement in the IDP review | # of IDP/Budget/ PMS REP Forum meetings held by 30 June 2016. | Number | 5 IDP/Budget/PMS REP Forum meetings held | Hold 5 IDP/Budget/PMS REP Forum meetings by 30 June 2016 | Operational | 1 IDP/Budget/PMS REP Forum meetings held | 1 IDP/Budget/PMS REP Forum meetings held | 1 IDP/Budget/PMS REP Forum meetings held | 2 IDP/Budget/PMS REP Forum meetings held | Director INDEP | Agenda & Attandance register
| Improved Governance and Organisational Excellence | Public Participation | To ensure public involvement in the IDP review within a financial year | # of IDP/Budget/ PMS Steering Committee meetings held by 30 June 2016. | Number | 5 IDP/Budget/PMS Steering Committee meetings held | Hold 5 IDP/Budget/PMS Steering Committee meetings by 30 June 2016 | Operational | 1 IDP/Budget/PMS Steering Committee meetings held | 1 IDP/Budget/PMS Steering Committee meetings held | 1 IDP/Budget/PMS Steering Committee meetings held | 1 IDP/Budget/PMS Steering Committee meetings held | Director INDEP | Agenda & Attandance register
|  | Public Participation | To ensure public involvement in Mayoral Imbizo 's within a financial year | # of Mayoral Imbizos held by 30 June 2016. | Number | 4 Mayoral Imbizo s held | Hold 4 Mayoral Imbizos by 30 June 2016 | Operational | 1 Mayoral Imbizos held | 1 Mayoral Imbizos held | 1 Mayoral Imbizos held | 1 Mayoral Imbizos held | Manager (Mayors Office) | Agenda & Attandance register
| Improved Governance and Organisational Excellence | Internal Audit | To ensure functionality of Audit committee within a financial year | # of Audit Committee meetings held by 30 June 2016. | Number (Accumulative) | 2 Audit Committee meetings held | Hold 4 Audit Committee meeting by 30 June 2016 | Operational | 1 Audit Committee meetings held | 1 Audit Committee meetings held | 1 Audit Committee meetings held | 1 Audit Committee meetings held | Municipal Manager | Agenda, Minutes & Attandance register
| Improved Governance and Organisational Excellence | Risk | To ensure functionality of Risk committee within the financial year. | # of Risk Committee meetings held by 30 June 2016. | Number (Accumulative) | 3 Risk Committee meeting held | Hold 4 Risk Committee meetings by 30 June 2016 | Operational | 1 Risk Committee meetings held | 1 Risk Committee meetings held | 1 Risk Committee meetings held | 1 Risk Committee meetings held | Municipal Manager | Agenda, Minutes & Attandance register
| Improved Governance and Organisational Excellence | Risk | To ensure functionality of Risk committee within the financial year. | To approved Fraud and Anti Coruption strategy by 30 June 2016. | Number | New Indicator | Approve Fraud and Anti Corruption strategy by 30 June 2016 | Operational | N/A | N/A | N/A | Approved Fraud and Anti Corruption strategy | Municipal Manager | Approved Fraud and Anti Corruption strategy
| Improved Governance and Organisational Excellence | Internal Audit | To conduct quarterly assessment on municipal performance information. | # of performance audit reports issued by 30 June 2016. | Number | 2 Performance audit reports issued | Issue 4 Performance audit reports by 30 June 2016 | Operational | 1 Performance audit reports issued | 1 Performance audit reports issued | 1 Performance audit reports issued | 1 Performance audit reports issued | Municipal Manager | Performance Audit report tabled in council and resolution
| Improved Governance and Organisational Excellence | Internal Audit | To develop annual year internal audit plan and implement by 30 June 2016. | To approve audit plan and % of the IA plan implementation by 30 June 2016.. | Percentage | 90% IA plan Implementation | Implement 100% in Internal Audit plan by 30 June 2016 | Operational | 25% IA plan implementation | 50% IA plan implementation | 75% IA plan implementation | 100% IA plan implementation | Municipal Manager/ All Directors | Approved Internal Audit plan
| Improved Governance and Organisational Excellence | Internal Audit | To attain Clean Audit by ensuring compliance to all governance; financial management and reporting requirements by 12 December 2015 | % of internal audit issues resolved (# of Internal Audit issues resolved / # of issues raised) by 30 June 2016. | Percentage | 60% internal audit issues resolved | Resolve 100% in internal audit issues by 30 June 2016 | Operational | 25% internal audit issues resolved | 50% internal audit issues resolved | 75% internal audit issues resolved | 100% internal audit issues resolved | Municipal Manager/ All Directors | Proof of Internal Audit issues resolved
| Improved Governance and Organisational Excellence | Internal Audit | To attain Clean Audit by ensuring compliance to all governance; financial management and reporting requirements by 30 June 2016 | % in Addressing Audit quesries (2014/15) by 30 June 2016. | Percentage | 90% Audit querries addresed | Address 100% in Audit querries by 30 June 2016 | Operational | N/A | N/A | 50% AG issues resolved | 100% AG issues resolved | Municipal Manager/ All Directors | resolved AG issues and POE 's submitted
| Improved Governance and Organisational Excellence | Risk management | To ensure efffective implementation of risk mitigations actions 30 June 2016. | % of Risk issues resolved (# Risk issues implemented / resolved / # of risks identified) by 30 June 2016. | Percentage | 80% Risk issues resolved | Resolve 100% in Risk issues by 30 June 2016 | Operational | 25% Risk issues resolved | 50% Risk issues resolved | 75% Risk issues resolved | 100% Risk issues resolved | Municipal Manager/ All Directors | Resolved Risk issues and POE submitted

## GGP Projects
2015/16 CAPITAL WORKS PLAN SUMMARY OF CAPITAL AND OPERATIONAL PROJECTS PER RESPONSIBLE MANAGER
Vote Nr | Region | Key Performance Area | Strategic Objective | Programme | Measurable Objective/ Performance Indicator | Project Name | Start Date | Completion date | Project Owner | Source of funding | Annual Target (30/06/16) | Budget | Adjusted Budget | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | Evidence required
28 | Head Office | Basic Service Delivery | Access to Sustainable Basic Services | Traffic and Licensing | To purchase 2 Traffic Blue Lights by 30 June 2016 | Traffic Blue Lights | 01/07/2015 | 30/06/2016 | Director COMM | GLM | Purchase 2 Traffic Lights by 30 June 2016 | 10000 | 5000 | N/A | N/A | Develop and submit specification to SCM for procurement | 2 Traffic Lights purchased and Delivered | Delivery note
28 | Head Office | Basic Service Delivery | Access to Sustainable Basic Services | Traffic and Licensing | To Purchase 6 Stop Watchers by 30 June 2016. | Stop Watchers | 01/07/2015 | 30/06/2016 | Director COMM | GLM | Purchase 6 Stop Watchers by 30 June 2016 | 5000 | 10000 | N/A | N/A | Develop and submit specification to SCM for procurement | 6 Stop Watchers purchased and delivered | Delivery note
18 | Head Office | Basic Service Delivery | Access to Sustainable Basic Services | Community Services | To purchase Fire 12 Extinguisher by 30 June 2016 | Fire Extinguishers | 01/07/2015 | 30/06/2016 | Director COMM | GLM | Purchase Fire Extinguishers by 30 June 2016 | 300000 | 300000 | N/A | Develop and submit specification to SCM for advertisement | Advertisement and appointment of Service Provider | Fire Extinguishers purchased and delivered | Delivery note
41 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | To purchase 4 Suggestion Boxes by 30 June 2016 | Suggestion Boxes | 01/07/2015 | 30/06/2016 | Director Corp | GLM | Purchase 4 Suggestion Boxes by 30 June 2016 | 60000 | 60000 | N/A | Submit specifications to SCM | Advertisement and Appointment of Service Provider | Suggestion Boxes purchased and delivered | Delivery note
41 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | To purchase 4 Batho-Pele Banners by 30 June 2016. | Batho-Pele Banners | 01/07/2015 | 31/03/2016 | Director Corp | GLM | Purchase 4 Batho-Pele banners by 30 June 2016 | 15000 | 0 | Removed during budget adjustement in order to cater for rolled over projects
41 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | To purchase 10 Folding Tables by 31 March 2016 | 10 Folding Tables | 01/07/2015 | 31/03/2016 | Director Corp | GLM | Purchase 10 Folding tables by 31 March 2016 | 10000 | 0 | Removed during budget adjustement in order to cater for rolled over projects
40 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | To purchase 1 Podium by 31 December 2015 | Podium | 01/07/2015 | 31/12/2015 | Manager Mayors Office | GLM | Purchase 1 Podium by 31 December 2015 | 10000 | 0 | Removed during budget adjustement in order to cater for rolled over projects
40 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Property Services | To decorate Council Chamber by 30 June 2016 | Council Chamber decoration | 01/07/2015 | 30/06/2016 | Director Corps | GLM | Decorate Council Chamber by 30 June 2016 | 700000 | 311000 | N/A | N/A | Develop and Submit Specifications to SCM for advertisement, Advertise and appoint service provider | Council Chamber decorated | Completion certificate
40 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Property Services | To fence and pave Kgapane Old Sub Office by 30 June 2016 | Fencing and paving of Kgapane Old Sub Office (rolled over) | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete fencing and paving at Kgapane Old sub Office by 30 June 2016 | 104320 | 161000 | Submit specifications for Side walks to SCM for advertisement | Advertise the Tender, Adjudication and Evaluations processes completed | Appointment of service provider and commence with Construction. | Fencing and paving at Kgapane Old sub Office completed | Completion certificate, Progress report
40 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Property Services | To rehabilitate Rotaba Cottages by 30 June 2016. | Rehabilitation of Rotaba Cottages | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Rehablilitate Rotaba Cottages by 30 June 2016 | 500000 | 500000 | Submit specifications for Side walks to SCM for advertisement | Advertise the Tender, Adjudication and Evaluations processes completed | Appointment of service provider and commence with Construction. | Rehablilitation of Rotaba Cottages completed | Completion certificate, Progress report
40 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Property Services | To renovate Mokwakwaila Sub office by 30 June 2016. | Renovation of Mokwakwaila Sub Office | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete Renovation of Mokwaikwaila Sub Office by 30 June 2016 | 500000 | 500000 | Submit specifications for Side walks to SCM for advertisement | Advertise the Tender, Adjudication and Evaluations processes completed | Appointment of service provider and commence with Construction. | Renovation of Mokwaikwaila Sub Office completed | Completion certificate, Progress report
40 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Property Services | To Contruct Parking at Municipal Offices by 30 June 2016. | Parking at municipal Offices | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete contsruction of Parking at MunicipalOffices by 30 June 2016 | 45357 | 46000 | Submit specifications for Side walks to SCM for advertisement | Advertise the Tender, Adjudication and Evaluations processes completed | Appointment of service provider and commence with Construction. | Parking at MunicipalOffices completed | Completion certificate, Progress report
40 | Head Office | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Property Services | To renovate Registry & Corporate services roof by 30 June 2016. | Renovation of Registry & Corporate services roof | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | Complete Renovation of Registry & Corporate Services roof completed | 15000 | 15000 | Submit specifications for Side walks to SCM for advertisement | Advertise the Tender, Adjudication and Evaluations processes completed | Appointment of service provider and commence with Construction. | Renovation of Registry & Corporate Services roof completed | Completion certificate, Progress report

## MFMV PROJECTS (hidden)
KPA 4 MUNICIPAL FINANCIAL VIABILITY PROJECTS OUTCOME NINE (OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY)
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project / Initiative | Budget 2014/2015 | Budget 2014/2015 | Start Date | Completion Date | Milestones Qtr Ending Sept 2014 | Milestones Qtr Ending Dec 2014 | Milestones Qtr Ending March 2015 | Milestones Qtr Ending June 2015 | Project Owner
50 | Sustainable Financial Institution | Budget and Treasury | Installation of GPS system and training of end users by 31 March 2015 | GPS system and training | 80000 | 80000 | 01/07/2014 | 31/03/2015 | Tender advertisement for supply, delivery and training | Appointment of service provider to supply, instal and conduct training | Installation of GPS systems and training completed | n/a | CFO
50 | Sustainable Financial Institution | Budget and Treasury | Installation of security glass at Senwamokgope sub-office by 30 September 2014 | Security glass at Senwamokgope sub office | 8000 | 8000 | 01/07/2014 | 30/09/2014 | Request quatations for procurement, appoint service provider, supply and installation of security glass | n/a | n/a | n/a | CFO
50 | Sustainable Financial Institution | Budget and Treasury | To conduct environmental impact assessment, purchase new tanks, pumps and shades by 31 March 2015 | New tanks, pumps and shades | 550000 | 1300000 | 01/07/2014 | 31/03/2015 | Tender advertisement and appointment. | Conduct environmental impact assessment | tanks, pumps and shades purchased and environmental impact assessments conducted | n/a | CFO
54 | Access to Sustainable Basic Services | Property Services | To purchase 1 concrete mixer by 30 September 2014 | Concrete Mixer | 20000 | 65000 | 01/07/2014 | 30/09/2014 | Develop, submit specifications to SCM and purchase, 1 cocrete mixer purchased | n/a | n/a | n/a | INDEP / B & T
52 | Access to Sustainable Basic Services | Electricity Distribution | Purchasing of electrical tools and equipment by 30 September 2014 | Tools and equipment | 200000 |  | 01/07/2014 | 30/09/2014 | Develop, submit specifications to SCM and purchase, electrical tools and equipment purchased. | n/a | n/a | n/a | INDEP / B & T
50 | Sustainable Financial Institution | Indigent Management | To register qualifying indigents 30 June 2014 | Updating of Indigent Register | Operational | Operational | 01/07/2014 | 30/06/2015 | Collection of information on indigent households and update the register | Collection of information on indigent households and update the register | Collection of information on indigent households and update the register | qualifying indigent registered in the indigent register | CFO
50 | Sustainable Financial Institution | Revenue Management | Review, adopt and implement Revenue Enhancement Strategy 30 June 2015 | Revenue Enhancement Strategy | Operational | Operational | 01/07/2014 | 30/06/2015 | Review and adoption of Draft Revenue Enhancement Strategy | Implementation of the adopted Revenue Enhancement Strategy | Implementation of the adopted Revenue Enhancement Strategy | Revenue Emhancement strategy reviewed, adopted and implemented | CFO
50 | Sustainable Financial Institution | Revenue Management | To update household billing system information 30 Sept 2014 and implement | Data cleansing | Operational | Operational | 01/07/2014 | 30/06/2015 | Update households information on billing system | Approval by Council | Implement cleased database | Household billing sytem information updated | CFO
50 | Sustainable Financial Institution | Asset Management | To monitor the process of unbundling and make progress report by 30 June 2015 | Unbundling of Infrastructure Assets to update the asset register | Operational | Operational | 01/07/2014 | 30/06/2015 | Tender advertisement | Appointment of professional service provider for unbundling of municipal assets and updating of GRAP compialnt asset register. | Continuation of Unbundling of new municipal assets and updating of GRAP compliant asset register | Completion of compilation of GRAP compliant asset register | CFO
50 | Sustainable Financial Institution | Asset Management | o | Valuation Roll | Operational | Operational | 01/07/2014 | 30/06/2015 | Conduct assessment of supplementary valuation roll. | Conduct assessment of supplementary valuation roll. | Complete assessment of supplementary valuation roll | Approval of valuation roll by Council | CFO

## GGPP PROJECTS (hidden)
KPA 5 GOOD GOVERNANCE AND PUBLIC PARTICIPATION PROJECTS OUTPUT 5: DEEPEN DEMOCRACY THROUGH A REFINED WARD COMMITTEE MODEL, OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY)
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project Description | Original Budget 2014/2015 | Adjusted Budget 2014/2015 | Start Date | Completion Date | Milestones Qtr Ending Sept 2014 | Milestones Qtr Ending Dec 2014 | Milestones Qtr Ending March 2015 | Milestones Qtr Ending June 2015 | Project Owner
34 | Improved Governance and Organisational Excellence | Good Governance | Manage events effectively by 30 June 2015 | Communication and event management | 100000 | 100000 | 01/07/2014 | 30/06/2015 | Manage events and 25% of the budget spent | Manage events and 50% of the budget spent | Manage events and 75% of the budget spent | Manage events and 100% of the budget spent | MM
40 | Improved Governance and Organisational Excellence | Good Governance | To award academic excellent performers by 30 June 2015 | Municipal Mayor’s excellent award | 200000 | 400000 | 01/01/2015 | 31/03/2015 | n/a | n/a | n/a | Excellence award ceremony | MM
34 | Improved Governance and Organisational Excellence | Good Governance | Attending of conference and congresses | Conference and congresses | 100000 | 100000 | 01/07/2014 | 30/06/2015 | Adrehence to procedures and attend conference and congresses | Adrehence to procedures and attend conference and congresses | Adrehence to procedures and attend conference and congresses | Adrehence to procedures and attend conference and congresses | CORPS
46 | Improved Governance and Organisational Excellence | Skills Development/Training | To improve capacity of councillors by 30 June 2015 | Capacity building: councillors | 318600 | 550000 | 01/10/2014 | 30/06/2015 | Identification of councillors | Conduct need analysis and submit specification to SCM | Advertisement of tender and appointment of service provider | 100% councillors trained | CORPS
40 | Improved Governance and Organisational Excellence | Batho Pele | To implement Batho Pele principles by 31 March 2015 | Batho Pele strategies | 30798 | 30798 | 01/10/2014 | 12/12/2014 | n/a | n/a | Oraganise and ecelbrate Bathopele event | n/a | MM
40 | Improved Governance and Organisational Excellence | Bursary Scheme | To fund good performing student from the needy families | Bursary scheme council | R2 000 000 | R2 000 001 | 01/07/2014 | 30/06/2015 | n/a | Advertise for applications and pay costs- Payment of costs | Adjudication of all applications and payments of costs | Payment of costs | MM
54 | Improved Governance and Organisational Excellence | Humanitarian | To enhance humanitarian by 30 June 2014 | Humanitarian Aid | 100000 | 110000 | 01/07/2014 | 30/06/2015 | 25% | 50% | 75% | 100% | MM
40 | Improved Governance and Organisational Excellence | Communication | To issue 4 newsletters by 30/06/2015 | News letter | 350000 | 200000 | 01/07/2014 | 30/06/2015 | 1 | 1 | 1 | 1 | MM
40 | Improved Governance and Organisational Excellence | Communication | To purchase calenders and diaries by 30/09/2014 | Calendar and diaries | 20000 | 20000 | 01/07/2014 | 30/09/2014 | 100% | n/a | n/a | n/a | MM
40 | Improved Governance and Organisational Excellence | MM | Purchasing of Council vehicle for the Speaker by 31 March 2015 | Council Vehicle for the speaker | 700000 |  | 01/09/2014 | 31/09/2014 | Develop specifications and submit to SCM. Advertise and appointment of service providers | vehicle for the Speaker purchased | n/a | n/a | MM
40 | Improved Governance and Organisational Excellence | MM | Purchasing of two (2) gazebos by 30 September 2014 | 2 x Gazebos | 40000 | 40000 | 01/07/2014 | 30/09/2014 | Sourcing of quatations and appointment of service provider for supply , 2 Gazebos purchased | n/a | n/a | n/a | MM
40 | Improved Governance and Organisational Excellence | MM | Purchasing of a scanner by 30 September 2014 | Scanner | 5000 | 5000 | 01/07/2014 | 30/09/2014 | Sourcing of quatations and appointment of service provider for supply , Scanner purchased | n/a | n/a | n/a | MM
40 | Improved Governance and Organisational Excellence | MM | Purchasing of a Cooler box by 30 September 2014 | Cooler box | 5000 | 5000 | 01/07/2014 | 30/09/2014 | Sourcing of quatations and appointment of service provider for supply, Cooler box purchased | n/a | n/a | n/a | MM
54 | Improved Governance and Organisational Excellence | Property Services | Purchasing of 5 Aqua Coolers by 30 September 2014 | 5x Aqua coolers | 15000 | 15000 | 01/07/2014 | 30/09/2014 | Sourcing of quatations and appointment of service provider for supply, 5 Aqua Coolers purchased | n/a | n/a | n/a | CORPS
54 | Improved Governance and Organisational Excellence | Property Services | Purchasing of shredding machine for registry by 30 September 2014 | Shredding machine for registry | 8000 | 20000 | 01/07/2014 | 30/09/2014 | Sourcing of quatations and appointment of service provider for supply, Shredding machine purchased | n/a | n/a | n/a | MM
40 | Improved Governance and Organisational Excellence | Special Programmes | To facilitate youth development activities by 30 June 2015 | Youth desk activities | 280000 | 180000 | 01/07/2014 | 30/06/2015 | Develop youth desk activity program | facilitate youth development activities | facilitate youth development activities | facilitate youth development activities | MM
40 | Improved Governance and Organisational Excellence | Special Programmes | To facilitate gender desk activities by 30 June 2016 | Gender desk activities | 200000 | 250000 | 01/07/2014 | 30/06/2015 | Develop Gender desk activity program | facilitate Gender Desl activities | facilitate Gender Desl activities | facilitate Gender Desl activities | MM
54 | Improved Governance and Organisational Excellence | Special Programmes | To facilitate Disability desk activities by 30 June 2017 | Disability desk activities | 100000 | 177000 | 01/07/2014 | 30/06/2015 | Develop Disability desk activity program | facilitate Disability desk activities | facilitate Disability desk activities | facilitate Disability desk activities | MM
40 | Improved Governance and Organisational Excellence | Special Programmes | To facilitate HIV/AIDS Council activities by 30 June 2018 | HIV & AIDS Council activities | 95000 | 60000 | 01/07/2014 | 30/06/2015 | Develop HIV/AIDS Council activity program | Facilitae HIV/AIDS Council activities | Facilitae HIV/AIDS Council activities | Facilitae HIV/AIDS Council activities | MM
40 | Improved Governance and Organisational Excellence | Special Programmes | Supporting initiatives for youth empowerment | Youth empowerment projects | 200000 | 200000 | 01/07/2014 | 30/06/2015 | Support Youth empowerment | Support Youth empowerment | Support Youth empowerment | Support Youth empowerment | MM
14 | Access to Sustainable Basic Services | Libraries and Archives | Planning and designing of library for Shotong village by 30 June 2015 | Shotong Library | 300000 | 300000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Appoint service provider and designs resume | Designs Completed | Designs completed and submitted (Shotong) | INDEP / B & T
14 | Access to Sustainable Basic Services | Libraries and Archives | Planning and designing of library for Rotterdam village by 30 June 2015 | Rotterdam Library | 300000 | 300000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Appoint service provider and designs resume | Designs Completed | Develop, submit terms of reference to SCM and advertise for construction. | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Facilities | To do cemetry layout and fencing at Ga-Kgapane cemetry by 30 June 2015 | Kgapane Cemetry layout and fencing | 1500000 | 3000000 | 01/07/2014 | 30/06/2015 | Develop, submit terms of reference to SCM and advertise. | Appoint service provider | Construction resume | Construction completed | COMM
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of old age facility for Madumeleng village by 30 June 2015 | Madumeleng Old Age Facility | 220000 | 220000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Appoint service provider and designs progress at 30% | Complete designs | Develop, submit terms of reference to SCM and advertise for construction. | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of old age facility for Ga-Kgapane township by 30 June 2015 | Kgapane Old Age Facility | 220000 | 220000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Appoint service provider and designs resume | Complete designs | Develop, submit terms of reference to SCM and advertise for construction. | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of old age facility for Roerfontein village by 30 June 2015 | Roerfontein Old Age Facility | 220000 | 220000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Appoint service provider and designs resume | Complete designs | Develop, submit terms of reference to SCM and advertise for construction. | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Supply and erection of bus shelter at Mokwakwaila - Ga-Kgapane road by 31 March 2015 | Mokwakwaila to Kgapane Bus shelter | 75000 | 75000 | 01/07/2014 | 31/03/2015 | Develop and submit specifications to SCM and advertise | Appoint service provider and erection of bus shelter resume | Erection of bus shelter and complete | n/a | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Supply and erection of bus shelter at Malematsa - Rapitsi road by 31 March 2015 | Rapitsi to Malematsa Bus Shelter | 75000 | 75000 | 01/07/2014 | 31/03/2015 | Develop and submit specifications to SCM and advertise | Appoint service provider and erection of bus shelter resume | Erection of bus shelter and completed | n/a | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Supply and erection of bus shelter at Lemondokop - Mamaila road by 31 March 2015 | Lemondokop to Mamaila via Phooko Bus Shelter | 75000 | 75000 | 01/07/2014 | 31/03/2015 | Develop and submit specifications to SCM and advertise | Appoint service provider and erection of bus shelter resume | Erection of bus shelter and completed | n/a | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Supply and erection of bus shelter at Modjadji Head Kraal by 31 March 2015 | Modjadji Headkraal Bus Shelter | 75000 | 75000 | 01/07/2014 | 31/03/2015 | Develop and submit specifications to SCM and advertise | Appoint service provider and erection of bus shelter resume | Erection of bus shelter and completed | n/a | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Supply and erection of bus shelter at Goudplaats village by 31 March 2015 | Goudplaas Bus Shelter | 75000 | 75000 | 01/07/2014 | 31/03/2015 | Develop and submit specifications to SCM and advertise | Appoint service provider and erection of bus shelter resume. | Erection of bus shelter and completed | n/a | INDEP / B & T
28 | Roads & Transport | Vehicle Licencing and Test | Purchasing of twotraffic Blue lights by 30 September 2014 | Traffic Blue lights (2) | 20000 |  | 1/07/2014 | 30/09/2015 | Appointment of service provider and 2 Traffic Blue lights purchased. | n/a | n/a | n/a | COMM
28 | Roads & Transport | Vehicle Licencing and Test | Construction Of Testing room for learners Licences by 31 March 2015 | Testing room for learners Licence | 300000 |  | 01/07/2014 | 31/03/2015 | Submission of specifications and advertisement for service providers | Appoint service providers and construction resume | Constructio completed | n/a | COMM
28 | Roads & Transport | Vehicle Licencing and Test | Purchasing of Traffic Sedan by 12 December 2014 | Traffic Sedan | 350000 |  | 01/07/2014 | 12/12/2014 | Submission of specifications and advertisement for service providers | Appoint service provider and purchase of Traffic Sedan | n/a | n/a | COMM