## COVER
GREATER LETABA MUNICIPALITY
SERVICE DELIVERY AND BUDGET
IMPLEMENTATION PLAN
2015/16

## INDEX
Table of Contents
Introduction | 2
Legislation | 2
Methodology and Contents | 4
Strategic Vision, Mission and Strategy Map | 5
Votes and Operational Objectives | 6
Municipal Financial projections | 7 to 14
Municipal Transformation and Organisational Development KPI's | 15 to 20
Basic Service Delivery KPI's | 20 to 20
Municipal Financial Viability KPI's | 22 to 25
Good Governance and Public Participation KPI's | 26 to 28
Capital Worksplan | 29 to 38
Approval | 39

## INTR AND LEGISLATION
Introduction | The development, implementation and monitoring of a Service Delivery and Budget Implementation Plan (SDBIP) is required by the Municipal Finance Management Act (MFMA). In terms of Circular 13 of National Treasury, “the SDBIP gives effect to the Integrated Development Plan (IDP) and budget of the municipality and will be possible if the IDP and budget are fully aligned with each other, as required by the MFMA.” As the budget gives effect to the strategic priorities of the municipality it is important to supplement the budget and the IDP with a management and implementation plan. The SDBIP serves as the commitment by the Municipality, which includes the administration, council and community, whereby the intended objectives and projected achievements are expressed in order to ensure that desired outcomes over the long term are achieved and these are implemented by the administration over the next twelve months.
The SDBIP provides the basis for measuring performance in service delivery against quarterly targets and implementing the budget based on monthly projections. Circular 13 further suggests that “the SDBIP provides the vital link between the mayor, council (executive) and the administration, and facilitates the process for holding management accountable for its performance. The SDBIP is a management, implementation and monitoring tool that will assist the mayor, councillors, municipal manager, senior managers and community.” The purpose of the SDBIP is to monitor the execution of the budget, performance of senior management and achievement of the strategic objectives set by council. It enables the municipal manager to monitor the performance of senior managers, the mayor to monitor the performance of the municipal manager, and for the community to monitor the performance of the municipality.
In the interests of good governance and better accountability, the SDBIP should therefore determine and be aligned with the performance agreements of the municipal manager and senior managers. The development, implementation and monitoring of a Service Delivery and Budget Implementation Plan (SDBIP) is required by the Municipal Finance Management Act (MFMA). In terms of Circular 13 of National Treasury, “the SDBIP gives effect to the Integrated Development Plan (IDP) and budget of the municipality and will be possible if the IDP and budget are fully aligned with each other, as required by the MFMA.”
Legislation | According to the Municipal Finance Act (MFMA) the definition of a SDBIP is: 'service delivery and budget implementation plan' means a detailed plan approved by the mayor of a municipality in terms of section 53 (1) (c) (ii) for implementing the municipality's delivery of municipal services and its annual budget, and which must indicate- (a) projections for each month; (i) revenue to be collected by source; (ii) operational and capital expenditure by vote; (b) service delivery targets and performance indicators for each quarter. Section 53 of the MFMA stipulates that the Mayor should approve the SDBIP within 28 days after the approval of the budget. The Mayor must also ensure that the revenue and expenditure projections for each month and the service delivery targets and performance indicators as set out in the SDBIP are made public within 14 days after their approval.
The following National Treasury prescriptions as minimum requirements that must form part of the SDBIP are applicable to the Municipality : (1) Monthly projections of revenue to be collected by source. (2) Monthly projections of expenditure (operating and capital) and revenue for each vote. (3) Quarterly projections of service delivery targets and performance indicators for each vote. (4) Ward information for expenditure and service delivery. (5) Detailed capital works plan broken down per ward for three years. * Section 1 of the MFMA defines a “vote” as: a) One of the main segments into which a budget of a municipality is divided for the appropriation of money for the different departments or functional areas of the municipality; and b) which specifies the total amount that is appropriated for the purposes of the department or functional area concerned.

## METHODOLOGY AND CONTENT
Methodology and Content | National Treasury directives are clear on the contents and methodology to derive at the SDBIP. As a first step, the IDP objectives need to be quantified and related into key performance indicators. The budget is aligned to the objectives, projects and activities to enable the SDBIP to serve as monitoring tool for service delivery. The SDBIP is described as a layered plan. The top layer deals with consolidated service delivery targets and time frames. Top Management is held accountable for the implementation of the consolidated projects and Key Performance Indicators. From the consolidated information, top management is expected to develop the next level of detail by breaking up outputs into smaller outputs and then linking and assigning responsibility to middle-level and junior managers.
The SDBIP of the Greater Letaba Municipality consists of strategic objectives derived from the IDP that are aligned with the strategic intent of the organisation. Strategic indicators with targets are set to measure the objectives. The Municipal Manager takes responsibility for the strategic indicators and objectives which will form part of his/her Performance Agreement and Plan. Projects and activities are aligned to the indicators with quarterly targets, time-frame and budget assigned to each. The Strategic Indicators give rise to the institutional indicators for which the Directors will take responsibility. These indicators will form part of the Performance Agreements and Plans of Senior Managers (Directors). Indicators are assigned quarterly targets and responsibilities to monitor performance. Derived from this, the next layer is developed, whereby the details with responsibilities for the next level of management is outlined and forms part of the Lower SDBIP. This lower SDBIP is a management tool for the S57 Managers and need not be made public and is a separate document for each internal department. The SDBIP serves as a management, implementation and monitoring tool that will assist the Mayor, Councilors, Municipal Manager and Directors in delivering services to the community

## STRATEGY
Vision and Mission | The strategic vision of the organisation sets the long term goal the Municipality wants to achieve. The vision of Greater Letaba Municipality is: "To be an outstanding agro-processing and eco-cultural tourism hub". The strategic mission speaks about what the purpose of Greater Letaba Municipality is: The mission of Greater Letaba Municipality is to ensure an effective, efficient and economically viable municipality through: Provision of accountable, transparent, consultative and co-operative governance. Improving the quality of life through economic development and poverty alleviation. Provision of sustainable services. Ensuring a safe and healthy environment.
Strategy map | The Strategy Map depicts the strategic objectives on how Greater Letaba Municipality will be able to become an outstanding agro-processing and eco-cultural tourism hub while providing sustainable and affordable services to all. These objectives were positioned in terms of the Balanced Scorecard Perspectives being: Learning and Growth; Institutional Processes; Financial results and Community Satisfaction. All operational outputs (projects, initiatives and process) as contained within the SDBIP are aligned to the attainment of one or more of these objectives.

## OPERATIONAL STRATEGIES
Votes and Operational objectives | Votes | Objectives and Targets
| Municipal Manager Office (Vote 0040) | To lead, direct and manage a motivated and inspired administration and account to the Greater Letaba Municipal Council as Accounting Officer for long term municipal sustainability to achieve a good creditor rating within the requirements of the relevant legislation and whereas the following sections within the department, i.e. HIV/Aids, Youth, Disabled and Gender Desk, Communication and Internal Auditing is managed for integration, economic growth, marginalised poverty alleviation, efficient, economic and effective communication and service delivery.
| Finance (Vote 0050) | To secure a sound and sustainable management of the financial affairs of Greater Letaba Municipality by managing the budget and treasury office and advising and if necessary assisting the Accounting Officer and the Directors in their duties and delegation contained in the MFMA. Ensuring that the Greater Letaba Municipality is 100% financially viable when it comes to cost coverage and to manage the grant revenue of the municipality so that no grant funding is foregone
| Community Services (Vote 0028) | To co-ordinate Environmental Health Services, Sports Arts and Culture, Education, Libraries, Safety and Security, Environmental and Waste management, Health and Social development programmes as well as Disaster management to decrease community affected by disasters
| Infrastructure Development and Economic Planning (Votes 0029 and 0022) | To ensure that the service delivery requirements for roads are met and maintenance of water, sewerage and electricity are conducted for access to basic services as well as no less than an average of 100% MIG expenditure
To direct the Greater Letaba Municipality’s resources for advanced economic development and investment growth through appropriate town and infrastructure planning in order that an environment is created whereby all residents will have a sustainable income.
| Corporate Services (Vote 0046 ) | To ensure efficient and effective operation of council services, human resources and management, legal services and the provision of high quality customer orientated administrative systems. Ensuring 100% compliance to the Skills Development Plan.

## Finance projections
Monthly Projections of Revenue for Each Source
Sources of Revenue | 2015 Monthly Projections R'00 | [5 empty] | 2016 Monthly Projections | [5 empty] | Evidence required
| Jul. | Aug. | Sep. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | Apr. | May. | Jun.
Property rates | 495 | 501 | 521 | 489 | 456 | 500 | 618 | 455 | 514 | 465 | 523 | 463 | Billing VS Collection
Service charges-electricity revenue | 1000 | 1200 | 1300 | 1458 | 1500 | 985 | 800 | 1400 | 1500 | 1874 | 1333 | 1650 | Billing VS Collection
Services Charges- refuse revenue | 258 | 300 | 345 | 285 | 299 | 315 | 400 | 421 | 333 | 367 | 333 | 344 | Billing VS Collection
Rental of Facilities and Equipment | 5 | 6 | 5 | 8 | 10 | 15 | 12 | 15 | 14 | 13 | 16 | 10 | Billing VS Collection
Interest earned-external investments | 254 | 268 | 276 | 280 | 291 | 297 | 300 | 301 | 315 | 357 | 421 | 424 | Billing VS Collection
Intersest Earned- Outstanding Debtors | 360 | 354 | 421 | 356 | 425 | 439 | 520 | 648 | 440 | 566 | 651 | 697 | Billing VS Collection
Dividends received | [12 empty] | Billing VS Collection | bar: 2015 Monthly Projections R'00 Jul. to 2016 Monthly Projections Jun.
Fines | 20 | 32 | 15 | 40 | 29 | 32 | 38 | 22 | 15 | 35 | 43 | 32 | Billing VS Collection
Licenses and Permits | 432 | 457 | 394 | 521 | 355 | 490 | 325 | 356 | 540 | 766 | 600 | 641 | Billing VS Collection
Agency services | 100 | 112 | 139 | 152 | 154 | 105 | 168 | 166 | 175 | 186 | 198 | 167 | Billing VS Collection
Transfers recognised- operational | 78145 | _ | _ | _ | 89320 | _ | _ | _ | 45495 | _ | _ | _ | Billing VS Collection
Other Revenue | 147 | 169 | 201 | 222 | 187 | 251 | 269 | 244 | 360 | 378 | 235 | 353 | Billing VS Collection
Transfers recognised- Capital | 21000 | _ | _ | _ | 18000 | _ | _ | _ | 16692 | _ | _ | _ | Billing VS Collection
Total Revenue by Source | 102216 | 3399 | 3616 | 3811 | 111025 | 3429 | 3450 | 4028 | 66394 | 5007 | 4354 | 4780
Monthly Projections of Expenditure (Operating, Capital and Revenue) by vote : First Quarter
Expenditure and Revenue by Vote | 2015 Monthly Projections R'00 Jul.: 2015-07-01; 2015 Monthly Projections R'00 Oct.: 2015-08-01; 2016 Monthly Projections Jan.: 2015-09-01; 2016 Monthly Projections Apr.: Evidence required
| Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex
Executive and Council | _ | 2895 |  | _ | 3003 |  | _ | 3150 | 20 | Financial reports
Budget and Treasury | 24019 | 1652 |  | 30000 | 1800 |  | 31000 | 1236 | 393 | Financial reports
Corporate Services | _ | 1900 |  | _ | 2145 | 150 | _ | 2450 |  | Financial reports
Planning and Development | 2015 Monthly Projections R'00 Jul.: _; 2015 Monthly Projections R'00 Aug.: 850; 2015 Monthly Projections R'00 Oct.: _; 2015 Monthly Projections R'00 Nov.: 1200; 2016 Monthly Projections Jan.: _; 2016 Monthly Projections Feb.: 1452; 2016 Monthly Projections Apr.: Financial reports
Community Services | 2015 Monthly Projections R'00 Jul.: _; 2015 Monthly Projections R'00 Aug.: 230; 2015 Monthly Projections R'00 Oct.: _; 2015 Monthly Projections R'00 Nov.: 216; 2016 Monthly Projections Jan.: _; 2016 Monthly Projections Feb.: 241; 2016 Monthly Projections Apr.: Financial reports
Housing | 2015 Monthly Projections R'00 Jul.: _; 2015 Monthly Projections R'00 Aug.: 45; 2015 Monthly Projections R'00 Oct.: _; 2015 Monthly Projections R'00 Nov.: 36; 2016 Monthly Projections Jan.: _; 2016 Monthly Projections Feb.: 29; 2016 Monthly Projections Apr.: Financial reports
Public Safety | _ | 158 |  | _ | 168 |  | _ | 149 | 320 | Financial reports
Sports and Recreation | _ | 495 |  | _ | 500 |  | _ | 515 | 1500 | Financial reports
Waste Water Management |  | 47 | _ | _ | 54 | _ | _ | 49 | _ | Financial reports
Waste Management | 2015 Monthly Projections R'00 Jul.: 357; 2015 Monthly Projections R'00 Aug.: 47; 2015 Monthly Projections R'00 Oct.: 357; 2015 Monthly Projections R'00 Nov.: 500; 2016 Monthly Projections Jan.: 357; 2016 Monthly Projections Feb.: 521; 2016 Monthly Projections Apr.: Financial reports
Road Transport | 671 | 485 | 3400 | 671 | 1985 | 8500 | 671 | 2000 | 5640 | Financial reports
Electricity | 2015 Monthly Projections R'00 Jul.: 1400; 2015 Monthly Projections R'00 Aug.: 1875; 2015 Monthly Projections R'00 Oct.: 1400; 2015 Monthly Projections R'00 Nov.: 1485; 2016 Monthly Projections Jan.: 1400; 2016 Monthly Projections Feb.: 1354; 2016 Monthly Projections Apr.: Financial reports
Total by Vote | 26447 | 12282 | 3400 | 26447 | 13091 | 8650 | 26447 | 13145 | 7873 | Financial reports
Monthly Projections of Expenditure (Operating, Capital and Revenue) by vote : Second Quarter
Expenditure and Revenue by Vote | 2015 Monthly Projections R'00 Jul.: 2015-10-01; 2015 Monthly Projections R'00 Oct.: 2015-11-01; 2016 Monthly Projections Jan.: 2015-12-01; 2016 Monthly Projections Apr.: Evidence required
| Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex
Executive and Council | 2015 Monthly Projections R'00 Jul.: _; 2015 Monthly Projections R'00 Aug.: 3828; 2015 Monthly Projections R'00 Oct.: _; 2015 Monthly Projections R'00 Nov.: 4000; 2016 Monthly Projections Jan.: _; 2016 Monthly Projections Feb.: 3520; 2016 Monthly Projections Apr.: Financial reports
Budget and Treasury | 2015 Monthly Projections R'00 Jul.: 31590; 2015 Monthly Projections R'00 Aug.: 2000; 2015 Monthly Projections R'00 Oct.: 30975; 2015 Monthly Projections R'00 Nov.: 2500; 2016 Monthly Projections Jan.: 30547; 2016 Monthly Projections Feb.: 1256; 2016 Monthly Projections Apr.: Financial reports
Corporate Services | _ | 2641 | 40 | _ | 2100 |  | _ | 2800 | 500 | Financial reports
Planning and Development | 2015 Monthly Projections R'00 Jul.: _; 2015 Monthly Projections R'00 Aug.: 985; 2015 Monthly Projections R'00 Oct.: _; 2015 Monthly Projections R'00 Nov.: 1256; 2016 Monthly Projections Jan.: _; 2016 Monthly Projections Feb.: 1061; 2016 Monthly Projections Apr.: Financial reports
Community Services | _ | 148 |  | _ | 200 | 800 | _ | 235 |  | Financial reports
Housing | 2015 Monthly Projections R'00 Jul.: _; 2015 Monthly Projections R'00 Aug.: 39; 2015 Monthly Projections R'00 Oct.: _; 2015 Monthly Projections R'00 Nov.: 36; 2016 Monthly Projections Jan.: _; 2016 Monthly Projections Feb.: 51; 2016 Monthly Projections Apr.: Financial reports
Public Safety | 2015 Monthly Projections R'00 Jul.: _; 2015 Monthly Projections R'00 Aug.: 162; 2015 Monthly Projections R'00 Oct.: _; 2015 Monthly Projections R'00 Nov.: 234; 2016 Monthly Projections Jan.: _; 2016 Monthly Projections Feb.: 200; 2016 Monthly Projections Apr.: Financial reports
Sports and Recreation | _ | 486 |  | _ | 524 |  | _ | 589 | 6540 | Financial reports
Waste Water Management | _ | 46 | _ | _ | 52 | 2400 | _ | 48 | _ | Financial reports
Waste Management | 357 | 504 |  | 357 | 499 | 3000 | 357 | 552 |  | Financial reports
Road Transport | 671 | 2100 | 8900 | 671 | 1784 | 12000 | 671 | 2000 | 13580 | Financial reports
Electricity | 1400 | 1200 | 600 | 1400 | 1175 | 1540 | 1400 | 1230 |  | Financial reports
Total by Vote | 26447 | 14139 | 9540 | 26447 | 14360 | 19740 | 26447 | 13541 | 20620
Monthly Projections of Expenditure (Operating, Capital and Revenue) by vote : Third Quarter
Expenditure and Revenue by Vote | 2015 Monthly Projections R'00 Jul.: 2016-01-01; 2015 Monthly Projections R'00 Oct.: 2016-02-01; 2016 Monthly Projections Jan.: 2016-03-01; 2016 Monthly Projections Apr.: Evidence required
| Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex
Executive and Council | _ | 2856 |  | _ | 4265 | 500 | _ | 3460 |  | Financial reports
Budget and Treasury | 2015 Monthly Projections R'00 Jul.: 20600; 2015 Monthly Projections R'00 Aug.: 985; 2015 Monthly Projections R'00 Oct.: 20541; 2015 Monthly Projections R'00 Nov.: 1001; 2016 Monthly Projections Jan.: 20655; 2016 Monthly Projections Feb.: 2500; 2016 Monthly Projections Apr.: Financial reports
Corporate Services | 2015 Monthly Projections R'00 Aug.: 3500; 2015 Monthly Projections R'00 Sep.: 40; 2015 Monthly Projections R'00 Nov.: 2731; 2016 Monthly Projections Feb.: 2734; 2016 Monthly Projections Apr.: Financial reports
Planning and Development | 2015 Monthly Projections R'00 Aug.: 1426; 2015 Monthly Projections R'00 Nov.: 1050; 2016 Monthly Projections Feb.: 875; 2016 Monthly Projections Apr.: Financial reports
Community Services | 2015 Monthly Projections R'00 Aug.: 300; 2015 Monthly Projections R'00 Nov.: 325; 2015 Monthly Projections R'00 Dec.: 2500; 2016 Monthly Projections Feb.: 235; 2016 Monthly Projections Mar.: 5800; 2016 Monthly Projections Apr.: Financial reports
Housing | 2015 Monthly Projections R'00 Aug.: 50; 2015 Monthly Projections R'00 Nov.: 54; 2016 Monthly Projections Feb.: 36; 2016 Monthly Projections Apr.: Financial reports
Public Safety | 2015 Monthly Projections R'00 Aug.: 245; 2015 Monthly Projections R'00 Nov.: 142; 2016 Monthly Projections Feb.: 110; 2016 Monthly Projections Apr.: Financial reports
Sports and Recreation | 2015 Monthly Projections R'00 Aug.: 600; 2015 Monthly Projections R'00 Nov.: 1250; 2015 Monthly Projections R'00 Dec.: 8531; 2016 Monthly Projections Feb.: 1010; 2016 Monthly Projections Apr.: Financial reports
Waster Water Management | _ | 60 | _ | _ | 55 | _ | _ | 42 | _ | Financial reports
Waste Management | 357 | 541 |  | 357 | 564 | 3260 | 357 | 500 |  | Financial reports
Road Transport | 671 | 1875 | 8900 | 671 | 1920 | 4896 | 671 | 2235 | 5800 | Financial reports
Electricity | 1400 | 1500 | 600 | 1400 | 1607 |  | 1400 | 1800 |  | Financial reports
Total by Vote | 26447 | 13938 | 9540 | 26447 | 14965 | 26891 | 26447 | 15537 | 11600
Monthly Projections of Expenditure (Operating, Capital and Revenue) by vote : Fourth Quarter
Expenditure and Revenue by Vote | 2015 Monthly Projections R'00 Jul.: 2016-04-01; 2015 Monthly Projections R'00 Oct.: 2016-05-01; 2016 Monthly Projections Jan.: 2016-06-01; 2016 Monthly Projections Apr.: Evidence required
| Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex
Executive and Council | 2015 Monthly Projections R'00 Jul.: _; 2015 Monthly Projections R'00 Aug.: 4600; 2015 Monthly Projections R'00 Oct.: _; 2015 Monthly Projections R'00 Nov.: 3828; 2016 Monthly Projections Jan.: _; 2016 Monthly Projections Feb.: 4534; 2016 Monthly Projections Apr.: Financial reports
Budget and Treasury | 2015 Monthly Projections R'00 Jul.: 25500; 2015 Monthly Projections R'00 Aug.: 300; 2015 Monthly Projections R'00 Oct.: 27500; 2015 Monthly Projections R'00 Nov.: 3800; 2016 Monthly Projections Jan.: 22762; 2016 Monthly Projections Feb.: 4846; 2016 Monthly Projections Apr.: Financial reports
Corporate Services | 2015 Monthly Projections R'00 Aug.: 3456; 2015 Monthly Projections R'00 Sep.: 1000; 2015 Monthly Projections R'00 Nov.: 4700; 2015 Monthly Projections R'00 Dec.: 700; 2016 Monthly Projections Feb.: 3547; 2016 Monthly Projections Mar.: 2220; 2016 Monthly Projections Apr.: Financial reports
Planning and Development | 2015 Monthly Projections R'00 Aug.: 745; 2015 Monthly Projections R'00 Nov.: 875; 2016 Monthly Projections Feb.: 816; 2016 Monthly Projections Apr.: Financial reports
Community Services | 2015 Monthly Projections R'00 Aug.: 231; 2015 Monthly Projections R'00 Nov.: 347; 2015 Monthly Projections R'00 Dec.: 6000; 2016 Monthly Projections Feb.: 363; 2016 Monthly Projections Mar.: 7411; 2016 Monthly Projections Apr.: Financial reports
Housing | 2015 Monthly Projections R'00 Aug.: 75; 2015 Monthly Projections R'00 Nov.: 69; 2016 Monthly Projections Feb.: 81; 2016 Monthly Projections Apr.: Financial reports
Public Safety | 2015 Monthly Projections R'00 Aug.: 201; 2015 Monthly Projections R'00 Nov.: 187; 2016 Monthly Projections Feb.: 181; 2016 Monthly Projections Apr.: Financial reports
Sports and Recreation | 2015 Monthly Projections R'00 Aug.: 800; 2015 Monthly Projections R'00 Sep.: 2354; 2015 Monthly Projections R'00 Nov.: 750; 2015 Monthly Projections R'00 Dec.: 6541; 2016 Monthly Projections Feb.: 1060; 2016 Monthly Projections Mar.: 5095; 2016 Monthly Projections Apr.: Financial reports
Waste Water Management | _ | 49 | _ | _ | 60 | _ | _ | 63 | _ | Financial reports
Waste Management | 2015 Monthly Projections R'00 Jul.: 357; 2015 Monthly Projections R'00 Aug.: 600; 2015 Monthly Projections R'00 Oct.: 357; 2015 Monthly Projections R'00 Nov.: 785; 2016 Monthly Projections Jan.: 357; 2016 Monthly Projections Feb.: 917; 2016 Monthly Projections Apr.: Financial reports
Road Transport | 671 | 2300 | 6000 | 671 | 2785 | 4580 | 671 | 2784 | 13940 | Financial reports
Electricity | 2015 Monthly Projections R'00 Jul.: 1400; 2015 Monthly Projections R'00 Aug.: 2000; 2015 Monthly Projections R'00 Oct.: 1400; 2015 Monthly Projections R'00 Nov.: 1988; 2016 Monthly Projections Jan.: 1400; 2016 Monthly Projections Feb.: 2296; 2016 Monthly Projections Apr.: Financial reports
Total by Vote | 26447 | 15357 | 9354 | 26447 | 20173 | 17821 | 26447 | 21489 | 28666

## MTOD KPI's
KPA 1 MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT
KEY PERFORMANCE INDICATORS
OUTCOME NINE (OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING, PLANNING AND SUPPORT, OUTPUT 4: ACTIONS SUPPORTIVE OF THE HUMAN SETTLEMENT OUTCOMES)
Vote Nr | Strategic Objective | Municipal Programmes | Measurable Objectives | Key Performance measures/ Indicator | KPI Unit of measure | Baseline / Status | Annual Target (30/06/2016) | Budget 2015/16 | 1st Quarter (1 Jul-30 Sept 2015) | 2nd Quarter (1 Oct -31 Dec 2015) | 3rd Quarter (1 Jan 31 Mar 2016) | 4th Quarter (1 Apr- 3 Jun 2016) | Responsible Person | Evidence requires
| Improved Governance and Organisational Excellence | Human Resource Management | To ensure that the reviewed organiztional structure is approved by council by 31/05/2016 | Approval of Reviewed Organisational structure by 31 May 2016 | Date | 31/05/2015 | Council Approved Organizational structure by 31 May 2016 | Operational | N/A | N/A | N/A | Council Approved Organizational structure by 31 May 2016 | Director Corp | Council Approved Organizational structure
| Improved Governance and Organisational Excellence | Human Resource Management | Reducing the vacancy rate within the financial year | # of vacant positions to be filled | Number | 12 Positions filled | 40 Positions filled | Operational | N/A | 30 Positions filled | N/A | 10 Positions filled | Director Corp | Appointment letters
| Integrated Sustainable Development | IDP | Approval of the IDP/Budget/PMS process by 31 July 2015 | Approval of 2015/16 IDP/Budget/ PMS Process Plan by council by 31 July 2016 | Date | 31/07/2014 | 31/07/2015 | Operational | 31/07/2015 | N/A | N/A | N/A | Director INDEP | Council Approved IDP/ Budget/ PMS Process plan
| Integrated Sustainable Development | IDP | Approval of the Draft 2016/17 IDP by 31 March 2016 | Approval of Draft 2016/17 IDP by 31 March 2016 | Date | 31/03/2015 | 31/03/2016 | Operational | N/A | N/A | 31/03/2016 | N/A | Director INDEP | Council approved Draft IDP and resolution
| Integrated Sustainable Development | IDP | Approval of the Final 2016/17 IDP by council within the financial year | Approval of Final 2016/17 IDP by Council 31 May 2016. | Date | 31/05/2015 | 31/05/2016 | Operational | N/A | N/A | N/A | 31/05/2016 | Director INDEP | Council approved IDP and resolution
| Improved Governance and Organisational Excellence | PMS | To ensure that SDBIP is finalised by 30 June 2016 | Approval of the final SDBIP by the Mayor within 28 days after adoption of the final Budget and IDP by 30 June 2016. | Date | 28/06/2015 | 30/06/2016 | Operational | N/A | N/A | N/A | 30/06/2016 | Municipal Manager | SDBIP approved by Mayor 28 days after adoption of budget/IDP/PMS
| Improved Governance and Organisational Excellence | PMS | To ensure quarterly reporting and compliance within the financial year | # of Quarterly performance reports compiled and submitted to Council within 30 days after the end of each quarter | Number | 4 Quarterly performance reports compiled | 4 Quarterly performance reports compiled | Operational | 1 Quarterly performance reports compiled | 1 Quarterly performance reports compiled | 1 Quarterly performance reports compiled | 1 Quarterly performance reports compiled | Municipal Manager | Council approved Quarterly reports
| Improved Governance and Organisational Excellence | PMS | To ensure that S54 & 56 Managers sign the performance agreements within 30 days after adoption of the final SDBIP. | Signing of performance agreements within 30 days after the approval of the SDBIP. | Date | 07/07/2014 | 31/07/2015 | Operational | 31/07/2015 | N/A | N/A | N/A | Municipal Manager | Signed Performance Agreements for Sec 54 & 56 Managers
| Improved Governance and Organisational Excellence | PMS | To ensure quartely assessments for S54 & 56 Managers is conducted within 30 days after the end of the quarter. | # of Individual performance assessments conducted in 2015/16 financial year | Number | 0 | 2 Individual performnace conducted | Operational | 1 Individual performnace conducted | N/A | 1 Individual performnace conducted | N/A | Municipal Manager | Performance Assessments report
| Improved Governance and Organisational Excellence | PMS | To ensure municipal reporting and compliance within the financial year | Submission of Annual Institutional Performance report as per Sec 46 of the MFMA | Date | 30/08/0014 | 30/08/2015 | Operational | 30/08/2015 | N/A | N/A | N/A | Municipal Manager | Dated proof of submission to CoGHSTA, Provincial and National Treasury
| Improved Governance and Organisational Excellence | PMS | To ensure municipal reporting and compliance within the financial year | Submission of Mid-Year report to CoGHSTA, Provincial and National Treasury by 25 January 2016 | Date | 25/01/2015 | 25/01/2016 | Operational | N/A | N/A | 25/01/2016 | N/A | Municipal Manager | Dated proof of submission to CoGHSTA, Provincial and National Treasury
| Improved Governance and Organisational Excellence | PMS | To ensure municipal reporting and compliance | Tabling of the Annual Report in Council by 31 January 2016 | Date | 31/01/2015 | 31/01/2016 | Operational | N/A | N/A | 31/01/2016 | N/A | Municipal Manager | Council approved Annual report andd resolution
| Improved Governance and Organisational Excellence | PMS | To ensure municipal reporting and compliance within the financial year | Deadline for tabling an oversight report on the Annual Report in Council by 31 March 2016 | Date | 31/03/2015 | 31/03/2016 | Operational | N/A | N/A | 31/03/2016 | N/A | Municipal Manager | Council approved Oversight report on the Annual report and resolution
| Improved Governance and Organisational Excellence | PMS | To ensure municipal reporting and compliance within the financial year | Deadline for publishing the oversight report in the newspaper & website within 7 days of adoption | Date | 10/04/2015 | 07/04/2016 | Operational | N/A | N/A | N/A | 07/04/2016 | Municipal Manager | Council approved Annual report andd resolution
| Improved Governance and Organisational Excellence | PMS | To ensure implementation of the performance management system in the organisation within the financial year. | Deadline for the approval of Performance management policy for officials lower than sec 54 & 56 development and approved by council | Date | New Indicator | 30/06/2016 | Operational | N/A | N/A | N/A | 30/06/2016 | Municipal Manager | Council approved PMS policy for all municipal officials
| Improved Governance and Organisational Excellence | PMS | To ensure municipal reporting and compliance within the financial year | Deadline for reviewal of the SDBIP | Date | 31/03/2015 | 31/03/2016 | Operational | N/A | N/A | 31/03/2016 | N/A | Municipal Manager | Reviewed 2015/16 SDBIP
| Improved Governance and Organisational Excellence | Legal Services | To improve effecience and effictiveness of municipal administration within the financial year | % in developing Service Level Agreements within 30 days after the appointment of Service provider | Percentage | New Indicator | 100% | Operational | 100% | 100% | 100% | 100% | Director Corp | Service Level Agreements signed within 30 days after appointment
| Improved Governance and Organisational Excellence | Internal Audit | To ensure functionality of Audit committee within the financial year. | # of Audit Committee meetings held per quarter. | Number (Accumulative) | 2 Audit Committee meetings held | 4 Audit Committee meetings held | Operational | 1 Audit Committee meeting held | 1 Audit Committee meeting held | 1 Audit Committee meeting held | 1 Audit Committee meeting held | Municipal Manager | Agenda, Minutes & Attandance register
| Improved Governance and Organisational Excellence | Risk | To ensure functionality of Risk committee within the financial year. | # of Risk Committee meetings held per quarter. | Number (Accumulative) | 2 Risk Committee Meetings held | 4 Risk Committee Meetings held | Operational | 1 Risk Committee Meetings held | 1 Risk Committee Meetings held | 1 Risk Committee Meetings held | 1 Risk Committee Meetings held | Municipal Manager | Agenda, Minutes & Attandance register
| Improved Governance and Organisational Excellence | Internal Audit | To conduct quarterly assessment on municipal performance within the financial year | # of performance audit reports issued per quarter. | Number | 1 Performance audit reports issued | 4 Performance audit reports issued | Operational | 1 Performance audit reports issued | 1 Performance audit reports issued | 1 Performance audit reports issued | 1 Performance audit reports issued | Municipal Manager | Performance Audit report tabled in council and resolution
| Improved Governance and Organisational Excellence | Internal Audit | Functionality of Audit within the financial year | Development of audit action plan 31 January 2016 | Date | 31/01/2015 | 31/01/2016 | Operational | N/A | N/A | 31/01/2016 | N/A | Municipal Manager | Council approved audit action plan
| Improved Governance and Organisational Excellence | Internal Audit | To develop annual year internal audit plan and implement by 30 June 2016. | Approved audit plan and % of the IA plan implementation. | Percentage | 60% IA plan Implementation | 100% IA plan implementation | Operational | 25% IA plan implementation | 50% IA plan implementation | 75% IA plan implementation | 100% IA plan implementation | Municipal Manager | Updated IA Plan register
| Improved Governance and Organisational Excellence | Internal Audit | To attain Clean Audit by ensuring compliance to all governance; financial management and reporting requirements by 30 June 2016 | % of internal audit issues resolved (# of Internal Audit issues resolved / # of issues raised) | Percentage | 90% Internal audit issues resolved | 100% internal audit issues resolved | Operational | 25% internal audit issues resolved | 50% internal audit issues resolved | 75% internal audit issues resolved | 100% internal audit issues resolved | Municipal Manager | resolved AG issues and POE submitted
| Improved Governance and Organisational Excellence | Internal Audit | To attain Clean Audit by ensuring compliance to all governance; financial management and reporting requirements by 30 June 2016 | % of AG issues resolved (# of Auditor General issues resolved / # of issues raised) | Percentage | 90% issues resolved | 100% AG issues resolved | Operational | N/A | N/A | 50% AG issues resolved | 100% AG issues resolved | Municipal Manager | resolved AG issues and POE 's submitted
| Improved Governance and Organisational Excellence | Risk management | To ensure efffective implementation of risk mitigations actions 30 June 2016. | % of Risk issues resolved (# Risk issues implemented / resolved / # of risks identified) | Percentage | 85% Risk issues resolved | 100% Risk issues resolved | Operational | 25% Risk issues resolved | 50% Risk issues resolved | 75% Risk issues resolved | 100% Risk issues resolved | Municipal Manager | Resolved Risk issues and POE submitted

## BSD KPI's
KPA 2 : BASIC SERVICE DELIVERY INDICATORS OUTPUT 2: IMPROVING ACCESS TO BASIC SERVICES, OUTPUT 3: IMPLEMENTATION OF THE COMMUNITY WORKS PROGRAMME
Vote Nr | Strategic Objective | Programme | Measurable Objective | KPI Unit of measure | Baseline / Status | Annual Target (30/06/15) | Budget 2014/2015 | 1st Quarter (1 Jul-30 Sept 2015) | 2nd Quarter (1 Oct -31 Dec 2015) | 3rd Quarter (1 Jan 31 Mar 2016) | 4th Quarter (1 Apr- 3 Jun 2016) | Responsible Person | Evidence required
22 | Integrated and Sustainable Human Settlement | Spatial Planning | To submit housing demand database to COGHSTA by 31 December 2015 | Deadline for submission of the House demand database to CoGHSTA | Database submitted to COGHSTA by the 31 December 2014 | Database submitted to COGHSTA by the 31 December 2015 | Operational | N/A | Database submitted to COGHSTA by the 31 December 2015 | N/A | N/A | Director INDEP | Dated proof of submiision to CoGHSTA
32 | Integrated and Sustainable Human Settlement | Spatial Planning | To ensure that land use applications are processed within 90 days of receipt. | % of land use applications processed (# of applications received / # of land use applications processed) within 90 days of receipt | 80% applications processed | 100% applications processed | Operational | 25% applications processed | 50% applications processed | 75% applications processed | 100% applications processed | Director INDEP | Dated proof of processed applications
32 | Access to Sustainable Basic Services | Waste management | Provision of waste removal within the financial year | # of HH with access to refuse removal at least once a week | 4654 HH with access to refuse removal at least once a week | 4654 HH with access to refuse removal at least once a week | Operational | 4654 HH with access to refuse removal at least once a week | 4654 HH with access to refuse removal at least once a week | 4654 HH with access to refuse removal at least once a week | 4654 HH with access to refuse removal at least once a week | Director COMM | Rooster/ waste management reports
32 | Access to Sustainable Basic Services | Waste management | Provision of waste removal within the financial year | Deadline for completing Land Fill Site | Designs for Maphalle Land fill site completed | Construction of Guard house, way bridge and , Office block completed and development of 2 dumping cell. | R 3 000 000 (Capital) | Specifications submitted to SCM for advertisement | Appoint service provider | Construction of Guard house, way bridge and , Office block completed and development of 2 dumping cell. | Project completed | Director COMM | Payment certificates
32 | Access to Sustainable Basic Services | Roads | To ensure access to municipal roads within the financial year | # of Km of gravel roadsu pgraded to paving | 75km paved | 42km of paved | Capital | Develop specification and submit to SCM unit for advertisement | Advertise and appoint service provider for construction of street paving projects | Layer works completed for 19 km | Completion stage : project completed and handed-over to the municipality | Director INDEP | Handover reports / Practical completion certificate

## LED KPI's
KPA 3 : LOCAL ECONOMIC DEVELOPMENT
KEY PERFORMANCE INDICATORS
OUTCOME 9: IMPLEMENTATION OF THE COMMUNITY WORK PROGRAMME
Vote Nr | Strategic Objective | Municipal Programmes | Measurable Objectives | Key Performance measures/ Indicator | KPI Unit of measure | Baseline / Status | Annual Target (30/06/2016) | Budget 2015/16 | 1st Quarter (1 Jul-30 Sept 2015) | 2nd Quarter (1 Oct -31 Dec 2015) | 3rd Quarter (1 Jan 31 Mar 2016) | 4th Quarter (1 Apr- 3 Jun 2016) | Responsible Person | Evidence requires
| Improved Governance and Organisational Excellence | Improved local economy | To ensure Promotion of local economy within the financial year | Total # of jobs created through municipal activies | Number | 656 Jobs created | 800 Jobs created | Operational | 200 Jobs created | 200 Jobs created | 200 Jobs created | 200 Jobs created | Director INDEP | Proof for SMME s supported
| Improved Governance and Organisational Excellence | Improved local economy | To ensure Promotion of local economy within the financial year | Total # of SMME s supported through Sypply Chain Management | Number | New Indicator | 120 SMME s supported | Operational | 30 SMME s supported | 30 SMME s supported | 30 SMME s supported | 30 SMME s supported | CFO | Proof for SMME s supported
| Integrated Sustainable Development | Improved local economy | To ensure Promotion of local economy within the financial year | # of EPWP reports submitted to Council | Number | 12 EPWP reports generated | 12 EPWP reports generated | Operational | 3 EPWP reports generated | 6 EPWP reports generated | 9 EPWP reports generated | 12 EPWP reports generated | Director INDEP | EPWP reports
| Integrated Sustainable Development | Improved local economy | To ensure Coordination of Agriculture forums within the financial year | # of Agriculture Forums coordinated per quarter | Number | 3 Agriculture forums coordinated | 4 Agriculture forums coordinated | Operational | 1 Agriculture forum coordinated | 1 Agriculture forum coordinated | 1 Agriculture forum coordinated | 1 Agriculture forum coordinated | Director INDEP | Agenda, Minutes & Attendance register
| Integrated Sustainable Development | Marketing/ Branding | To Market municipal initiatives within the financial year | # of Marketing initiatives conducted | Number | 4 Marketing iniatives conducted | 4 Marketing iniatives conducted | Operational | 1 Marketing iniatives conducted | 1 Marketing iniatives conducted | 1 Marketing iniatives conducted | 1 Marketing iniatives conducted | Director INDEP | proof for marketing initiated

## MFMV KPI
KPA 4 MUNICIPAL FINANCIAL VIABILITY KEY PERFORMANCE INDICATORS OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY
Vote Nr | Strategic Objective | Progranmes | Measurable Objectives | Performance measures | KPI Unit of measure | Baseline / Status | Annual Target (30/06/15) | Budget 2014/2015 | 1st Quarter (1 Jul-30 Sept 2015) | 2nd Quarter (1 Oct -31 Dec 2015) | 3rd Quarter (1 Jan 31 Mar 2016) | 4th Quarter (1 Apr- 3 Jun 2016) | Responsible Person | Evidence required
50 | Sustainable Financial Institution | Budget and Reporting | To effectively manage the financial affairs of the municipality within the financial year | Deadline for approval of Budget Planning schedule | Date | 31/07/2014 | 31/07/2015 | Operational | 31/07/2015 | N/A | N/A | N/A | CFO | Council approved Budget Planning schedule
| Sustainable Financial Institution | Revenue | To ensure improvement in revenue collection within the financial year | % in Improvement of revenue collection | Percentage | revenue collection | 75 revenue collection | Operational | 25% revenue collection | 50% revenue collection | 75% revenue collection | 100% revenue collection | CFO | Financial reports
| Sustainable Financial Institution | Expenditure Management | Provision of free basic services within the financial year | # of HH receiving free basic services | Number | 835 HH received free basic service | 1500 HH receiving free basic services | Operational | 1500 HH receiving free basic services | 1500 HH receiving free basic services | 1500 HH receiving free basic services | 1500 HH receiving free basic services | CFO | Indigent register
50 | Sustainable Financial Institution | Budget and Reporting | To ensure that quartely financial statements are prepared within 14 days after the end of each quarter. | # of quarterly financial statements submitted to the relevant authorities | Number | 4 financial statements submitted | 4 Financial statements submitted | Operational | 1 Financial statement submitted | 1 Financial statement submitted | 1 Financial statement submitted | 1 Financial statement submitted | CFO | dated proof of submission Financial Statements
| Sustainable Financial Institution | Budget and Reporting | To ensure compliance with legislation within the financial year | Deadline for approval of the Draft Budget by Council on 31/03/2016 | Date | 31/03/2015 | 31/03/2016 | Operational | N/A | N/A | 31/03/2016 | N/A | CFO | Council approved Draft Budget
| Sustainable Financial Institution | Budget and Reporting | To ensure compliance with legislation within the financial year | Deadline for approval of Final Budget by council by 31/05/2016 | Date | 31/05/2015 | 31/05/2016 | Operational | N/A | N/A | N/A | 31/05/2016 | CFO | Council Approved Final Budget
| Sustainable Financial Institution | Budget and Reporting | To ensure compliance with legislation within the financial year | Deadline for review of budget related policies | Date | 31/05/2015 | 31/05/2016 | Operational | N/A | N/A | N/A | 31/05/2016 | CFO | Council Approved Budget related policies
| Sustainable Financial Institution | Revenue Management | Review, adopt and implement Revenue Enhancement Strategy 30 June 2016 | Revenue Enhancement Strategy | Document |  | 01/07/2015 | 30/06/2016 | Review and adoption of Draft Revenue Enhancement Strategy | Implementation of the adopted Revenue Enhancement Strategy | Implementation of the adopted Revenue Enhancement Strategy | Revenue Emhancement strategy reviewed, adopted and implemented | CFO | Council Approved Revenue Enhancement Strategy
| Sustainable Financial Institution | Budget and Reporting | To ensure compliance with legislation within the financial year | Deadline for approval of adjustment budget by council by 28 February 2016 | Date | 28/02/2015 | 28/02/2016 | Operational | N/A | N/A | 28/02/2016 | N/A | CFO | Council approved adjustment budget
| Sustainable Financial Institution | Budget and Reporting | To ensure compliance with legislation within the financial year | Deadline of submitting unaudited financial statements by 31/08/2015 | Date | 30/08/2014 | 31/08/2015 | Operational | 31/08/2015 | N/A | N/A | N/A | CFO | Dated proof of submission of Unaudited AFS
| Sustainable Financial Institution | Budget and Reporting | To ensure compliance with legislation within the financial year | # of Sec 32 Register developed and updated | Number | New Indicator | 12 Sec 32 register | Operational | 3 Sec 32 registers | 3 Sec 32 registers | 3 Sec 32 registers | 3 Sec 32 registers | CFO | Dated proof of Sec 32 register
| Sustainable Financial Institution | Budget and Reporting | To ensure compliance with legislation within the financial year | Deadline for approval of finance by-laws by 31 May 2016 | Date | New Indicator | 31/05/2016 | Operational | N/A | N/A | n/a | 31/05/2016 | CFO | Council approved finance by-laws
| Sustainable Financial Institution | Budget and Reporting | To ensure compliance with legislation within the financial year | # of Finance compliance report submitted to Treasuries & CoGHSTA | Number | 12 Finance compliance report submitted | 12 Finance compliance report submitted | Oerational | 3 Finance compliance report submitted | 3 Finance compliance report submitted | 3 Finance compliance report submitted | 3 Finance compliance report submitted | CFO | Financial reports
| Sustainable Financial Institution | Budget and Reporting | To ensure compliance with legislation within the financial year | Deadline for submission of monthly Sec 71 reports to Provincial treasury | Date | Within 10 working days | within 10 working days | Operational | Within 10 working days | Within 10 working days | Within 10 working days | Within 10 working days | CFO | Dated proof of submission
| Sustainable Financial Institution | Supply Chain Management | To Improve financial viability within the financial year | Deadline for appointing Supply Chain Structures | Date | 31/07/2014 | 31/07/2015 | Operational | 31/07/2015 | N/A | N/A | N/A | Municipal Manager | Appointment Letters
50 | Sustainable Financial Institution | Supply Chain Management | To ensure payment of service providers within 30 days of the submission of invoices. | Deadline for payments of invoices wiithin 30 daysof receipt | Days | Invoices was paid within 30 days | Payment of invoices within 30 days | Operational | Payment of invoices within 30 days | Payment of invoices within 30 days | Payment of invoices within 30 days | Payment of invoices within 30 days | CFO | Dated proof of payment
| Sustainable Financial Institution | Assets Management | To ensure compliance with legislation within the financial year | # Assets verifications conducted in line with GRAP standards | Number | 2 Assets verifications conducted | 4 Assets verifications conducted | Operational | 1 Assets verifications conducted | 1 Assets verifications conducted | 1 Assets verifications conducted | 1 Assets verifications conducted | CFO | Quarterly Assets verification reports
50 | Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality within the financial year | % capital budget spent as approved by Council | Percentage | 70% | 100% | Capital | 25% Capital Budget spent | 50% Capital Budget spent | 75% Capital Budget spent | 100% Capital Budget spent | CFO | Financial reports
50 | Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality within the financial year | % MIG expenditure | Percentage | 79.53% | 100% | Capital | 25% MIG expenditure | 50% MIG expenditure | 75% MIG expenditure | 100% MIG expenditure | CFO/ INDEP | Financial reports
50 | Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality within the financial year | % FMG expenditure | Percentage | 90% | 100% | Operational | 25% FMG Expenditure | 50% FMG Expenditure | 75% FMG Expenditure | 100% FMG Expenditure | CFO | Financial reports
| Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality within the financial year | % MSIG expenditure | Percentage | 100% | 100% | Operational | 25% MSIG expenditure | 50% MSIG expenditure | 75% MSIG expenditure | 100% MSIG expenditure | CFO | Financial reports
50 | Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality within the financial year | % EPWP expenditure | Percentage | 100% | 100% | Operational | 25% EPWP expenditure | 50% EPWP expenditure | 75% EPWP expenditure | 100% EPWP expenditure | CFO/ INDEP | Financial reports
| Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality within the financial year | % FBS expenditure | Percentage | 100% | 100% | Operational | 25% FBS expenditure | 50% FBS expenditure | 75% FBS expenditure | 100% FBS expenditure | CFO | Financial reports

## GGPP KPI's
KPA 5 : GOOD GOVERNANCE AND PUBLIC PARTICIPATION KEY PERFORMANCE INDICATORS OUTCOME 9 (OUTPUT 5: DEEPEN DEMOCRACY THROUGH A REFINED WARD COMMITTEE MODEL, OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY)
Vote Nr | Strategic Objective | Programmes | Measurable Objectives | Performance measures | KPI Unit of measure | Baseline | Annual Target (30/06/2016) | Budget 2015/2016 | 1st Quarter (1 Jul-30 Sept 2015) | 2nd Quarter (1 Oct -31 Dec 2015) | 3rd Quarter (1 Jan 31 Mar 2016) | 4th Quarter (1 Apr- 3 Jun 2016) | Responsible Person | Evidence required
| Improved Governance and Organisational Excellence | Council | To ensure functionality of Council committee within the financial year. | # of Council Meetings held per quarter | Number | 11 Council meetings held | 4 Council meetings held | Operational | 1 Council meetings held | 1 Council meetings held | 1 Council meetings held | 1 Council meetings held | Director Corp | Agenda, Minutes & attandance register
| Improved Governance and Organisational Excellence | Council | To ensure functionality of EXCO committee within the financial year. | # of EXCO meetings held per quarter. | Number | 11 EXCO meetings held | 4 EXCO meetings held | Operational | 4 EXCO meetings held | 4 EXCO meetings held | 4 EXCO meetings held | 4 EXCO meetings held | Director Corp | Agenda, Minutes & attandance register
| Improved Governance and Organisational Excellence | Committees | To ensure functionality of Council committee within the financial year. | # of Ward Committee reports submitted | Number | 348 ward committee reports submitted | 348 ward committee reports submitted | Operational | 348 ward committee reports submitted | 348 ward committee reports submitted | 348 ward committee reports submitted | 348 ward committee reports submitted | Manager (Mayors Office) | Agenda, Minutes & attandance register
| Improved Governance and Organisational Excellence | Public Participation | To improve service delivery and public participation within the financial year | # of Ward reports consolidated into Batho-Pele reports | Number | New Indicator | 11 Batho-Pele reports | Operational | 11 Batho-Pele reports | 11 Batho-Pele reports | 11 Batho-Pele reports | 11 Batho-Pele reports | Director Copr/ Manager in Mayor s Office | Monthly Batho-Pele reports
| Improved Governance and Organisational Excellence | Committees | To ensure functionality of Council within the financial year | # of MPAC meetings held per quarter | Number | 14 MPAC meetings held | 12 MPAC meetings held | Operational | 3 MPAC meetings held | 3 MPAC meetings held | 3 MPAC meetings held | 3 MPAC meetings held | Manager (Mayors Office) | Agenda, Minutes & attandance register
| Improved Governance and Organisational Excellence | Human Resource management | To ensure functionality of Council within the financial year | # of LLF meetings held per month | Number | 6 LLF meetings held | 12 LLF meetings held | Operational | 3 LLF meetings held | 3 LLF meetings held | 3 LLF meetings held | 3 LLF meetings held | Director Corp | Agenda, Minutes & attandance register
| Improved Governance and Organisational Excellence | Labour Relations | To ensure functionality of Municipality within the financial year | % in implementation of LLF resolutions | Percentage | 60% of resolutions implemented | 100% resolutions implemented | Operational | 100% resolutions implemented | 100% resolutions implemented | 100% resolutions implemented | 100% resolutions implemented | Director Corp | Updated resolution reguster
| Improved Governance and Organisational Excellence | Public Participation | To ensure public involvement in the IDP review | # of IDP/Budget/ PMS REP Forum meetings held per quarter | Number (Accumulative) | 5 IDP/Budget/PMS REP Forum meetings held | 5 IDP/Budget/PMS REP Forum meetings held | Operational | 1 IDP/Budget/PMS REP Forum meetings held | 1 IDP/Budget/PMS REP Forum meetings held | 1 IDP/Budget/PMS REP Forum meetings held | 2 IDP/Budget/PMS REP Forum meetings held | Director INDEP | Agenda & Attandance register
| Improved Governance and Organisational Excellence | Public Participation | To ensure public involvement in the IDP review | # of IDP/Budget/ PMS Steering Committee meetings held per quarter | Number (Accumulative) | 5 IDP/Budget/PMS Steering Committee meetings held | 5 IDP/Budget/PMS Steering Committee meetings held | Operational | 1 IDP/Budget/PMS Steering Committee meetings held | 1 IDP/Budget/PMS Steering Committee meetings held | 1 IDP/Budget/PMS Steering Committee meetings held | 1 IDP/Budget/PMS Steering Committee meetings held | Director INDEP | Agenda & Attandance register
|  | Public Participation | To ensure public involvement in Mayoral Imbizo 's within a financial year | # of Mayoral Imbizos held per quarter | Number | 4 Mayoral Imbizo s held | 4 Mayoral Imbizos held | Operational | 1 Mayoral Imbizos held | 1 Mayoral Imbizos held | 1 Mayoral Imbizos held | 1 Mayoral Imbizos held | Manager (Mayors Office) | Agenda & Attandance register
| Improved Governance and Organisational Excellence | Internal Audit | To ensure functionality of Audit committee within a financial year | # of Audit Committee meetings held per quarter. | Number (Accumulative) | 2 Audit Committee meetings held | 4 Audit Committee meeting held | Operational | 1 Audit Committee meetings held | 1 Audit Committee meetings held | 1 Audit Committee meetings held | 1 Audit Committee meetings held | Municipal Manager | Agenda, Minutes & Attandance register
| Improved Governance and Organisational Excellence | Risk | To ensure functionality of Risk committee within the financial year. | # of Risk Committee meetings held per quarter. | Number (Accumulative) | 3 Risk Committee meeting held | 4 Risk Committee meetings held | Operational | 1 Risk Committee meetings held | 1 Risk Committee meetings held | 1 Risk Committee meetings held | 1 Risk Committee meetings held | Municipal Manager | Agenda, Minutes & Attandance register
| Improved Governance and Organisational Excellence | Risk | To ensure functionality of Risk committee within the financial year. | # of Approved Fraud and Ani Coruption strategy | Number | New Indicator | Approved Fraud and Anti Corruption strategy | Operational | N/A | N/A | N/A | Approved Fraud and Anti Corruption strategy | Municipal Manager | Approved Fraud and Anti Corruption strategy
| Improved Governance and Organisational Excellence | Internal Audit | To conduct quarterly assessment on municipal performance information. | # of performance audit reports issued per quarter. | Number | 2 Performance audit reports issued | 4 Performance audit reports issued | Operational | 1 Performance audit reports issued | 1 Performance audit reports issued | 1 Performance audit reports issued | 1 Performance audit reports issued | Municipal Manager | Performance Audit report tabled in council and resolution
| Improved Governance and Organisational Excellence | Internal Audit | To develop annual year internal audit plan and implement by 30 June 2016. | Approved audit plan and % of the IA plan implementation. | Percentage | 90% IA plan Implementation | 100% IA plan implementation | Operational | 25% IA plan implementation | 50% IA plan implementation | 75% IA plan implementation | 100% IA plan implementation | Municipal Manager/ All Directors | Approved Internal Audit plan
| Improved Governance and Organisational Excellence | Internal Audit | To attain Clean Audit by ensuring compliance to all governance; financial management and reporting requirements by 12 December 2015 | % of internal audit issues resolved (# of Internal Audit issues resolved / # of issues raised) | Percentage | 60% internal audit issues resolved | 100% internal audit issues resolved | Operational | 25% internal audit issues resolved | 50% internal audit issues resolved | 75% internal audit issues resolved | 100% internal audit issues resolved | Municipal Manager/ All Directors | Proof of Internal Audit issues resolved
| Improved Governance and Organisational Excellence | Internal Audit | To attain clean audit | Development and approal of AG action plan by 31 January 2016 | Date | 31/01/2015 | 31/01/2016 | Operational | N/A | N/A | 31/01/2016 | N/A | Municipal Manager/ CFO | Approved AG action plan
| Improved Governance and Organisational Excellence | Internal Audit | To attain Clean Audit by ensuring compliance to all governance; financial management and reporting requirements by 30 June 2016 | % in Addressing Audit quesries (2014/15) | Percentage | 90% Audit querries addresed | 100% Audit querries addresed | Operational | N/A | N/A | 50% AG issues resolved | 100% AG issues resolved | Municipal Manager/ All Directors | resolved AG issues and POE 's submitted
| Improved Governance and Organisational Excellence | Risk management | To ensure efffective implementation of risk mitigations actions 30 June 2016. | % of Risk issues resolved (# Risk issues implemented / resolved / # of risks identified) | Percentage | 80% Risk issues resolved | 100% Risk issues resolved | Operational | 25% Risk issues resolved | 50% Risk issues resolved | 75% Risk issues resolved | 100% Risk issues resolved | Municipal Manager/ All Directors | Resolved Risk issues and POE submitted

## Capital Works Plan- PROJECTS
2015/16 CAPITAL WORKS PLAN SUMMARY OF CAPITAL AND OPERATIONAL PROJECTS PER RESPONSIBLE MANAGER
Vote Nr | Key Performance Area | Strategic Objective | Programme | Measurable Objective | Project Name | Start Date | Completion date | Project Owner | Source of funding | Budget | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | Evidence required
62 | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | Access to municipal roads by 31 March 2016 | Construction of Ga-Kgapane Storm water channels | 01/07/2015 | 31/03/2016 | Director INDEP | GLM | 2400000 | Develop specification and submit to SCM unit for advertisement | Advertise and appoint service provider | Completion stage : project completed and handed-over to the municipality | N/A | Completion certificate
62 | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | Purchasing of pedestrian roller by 31 March 2015 | Pedestrian roller | 01/07/2015 | 31/03/2016 | Director INDEP | GLM | 120000 | Develop specification and submit to SCM unit for advertisement | Advertise and appoint service provider | Pedestrian roller purchased | N/A | Delivery note
62 | Basic Service Delivery | Access to Sustainable Basic Services | Roads & Stormwater | Purchasing of walker compactor by 31 March 2016 | Purchasing of walker compactor | 01/07/2015 | 31/03/2016 | Director INDEP | GLM | 50000 | Develop specification and submit to SCM unit for advertisement | Advertise and appoint service provider | Walker Compactor purchased | N/A | Delivery note
29 | Basic Service Delivery | Access to Sustainable Basic Services | Roads | Rehabilitation of Modjadjiskloof street for 2km by 30 June 2016 | Rehabilitation of Modjadjiskloof street | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 4000000 | Develop specification and submit to SCM unit for procurement | Advertise and appoint service provider for Rehabilitation of Modjadjiskloof Street | Layer works completed for 2km | Project Completed | Completion certificate
29 | Basic Service Delivery | Access to Sustainable Basic Services | Roads | Rehabilitation of street at Ga-Kgapane for 2km by 30 June 2016 | Rehabilitation of Ga-Kgapane street | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 4000000 | Develop specification and submit to SCM unit for advertisement | Advertise and appoint service provider for construction of Rehabilitation of Ga-Kgapane street | Layer works completed for 2km | Project Completed | Completion certificate
29 | Basic Service Delivery | Access to Sustainable Basic Services | Roads | Upgrading of street from gravel to paving blocks for Itieleng-Sekgosese for 1.8km by 30 June 2016 | Itieleng- Sekgosese Street Paving | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 5300000 | Advertise tender to appoint contractors | Appoint service provider for construction of Itieleng- Sekgosese Street Paving | Earthworks completed and layer works completed for 1km | Project Completed | Completion certificate
29 | Basic Service Delivery | Access to Sustainable Basic Services | Roads | Upgrading of street from gravel to concrete paving blocks for Refilwe for 1.8km by 30 June 2016 | Refilwe Street Paving | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 5300000 | Advertise tender to appoint contractors | Appoint service provider for construction of Refilwe Street Paving | Earthworks completed and layer works completed for 1km | Project Completed | Completion certificate
29 | Basic Service Delivery | Access to Sustainable Basic Services | Roads | Upgrading of street from gravel to concrete paving blocks for Mmamakata for 1.8km by 30 June 2016 | Mmamakata Raselaka Street Paving | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 5300000 | Advertise tender to appoint contractors | Appoint service provider for construction of Mmamakata Raselaka Street Paving | Earthworks completed and layer works completed for 1km | Project Completed | Completion certificate
29 | Basic Service Delivery | Access to Sustainable Basic Services | Roads | Upgrading of street from gravel to concrete paving blocks for Lemondokop for 1.8km by 30 June 2016 | Lemondokop Street Paving | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 5000000 | Advertise tender to appoint contractors | Appoint service provider for construction of Lemondokop Street Paving | Earthworks completed and layer works completed for 1km | Project Completed | Completion certificate
| Basic Service Delivery | Access to Sustainable Basic Services | Roads | Upgrading of street from gravel to concrete paving for 1.8km Sekgopo by 30 June 2016 | Sekgopo street paving | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 700000 | Develop terms of reference and submit to SCM for advertisement | Advertise and appoint service providers for planning of Goedplaas Community Hall project | Appoint service provider. Technical report and preliminary designs submitted | Designs completed and advertise for construction | Completion certificate
| Basic Service Delivery | Access to Sustainable Basic Services | Roads (MIG) | Upgrading of street from gravel to concrete paving blocks for 1.8km at Sephukubje by 30 June 2016 | Sephukhubje Street Paving | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | 4210240 | Advertise tender to appoint contractors | Appoint service provider for construction of Sephukhubje Street Paving | Earthworks completed and layer works completed for 1km | Project Completed | Completion certificate
| Basic Service Delivery | Access to Sustainable Basic Services | Roads (MIG) | Upgrading of street from gravel to concrete paving blocks for 1.8km at Seatlaleng by 30 June 2016 | Seatlaleng Street Paving | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | 6000000 | Advertise tender to appoint contractors | Appoint service provider for construction of Seatlaleng Street Paving | Earthworks completed and layer works completed for 1km | Project Completed | Completion certificate
| Basic Service Delivery | Access to Sustainable Basic Services | Roads (MIG) | Upgrading of street from gravel to concrete paving blocks for 1.8km at Mohlakong by 30 June 2016 | Mohlakong Street paving | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | 6000000 | Advertise tender to appoint contractors | Appoint service provider for construction of Mohlakong Street paving | Earthworks completed and layer works completed for 1km | Project Completed | Completion certificate
| Basic Service Delivery | Access to Sustainable Basic Services | Roads (MIG) | Upgrading of street from gravel to concrete paving blocks for 1.8km at Matshelapata by 30 June 2016 | Matshelapata Street Paving | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | 6000000 | Advertise tender to appoint contractors | Appoint service provider for construction of Matshelapata Street Paving | Earthworks completed and layer works completed for 1km | Project Completed | Completion certificate
| Basic Service Delivery | Access to Sustainable Basic Services | Roads (MIG) | Upgrading of street from gravel to concrete paving blocks for 1.8km at Shawela by 30 June 2016 | Shawela Street Paving | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | 6000000 | Advertise tender to appoint contractors | Appoint service provider for construction of Shawela Street Paving | Earthworks completed and layer works completed for 1km | Project Completed | Completion certificate
29 | Basic Service Delivery | Access to Sustainable Basic Services | Roads (MIG) | Upgrading of street from gravel to concrete paving blocks for 1.8km at Sekgopo-Maboying by 30 June 2016 | Sekgopo-Maboying Street Paving | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | 6000000 | Advertise tender to appoint contractors | Appoint service provider for construction of Sekgopo-Maboyini Street Paving | Earthworks completed and layer works completed for 1km | Project Completed | Completion certificate
29 | Basic Service Delivery | Access to Sustainable Basic Services | Roads (MIG) | Upgrading of street from gravel to concrete paving blocks for 1.8km at Thlothlokwe by 30 June 2016 | Thlothlokwe street paving | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | 6000000 | Advertise tender to appoint contractors | Appoint service provider for construction of Thlothlokwe street paving | Earthworks completed and layer works completed for 1km | Project Completed | Completion certificate
29 | Basic Service Delivery | Access to Sustainable Basic Services | Roads (MIG) | Upgrading of street from gravel to concrete paving blocks for 1.8km at Shamfana by 30 June 2016 | Shamfana Street Paving | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | 6000000 | Advertise tender to appoint contractors | Appoint service provider for construction of Shamfana Street Paving | Earthworks completed and layer works completed for 1km | Project Completed | Completion certificate
29 | Basic Service Delivery | Access to Sustainable Basic Services | Roads (MIG) | Upgrading of street from gravel to concrete paving blocks for 1.8km at Kherobeni by 30 June 2016 | Kherobeng Street Paving | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | 6000000 | Advertise tender to appoint contractors | Appoint service provider for construction of Kherobeng Street Paving | Earthworks completed and layer works completed for 1km | Project Completed | Completion certificate
29 | Basic Service Delivery | Access to Sustainable Basic Services | Transport | Planning and designing of taxi rank at Khosotupa by 30 June 2015 | Khosutupa Taxi Rank | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 2000000 | Advertise tender to appoint contractors | Appoint service provider for design and planning of Khosutupa Taxi Rank | Steel structure and toilets completed. Paving complete for 100 square meters | Project Completed | Completion certificate
29 | Basic Service Delivery | Access to Sustainable Basic Services | Transport | Construction of taxi rank at Wholesale by 30 June 2015 | Wholesale Taxi Rank | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 2000000 | Advertise tender to appoint contractors | Appoint service provider for design and planning of Wholesale Taxi Rank | Steel structure and toilets completed. Paving complete for 100 square meters | Project Completed | Completion certificate
29 | Basic Service Delivery | Access to Sustainable Basic Services | Transport | Construction of taxi rank at Mamphakati by 30 June 2015 | Mamphakati Taxi Rank | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 2000000 | Advertise tender to appoint contractors | Appoint service provider for design and planning of Mamphakati Taxi Rank | Steel structure and toilets completed. Paving complete for 100 square meters | Project Completed | Completion certificate
29 | Basic Service Delivery | Access to Sustainable Basic Services | Transport | Ga-Kgapane Taxi rank paving and storage tank by 30 June 2016 | Ga-Kgapane Taxi Rank | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 480000 | Develop specification and submit to SCM unit for advertisement | Avertise and appoint service provider for construction of Ga-Kgapane Taxi Rank | Earthworks, layer works and kerbing completed | Project Completed | Completion certificate
29 | Basic Service Delivery | Access to Sustainable Basic Services | Community services | Construction of Shotong Library by 30 June 2016 | Shotong Library | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 2600000 | Advertise tender to appoint contractors | Appoint service provider for construction of Shotong Library | Foundations completed and building at roof level | Project Completed | Completion certificate
29 | Basic Service Delivery | Access to Sustainable Basic Services | Community services | Construction of Rotterdam Library by 30 June 2016 | Rotterdam Library | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 2600000 | Advertise tender to appoint contractors | Appoint service provider for construction of Rotterdam Library | Foundations completed and building at roof level | Project Completed | Completion certificate
29 | Basic Service Delivery | Access to Sustainable Basic Services | Community services (MIG) | Construction of Mokwakwaila Library by 30 June 2016 | Mokwakwaila Library | 01/07/2015 | 30/06/2016 | Director COMM | GLM | 1000000 | Advertise tender to appoint contractors | Advertise for construction of Mokwakwaila library | Foundations completed and building at roof level | Project Completed | Completion certificate
| Basic Service Delivery | Access to Sustainable Basic Services | Community services | Construction of Matshwi Community Hall by 30 June 2016 | Matshwi Community Hall | 01/07/2015 | 30/06/2016 | Director COMM | GLM | 2400000 | Advertise tender to appoint contractors | Appoint service provider for construction of Matshwi Community Hall | Foundations completed and building at roof level | Project Completed | Completion certificate
29 | Basic Service Delivery | Access to Sustainable Basic Services | Community services | Construction of Mohlele Community Hall by 30 June 2016 | Mohlele Community Hall | 01/07/2015 | 30/06/2016 | Director COMM | GLM | 2400000 | Advertise tender to appoint contractors | Appoint service provider for construction of Mohlele Community Hall | Foundations completed and building at roof level | Project Completed | Completion certificate
29 | Basic Service Delivery | Access to Sustainable Basic Services | Community services | Construction of Mamaila-Kolobetona Community Hall by 30 June 2016 | Mamaila - Kolobetona Community Hall | 01/07/2015 | 30/06/2016 | Director COMM | GLM | 2400000 | Advertise tender to appoint contractors | Appoint service provider for construction of Mamaila - Kolobetona Community Hall | Foundations completed and building at roof level | Project Completed | Completion certificate
29 | Basic Service Delivery | Access to Sustainable Basic Services | Community services | Construction of Shamfana Community Hall by 30 June 2016 | Shamfana Community Hall | 01/07/2015 | 30/06/2016 | Director COMM | GLM | 2400000 | Advertise tender to appoint contractors | Appoint service provider for construction of Shamfana Community Hall | Foundations completed and building at roof level | Project Completed | Completion certificate
| Basic Service Delivery | Access to Sustainable Basic Services | Community services | Construction of Ward 2 Community Hall by 30 June 2016 | Ward 2 Community Hall | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 2400000 | Advertise tender to appoint contractors | Appoint service provider for construction of Ward 2 Community Hall | Foundations completed and building at roof level | Project Completed | Completion certificate
| Basic Service Delivery | Access to Sustainable Basic Services | Community services | Construction of Ward 5 Community Hall by 30 June 2016 | Ward 5 Community Hall | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 2400000 | Advertise tender to appoint contractors | Appoint service provider for construction of Ward 5 Community Hall | Foundations completed and building at roof level | Project Completed | Completion certificate
29 | Basic Service Delivery | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of Goedplass Community Hall by 30 June 2016 | Goedplaas Community Hall | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | 270000 | Develop terms of reference and submit to SCM for advertisement | Advertise and appoint service providers for planning of Goedplaas Community Hall project | Appoint service provider. Technical report and preliminary designs submitted | Designs completed and advertise for construction | Technical / Design report
29 | Basic Service Delivery | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of Thakgalane Community Hall by 30 June 2016 | Thakgalane Community Hall | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | 270000 | Develop terms of reference and submit to SCM for advertisement | Advertise and appoint service provider for planning of Thakgalane Community Hall project | Appoint service provider. Technical report and preliminary designs submitted | Designs completed and advertise for construction | Technical / Design report
29 | Basic Service Delivery | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of Ntata Community Hall by 30 June 2016 | Ntata Community Hall | 01/07/2015 | 30/06/2016 | Director INDEP | MIG | 271000 | Develop terms of reference and submit to SCM for advertisement | Advertise and appoint service provider for planning of Ntata Community Hall project | Appoint service provider. Technical report and preliminary designs submitted | Designs completed and advertise for construction | Technical / Design report
| Basic Service Delivery | Access to Sustainable Basic Services | Community services | Purchasing of 2000 Chairs and 10 Tables for Mokwakwaila and Senwamokgope Community Halls by 31 March 2016 | 2000 Chairs and 10 Tables for Mokwakwaila and Senwamokgope Community Halls | 01/07/2015 | 31/03/2016 | Director INDEP | GLM | 100000 | Develop, Submit terms of references to SCM. | Advertise and appoint service provider | 2000 chairs and 10 Tables puchased for Mokwakwaila and Senwamokgope Community halls | N/A | Delivery note
29 | Basic Service Delivery | Access to Sustainable Basic Services | Community Services | Construction of Mamanyoha Sports Complex by 30 June 2016 | Mamanyoha Sports Complex | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 6414503 | Advertise tender to appoint contractors | Appoint service provider for construction of Mamanyoha Sports Complex | Fencing, earthworks, toilets and change-rooms completed | Project Completed | Completion certificate
29 | Basic Service Delivery | Access to Sustainable Basic Services | Community Services | Construction of Rotterdam Sports Complex by 30 June 2016 | Rotterdam Sports Complex | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 6414503 | Advertise tender to appoint contractors | Appoint service provider for construction of Rotterdam Sports Complex | Fencing, earthworks, toilets and change-rooms completed | Project Completed | Completion certificate
29 | Basic Service Delivery | Access to Sustainable Basic Services | Community Services | Planning and designing of Madumeleng/Shotong Sports Complex by 30 June 2016 | Madumeleng/Shotong Sports Complex | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 500000 | Develop terms of reference and submit to SCM for advertisement | Advertise and appoint service provider for planning of Madumeleng/Shotong Sports Complex project | Appoint service provider. Technical report and preliminary designs submitted | Designs completed and advertise for construction | Technical / Design report
29 | Basic Service Delivery | Access to Sustainable Basic Services | Community Services | Planning and designing of Thakgalane Sports Complex by 30 June 2016 | Thakgalane Sports Complex | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 500000 | Develop terms of reference and submit to SCM for advertisement | Advertise and appoint service provider for planning of Thakgalane Sports Complex project | Appoint service provider. Technical report and preliminary designs submitted | Designs completed and advertise for construction | Technical / Design report
29 | Basic Service Delivery | Access to Sustainable Basic Services | Community Services | Construction of Sekgopo Youth Centre by 30 June 2016 | Sekgopo Youth Centre | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 2250000 | Advertise tender to appoint contractors | Appoint service provider for the construction of Sekgopo Youth Centre | Fencing and foundation completed. Building at roof level | Project Completed | Completion certificate
34 | Basic Service Delivery | Access to Sustainable Basic Services | Community Services | Construction of Ga-Kgapane Youth Centre by 30 June 2016 | Ga-Kgapane Youth Centre | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 2250000 | Advertise tender to appoint contractors | Appoint contractor to construct Ga-Kgapane Youth Centre | Fencing and foundation completed. Building at roof level | Project Completed | Completion certificate
29 | Basic Service Delivery | Access to Sustainable Basic Services | Community Services | Construction of Roerfontein Youth Centre by 30 June 2016 | Roerfontein Youth Centre | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 2250000 | Advertise tender to appoint contractors | Appoint contractor to construct Roerfontein Youth Centre | Fencing and foundation completed. Building at roof level | Project Completed | Completion certificate
29 | Basic Service Delivery | Access to Sustainable Basic Services | Community Services | Construction of Mokwakwaila Youth Centre by 30 June 2016 | Mokwaikwaila Youth Centre | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 2250000 | Advertise tender to appoint contractors | Appoint contractor to construct Mokwakwaila Youth Centre | Fencing and foundation completed. Building at roof level | Project Completed | Completion certificate
29 | Basic Service Delivery | Access to Sustainable Basic Services | Community Services | Construction of Madumeleng Old Age Facility by 30 June 2016 | Madumeleng Old Age Facility | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 1800000 | Advertise tender to appoint contractors | Appoint contractor to construct Madumeleng Old Age Facility | Fencing and foundation completed. Building at roof level | Project Completed | Completion certificate
29 | Basic Service Delivery | Access to Sustainable Basic Services | Community Services | Construction of Roerfontein Old Age Facility by 30 June 2016 | Roerfontein Old Age Facility | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 1800000 | Advertise tender to appoint contractors | Appoint contractor to construct Roerfontein Old Age Facility | Fencing and foundation completed. Building at roof level | Project Completed | Completion certificate
54 | Basic Service Delivery | Access to Sustainable Basic Services | Community Services | Construction of Ga-Kgapane Old Age Facility by 30 June 2016 | Ga-Kgapane Old Age Facility | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 1800000 | Advertise tender to appoint contractors | Appoint contractor to construct Ga-Kgapane Old Age Facility | Fencing and foundation completed. Building at roof level | Project Completed | Completion certificate
52 | Basic Service Delivery | Access to Sustainable Basic Services | Electricity | Upgrading of electricity infrastructure at Modjadjiskloof for compliance with NER by 31 March 2016 | Upgrade of Electricity to NER Standards | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 1000000 | Develop specification and submit to SCM unit for advertisement | Advertise contractors for upgrading of electricity network | Appoint contractors for the upgrading of electricity | Commence with upgrading and complete the project | Completion certificate
25 | Basic Service Delivery | Access to Sustainable Basic Services | Street Lighting | Installation Energy Efficient Street light by 31 March 2016 | Energy Efficient Street light | 01/07/2015 | 31/03/2016 | Director INDEP | GLM | 500000 | Develop specification and submit to SCM unit for advertisement | Advertise and appoint Service Provider and Installation commences | Project completed | N/A | Progress report
25 | Basic Service Delivery | Access to Sustainable Basic Services | Electricity | Installation of Prepaid Meters in Mokgoba Village by 31 March 2016 | Prepaid meters in Mokgoba | 01/07/2015 | 31/03/2016 | Director INDEP | GLM | 640000 | Develop specification and submit to SCM unit for advertisement | Advertise and appoint Service Provider and Installation commences | Project completed | N/A | Progress report
25 | Basic Service Delivery | Access to Sustainable Basic Services | Traffic and Licensing | Purchasing of Road Block Trailer and Equipment by 31 March 2016 | Road Block Trailer and Equipment | 01/07/2015 | 31/03/2016 | Director COMM | GLM | 250000 | Develop specification and submit to SCM unit for advertisement | Advertise and appoint Service Provider | Road Block Trailer purchased | N/A | Delivery note
25 | Basic Service Delivery | Access to Sustainable Basic Services | DLTC | Purchase and Installation of Strong Room in Modjadjiskloof by 31 March 2016 | Strong room Modjadjiskloof DLTC | 01/07/2015 | 31/03/2016 | Director COMM | GLM | 250000 | Develop specification and submit to SCM unit for advertisement | Advertise and appoint of Service Provider | Strong room purchased and installed | N/A | Completion certificate
25 | Basic Service Delivery | Access to Sustainable Basic Services | DLTC | Relocation of DLTC by 31 December 2016 | Relocation of DLTC | 01/07/2015 | 31/03/2016 | Director COMM | GLM | 250000 | Develop specification and submit to SCM unit for advertisement | Advertise and appoint service provider | DLTC relocated to Senwamokgope | N/A | Completion certificate
25 | Basic Service Delivery | Access to Sustainable Basic Services | DLTC | Purchase and Installation of Cublicles and Bullet proof Glass for DLTC by 31 March 2016. | Cubicle and Bullet proof Glass for DLTC | 01/07/2015 | 31/03/2016 | Director COMM | GLM | 250000 | Develop and submit specification to SCM for advertisement | Advertise and appoint service provider | Cubicle and bullet proof Purchased and Installed | N/A | Completion certificate
25 | Basic Service Delivery | Access to Sustainable Basic Services | DLTC | Completion for constructing Modjadjiskloof DLTC by 31 March 2016. | Completion of Modjadjiskloof DLTC | 01/07/2015 | 31/03/2016 | Director COMM | GLM | 250000 | Develop and submit specification to SCM for advertisement | Advertise and appoint service provider | Modjadjiskloof DLTC completed | N/A | Completion certificate
25 | Basic Service Delivery | Access to Sustainable Basic Services | Traffic and Licensing | Purchasing of Traffic Blue Lights (2) by 31 December 2016 | Traffic Blue Lights | 01/07/2015 | 31/03/2016 | Director COMM | GLM | 10000 | Develop and submit specification to SCM for procurement | 2 Traffic Lights purchased and Delivered | N/A | N/A | Delivery note
25 | Basic Service Delivery | Access to Sustainable Basic Services | Traffic and Licensing | Purchasing of 6 Stop Watchers | Stop Watchers | 01/07/2015 | 31/03/2016 | Director COMM | GLM | 5000 | Develop and submit specification to SCM for procurement | 6 Stop Watchers purchased and delivered | N/A | N/A | Delivery note
34 | Basic Service Delivery | Access to Sustainable Basic Services | Waste Management | Construction of landfill site at Maphalle village by 31 March 2016 | Maphalle Landfill Site | 01/07/2015 | 30/06/2016 | Director COMM | GLM | 3000000 | Advertise tender to appoint contractors | Advertise and appoint service provider for construction | Commence with contruction activities for landfill site | Project Completed | Completion certificate
| Basic Service Delivery | Access to Sustainable Basic Services | Waste Management | Rehabilitation of Old Modjadjiskloof Dumping Site | Modjadjiskloof Dumping site | 01/07/2015 | 31/03/2016 | Director COMM | GLM | 2500000 | Develop and submit specification to SCM for advertisement | Advertise and appoint service provider | Old Modjadjiskloof Dumping site rehabilitated | N/A | Completion certificate
22 | Basic Service Delivery | Access to Sustainable Basic Services | Waste Management | Purchasing of Swivel Bins by 31 March 2016 | Swivel Bins | 01/07/2015 | 31/03/2016 | Director COMM | GLM | 150000 | Develop and submit specification to SCM for advertisement | Advertsiment and appointment of Service Provider | Swivel Bins Purchased | N/A | Delivery note
32 | Basic Service Delivery | Access to Sustainable Basic Services | Waste Management | Purchasing of Skips Bins by 31 March 2016 | Skips Bins | 01/07/2015 | 31/03/2016 | Director COMM | GLM | 250000 | Develop and submit specification to SCM for advertisement | Advertsiment and appointment of Service Provider | Skips Bins Purchased | N/A | Delivery note
32 | Basic Service Delivery | Access to Sustainable Basic Services | Parks and Recreation | Upgrading of Ga-Kgapane Parks Below Civic Centre by 30 June 2016 | Ga-Kgapane Parks Below Civic centre | 01/07/2015 | 30/06/2016 | Director COMM | GLM | 300000 | Advertise tender to appoint contractors | N/A | Appoint service provider to upgrade the park | Ga-Kgapane Parks upgraded | Completion certificate
32 | Basic Service Delivery | Access to Sustainable Basic Services | Parks and Recreation | Purchasing of 7 Chain Saws by 31 December 2015 | Chain Saws | 01/07/2015 | 31/12/2015 | Director COMM | GLM | 92000 | Develop and submit specification to SCM for advertisement | Advertise and appoint service provider. Chain Saws purchased and delivered. | N/A | N/A | Delivery note
32 | Basic Service Delivery | Access to Sustainable Basic Services | Sports, Art and Recreation | Purchasing of Electric Lawn Mower by 31 March 2016 | Electric Lawn Mower | 01/07/2015 | 31/12/2015 | Director COMM | GLM | 20000 | Develop and submit specification to SCM for procurement | Electric Lawn Mower purchased and delivered | N/A | N/A | Delivery note
32 | Basic Service Delivery | Access to Sustainable Basic Services | Sports, Art and Recreation | Purchasing of Car Trailer by 31 march 2016 | Car Trailer | 01/07/2015 | 31/12/2015 | Director COMM | GLM | 30000 | Develop and submit specification to SCM for procurement | Car Trailer purchased and delivered | N/A | N/A | Delivery note
32 | Basic Service Delivery | Access to Sustainable Basic Services | Sports, Art and Recreation | Purchasing of Drive on Lawn Mower by 31 March 2016 | Drive on Lawn Mower | 01/07/2015 | 31/12/2015 | Director COMM | GLM | 150000 | Develop and submit specification to SCM for advertisement | Drive on Lawn Mower purchased and delivered | N/A | N/A | Delivery note
32 | Basic Service Delivery | Access to Sustainable Basic Services | Sports, Art and Recreation | Enhancement and Beautification of Town Entrances by 31 March 2016 | Entrances Beautification | 01/07/2015 | 30/06/2016 | Director COMM | GLM | 200000 | N/A | Develop and submit specification to SCM for advertisement | Advertisement and appointment of service provider | Town entrances beautification project completed | Completion certificate
32 | Basic Service Delivery | Access to Sustainable Basic Services | Community Services | Fencing of the New Cemetery by 30 June 2016 | Cemetery Fencing | 01/07/2015 | 30/06/2016 | Director COMM | GLM | 1000000 | Develop and submit specification to SCM for advertisement | Advertisement and appointment of service provider | Fencing and 280m of concrete beam completed | Project Completed | Completion certificate
34 | Basic Service Delivery | Access to Sustainable Basic Services | Community Services | Purchasing of Disaster Emergency lights by 31 December 2015 | Emergency Disaster Lights | 01/07/2015 | 31/12/2015 | Director COMM | GLM | 20000 | Develop and submit specification to SCM for procurement | Disaster Emergency Lights purchased and delivered | N/A | N/A | Delivery note
34 | Basic Service Delivery | Access to Sustainable Basic Services | Community Services | Purchasing of Fire Extinguisher by 31 March 2015 | Fire Extinguishers | 01/07/2015 | 31/03/2016 | Director COMM | GLM | 300000 | Develop and submit specification to SCM for advertisement | Advertisement and appointment of Service Provider | Fire Extinguishers purchased and delivered | N/A | Delivery note
34 | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | Purchasing of 4 Printers (Revenue, Assets and SCM) by 30 June 2016 | 4 Printers | 01/07/2015 | 30/06/2016 | Director Corp | GLM | 40000 | N/A | Develop and submit specification to SCM for procurement | Advertisement and Appointment of Service Provider | 4 Printers purchased and delivered | Delivery note
34 | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | Purchasing of 2 Printers (Salary & Revenue Section) by 30 June 2016. | 2 Printers | 01/07/2015 | 30/06/2016 | Director Corp | GLM | 300000 | Develop and submit specification to SCM for advertisement | Advertisement and Appointment of Service Provider | 2 Printers purchased and delivered | N/A | Delivery note
34 | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | Purchasing of All in One (Fax, Scan and Print) for budget office by 30 June 2016 | All in One Printer | 01/07/2015 | 30/06/2016 | Director Corp | GLM | 10000 | N/A | Develop and submit specification to SCM for procurement | Advertisement and Appointment of Service Provider | 1 All in one Fax, Scan and printer purchased and delivered | Delivery note
34 | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | Purchasing of an Advance Scanner (Huge MB) by 30 June 2016 | Advance Scanner (Huge) | 01/07/2015 | 30/06/2016 | Director Corp | GLM | 40000 | Develop and submit specification to SCM for advertisement | Advertisement and Appointment of Service Provider | Advance Scanner purchased and delivered | N/A | Delivery note
34 | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | Puchasing of Money Counting Machine by 31 March 2016 | Money Counting Machine | 01/07/2015 | 30/06/2016 | CFO | GLM | 3000 | Submit specifications to SCM | Advertisement and Appointment of Service Provider | Money Counting machine purchased and delivered | N/A | Delivery note
34 | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | Purchasing of office Furniture by 30 June 2016 | Office Furniture | 01/07/2015 | 30/06/2016 | Director Corp | GLM | 500000 | N/A | Develop and submit specification to SCM for advertisement | Advertisement and Appointment of Service Provider | Office Furniture purchased and delivered | Delivery note
34 | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | Upgrading of Telephone Management System by 31 March 2016 | Telephone Management System | 01/07/2015 | 31/03/2016 | Director Corp | GLM | 150000 | Develop and submit specification to SCM for advertisement, Advertise and appoint service provider | Telephone management system upgraded | N/A | N/A | Completion certificate
31 | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | Purchasing of 2 Mobile Overhead Projectors by 31 March 2016 | Mobile Overhead Projectors | 01/07/2015 | 31/03/2016 | Director Corp | GLM | 40000 | Develop and submit specification to SCM for advertisement | Appointment of Service Provider | 2 Mobile Overhead projector purchased and delivered | N/A | Delivery note
31 | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | Implementation of Disaster Recovery Plan by 30 June 2016 | Disaster Recovery Plan | 01/07/2015 | 30/06/2016 | Director Corp | GLM | 1000000 | N/A | Develop and submit specification to SCM for advertisement | Advertisement and Appointment of Service Provider | Disaster Recovery Plan Implemented | Completion certificate
31 | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | Replacement of 15 Laptops by 30 June 2016 | Laptop Replacement | 01/07/2015 | 30/06/2016 | Director Corp | GLM | 400000 | N/A | Develop and submit specification to SCM for advertisement | Advertisement and Appointment of Service Provider | 15 Laptops purchased and delivered | Delivery note
31 | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | Replacement of 20 Desktops by 30 June 2016 | Desktops replacements | 01/07/2015 | 30/06/2016 | Director Corp | GLM | 200000 | N/A | Develop and submit specification to SCM for advertisement | Advertisement and Appointment of Service Provider | 20 Desktops purchased and delivered | Delivery note
| Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | Purchase and Installation of of Uninterupted Power Supply by 30 June 2016 | Uninterrupted Power Supply | 01/07/2015 | 30/06/2016 | Director Corp | GLM | 150000 | N/A | Develop and submit specification to SCM for advertisement | Advertisement and Appointment of Service Provider | Uninterupted Power supply Installed | Delivery note
| Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | Purchasing of Traffic System Upgrade by 31 March 2016 | Traffic System Upgrade | 01/07/2015 | 31/03/2016 | Director COMM | GLM | 100000 | Develop and submit specification to SCM for advertisement | Advertisement and appointment of Service Provider | Traffic System purchased and Installed | N/A | Completion certificate
| Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | Purchasing and Installation of Brail Printer Software by 31 March 2016 | Brail Printer System | 01/07/2015 | 31/03/2016 | Director Corp | GLM | 100000 | Develop and submit specification to SCM for advertisement | Advertisement and appointment of Service Provider | Brail Printer Software purchased and Installed | N/A | Delivery note
| Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | Purchasing and Installation of Alli-Cad software by 31 March 2016 | Alli-Cad Software | 01/07/2015 | 31/03/2016 | Director Corp | GLM | 100000 | Develop and submit specification to SCM for advertisement | Advertisement and appointment of Service Provider | Alli-Cad system purchased and Installed | N/A | Installation certificate
| Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | Purchasing and Installation of Civil Designer Software by 31 March 2016 | Civil Designer Software | 01/07/2015 | 31/03/2016 | Director Corp | GLM | 100000 | Develop and submit specification to SCM for advertisement | Advertisement and appointment of Service Provider | Civil Designer Software purchased, installed and training completed | N/A | Installation certificate
| Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | Purchasing and Installation of Cash Power System by 31 March 2016 | Cash Power System | 01/07/2015 | 31/03/2016 | Director Corp | GLM | 150000 | Submit specifications to SCM | Advertisement and appointment of Service Provider | Cash Power system purchased and Installed | N/A | Completion certificate
| Municipal Transformation and Development | Improved Governance and Organisational Excellence | Information Technology | Purchasing and Installation of Call Log System by 31 March 2016 | Call Log System | 01/07/2015 | 31/03/2016 | Director Corp | GLM | 100000 | Submit specifications to SCM | Advertisement and appointment of Service Provider | Call Log System purchased and Installed | N/A | Completion certificate
| Municipal Transformation and Development | Improved Governance and Organisational Excellence | Equipments | Puchasing of Money Counting Machine by 31 March 2016 | Money Counting Machine | 01/07/2015 | 31/03/2016 | CFO | GLM | 3000 | Submit specifications to SCM | Advertisement and Appointment of Service Provider | Money Counting machine purchased and delivered | N/A | Delivery note
| Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | Purchasing and Installation of 10 Air Conditioners by 30 June 2016 | Air Conditioners | 01/07/2015 | 31/03/2016 | Director Corp | GLM | 50000 | Develop and submit specification to SCM for advertisement | Advertisement and appointment of Service Provider | 10 Air Conditioners purchased and Installed | N/A | Completion certificate
| Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | Purchasing of Recording Machine by 30 June 2016 | Recording Machine | 01/07/2015 | 31/03/2016 | Director Corp | GLM | 20000 | Submit specifications to SCM | Advertisement and Appointment of Service Provider | Recording Machine Purchased and delivered | N/A | Delivery note
| Municipal Transformation and Development | Improved Governance and Organisational Excellence | Assets Management | Purchase and Deliver of 2 Vehicles for Registry and Senwamokgope by 30 June 2016 | 2 Vehicles for Registry and Senwamokgope | 01/07/2015 | 31/03/2016 | Director Corp | GLM | 200000 | Submit specifications to SCM | Advertisement and Appointment of Service Provider | 2 Vehicles purchased and delivered | N/A | Delivery note
34 | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | Purchasing of a Refrigerator by 31 March 2016 | Refrigerator | 01/07/2015 | 31/03/2016 | Director Corp | GLM | 5000 | Submit specifications to SCM | Advertisement and Appointment of Service Provider | Refrigerator Purchased and Delivered | N/A | Delivery note
| Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | Purchasing of Mobile Filling Unit by 31 March 2016 | Mobile Filing Unit | 01/07/2015 | 31/03/2016 | Director Corp | GLM | 200000 | Submit specifications to SCM | Advertisement and Appointment of Service Provider | Mobile Filing Unit Purchased and delivered | N/A | Delivery note
| Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | Purchasing of 2 Aqua Cooler Bottles by 31 March 2016 | Aqua Cooler Bottles | 01/07/2015 | 31/03/2016 | Director Corp | GLM | 4000 | Submit specifications to SCM | Advertisement and Appointment of Service Provider | 2 Aqua Cooler Bottles purchased and delivered | N/A | Delivery note
| Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | Purchasing of 2 Aqua Cooler by 31 March 2016 | Aqua Cooler | 01/07/2015 | 31/03/2016 | Director Corp | GLM | 8000 | Submit specifications to SCM | Advertisement and Appointment of Service Provider | 2 Aqua Cooler purchased and delivered | N/A | Delivery note
| Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | Purchasing of Shredding Machine by 31 March 2016 | Shredding Machine | 01/07/2015 | 31/03/2016 | Director Corp | GLM | 5000 | Submit specifications to SCM | Advertisement and Appointment of Service Provider | Shredding Machine purchased and delivered | N/A | Delivery note
| Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | Purchasing of Microwave machine by 31 March 2016 | Microwave machine | 01/07/2015 | 31/03/2016 | Director Corp | GLM | 1500 | Submit specifications to SCM | Advertisement and Appointment of Service Provider | Microwave machine purchased and delivered | N/A | Delivery note
| Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | Purchasing of 4 Suggestion Boxes by 31 march 2016 | Suggestion Boxes | 01/07/2015 | 31/03/2016 | Director Corp | GLM | 60000 | Submit specifications to SCM | Advertisement and Appointment of Service Provider | Suggestion Boxes purchased and delivered | N/A | Delivery note
| Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | Purchasing of 4 Batho-Pele Banners by 31 March 2016 | Batho-Pele Banners | 01/07/2015 | 31/03/2016 | Director Corp | GLM | 15000 | Submit specifications to SCM | Advertisement and Appointment of Service Provider | 4 Batho-Pele Banners purchased and delivered | N/A | Delivery note
| Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | Purchase of Steel Fence and Gate for Senwamokgope sub-office by 31 March 2016 | Steel Fence and Gate | 01/07/2015 | 31/03/2016 | Director Corp | GLM | 20000 | Submit specifications to SCM for procurement | Advertisement and Appointment of Service Provider | Steel Fence and Gate purchased and erected at Senwamokgope sub-office | N/A | Completion certificate
| Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | Purchase of Counter (Security Burglar) Registry by 31 March 2016 | Counter for Registry (Security Burglar) | 01/07/2015 | 31/03/2016 | Director Corp | GLM | 15000 | Submit specifications to SCM | Advertisement and Appointment of Service Provider | Counter for Registry Installed | N/A | Completion certificate
| Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | Purchase of URNS for Mokwakwaila and Kgapane by 31 March 2016 | URNS (Mokwakwaila and Kgapane) | 01/07/2015 | 31/03/2016 | Director Corp | GLM | 1200 | Submit specifications to SCM | Advertisement and Appointment of Service Provider | URNS purchased and delivered | N/A | Delivery note
| Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | Purchase of Picture Camera by 31 March 2016 | Picture Camera | 01/07/2015 | 31/03/2016 | Director Corp | GLM | 15000 | Submit specifications to SCM | Advertisement and Appointment of Service Provider | Picture Camera Purchased and delivered | N/A | Proof of purchase
| Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | Purchase of 10 Folding Tables by 31 March 2016 | 10 Folding Tables | 01/07/2015 | 30/06/2016 | Director Corp | GLM | 10000 | Submit specifications to SCM | Advertisement and Appointment of Service Provider | 10 Folding Tables purchased and delivered | N/A | Delivery note
| Municipal Transformation and Development | Improved Governance and Organisational Excellence | Office Management | Purchasing of a Podium by 31 December 2015 | Podium | 01/07/2015 | 31/12/2015 | Manager Mayors Office | GLM | 10000 | Submit specifications to SCM and advertise | Podium Purchased and delivered | N/A | N/A | Delivery note
| Municipal Transformation and Development | Improved Governance and Organisational Excellence | Building | Interior Design for the main entrance (Registry and Corps) Foyer | Foyer to the main Interior Design (Registry and Corps) | 01/07/2015 | 31/03/2016 | Director Corp | GLM | 150000 | N/A | Submit specifications to SCM | Advertisement and Appointment of Service Provider | Interior Designs completed | Completion certificate
32 | Municipal Transformation and Development | Improved Governance and Organisational Excellence | Building | Refurbishment of Municipal Workshop and Stores | Municipal Workshop and Stores | 01/07/2015 | 30/06/2016 | Director INDEP | GLM | 500000 | Develop and Submit Specifications to SCM for advertisement | Advertisement for refurbishment of Municipal Workshop refurbished. | Appointment of service provider and commence with refurbishment. | Project Completed | Completion certificate

## MFMV PROJECTS (hidden)
KPA 4 MUNICIPAL FINANCIAL VIABILITY PROJECTS OUTCOME NINE (OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY)
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project / Initiative | Budget 2014/2015 | Budget 2014/2015 | Start Date | Completion Date | Milestones Qtr Ending Sept 2014 | Milestones Qtr Ending Dec 2014 | Milestones Qtr Ending March 2015 | Milestones Qtr Ending June 2015 | Project Owner
50 | Sustainable Financial Institution | Budget and Treasury | Installation of GPS system and training of end users by 31 March 2015 | GPS system and training | 80000 | 80000 | 01/07/2014 | 31/03/2015 | Tender advertisement for supply, delivery and training | Appointment of service provider to supply, instal and conduct training | Installation of GPS systems and training completed | n/a | CFO
50 | Sustainable Financial Institution | Budget and Treasury | Installation of security glass at Senwamokgope sub-office by 30 September 2014 | Security glass at Senwamokgope sub office | 8000 | 8000 | 01/07/2014 | 30/09/2014 | Request quatations for procurement, appoint service provider, supply and installation of security glass | n/a | n/a | n/a | CFO
50 | Sustainable Financial Institution | Budget and Treasury | To conduct environmental impact assessment, purchase new tanks, pumps and shades by 31 March 2015 | New tanks, pumps and shades | 550000 | 1300000 | 01/07/2014 | 31/03/2015 | Tender advertisement and appointment. | Conduct environmental impact assessment | tanks, pumps and shades purchased and environmental impact assessments conducted | n/a | CFO
54 | Access to Sustainable Basic Services | Property Services | To purchase 1 concrete mixer by 30 September 2014 | Concrete Mixer | 20000 | 65000 | 01/07/2014 | 30/09/2014 | Develop, submit specifications to SCM and purchase, 1 cocrete mixer purchased | n/a | n/a | n/a | INDEP / B & T
52 | Access to Sustainable Basic Services | Electricity Distribution | Purchasing of electrical tools and equipment by 30 September 2014 | Tools and equipment | 200000 |  | 01/07/2014 | 30/09/2014 | Develop, submit specifications to SCM and purchase, electrical tools and equipment purchased. | n/a | n/a | n/a | INDEP / B & T
50 | Sustainable Financial Institution | Indigent Management | To register qualifying indigents 30 June 2014 | Updating of Indigent Register | Operational | Operational | 01/07/2014 | 30/06/2015 | Collection of information on indigent households and update the register | Collection of information on indigent households and update the register | Collection of information on indigent households and update the register | qualifying indigent registered in the indigent register | CFO
50 | Sustainable Financial Institution | Revenue Management | Review, adopt and implement Revenue Enhancement Strategy 30 June 2015 | Revenue Enhancement Strategy | Operational | Operational | 01/07/2014 | 30/06/2015 | Review and adoption of Draft Revenue Enhancement Strategy | Implementation of the adopted Revenue Enhancement Strategy | Implementation of the adopted Revenue Enhancement Strategy | Revenue Emhancement strategy reviewed, adopted and implemented | CFO
50 | Sustainable Financial Institution | Revenue Management | To update household billing system information 30 Sept 2014 and implement | Data cleansing | Operational | Operational | 01/07/2014 | 30/06/2015 | Update households information on billing system | Approval by Council | Implement cleased database | Household billing sytem information updated | CFO
50 | Sustainable Financial Institution | Asset Management | To monitor the process of unbundling and make progress report by 30 June 2015 | Unbundling of Infrastructure Assets to update the asset register | Operational | Operational | 01/07/2014 | 30/06/2015 | Tender advertisement | Appointment of professional service provider for unbundling of municipal assets and updating of GRAP compialnt asset register. | Continuation of Unbundling of new municipal assets and updating of GRAP compliant asset register | Completion of compilation of GRAP compliant asset register | CFO
50 | Sustainable Financial Institution | Asset Management | o | Valuation Roll | Operational | Operational | 01/07/2014 | 30/06/2015 | Conduct assessment of supplementary valuation roll. | Conduct assessment of supplementary valuation roll. | Complete assessment of supplementary valuation roll | Approval of valuation roll by Council | CFO

## GGPP PROJECTS (hidden)
KPA 5 GOOD GOVERNANCE AND PUBLIC PARTICIPATION PROJECTS OUTPUT 5: DEEPEN DEMOCRACY THROUGH A REFINED WARD COMMITTEE MODEL, OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY)
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project Description | Original Budget 2014/2015 | Adjusted Budget 2014/2015 | Start Date | Completion Date | Milestones Qtr Ending Sept 2014 | Milestones Qtr Ending Dec 2014 | Milestones Qtr Ending March 2015 | Milestones Qtr Ending June 2015 | Project Owner
34 | Improved Governance and Organisational Excellence | Good Governance | Manage events effectively by 30 June 2015 | Communication and event management | 100000 | 100000 | 01/07/2014 | 30/06/2015 | Manage events and 25% of the budget spent | Manage events and 50% of the budget spent | Manage events and 75% of the budget spent | Manage events and 100% of the budget spent | MM
40 | Improved Governance and Organisational Excellence | Good Governance | To award academic excellent performers by 30 June 2015 | Municipal Mayor’s excellent award | 200000 | 400000 | 01/01/2015 | 31/03/2015 | n/a | n/a | n/a | Excellence award ceremony | MM
34 | Improved Governance and Organisational Excellence | Good Governance | Attending of conference and congresses | Conference and congresses | 100000 | 100000 | 01/07/2014 | 30/06/2015 | Adrehence to procedures and attend conference and congresses | Adrehence to procedures and attend conference and congresses | Adrehence to procedures and attend conference and congresses | Adrehence to procedures and attend conference and congresses | CORPS
46 | Improved Governance and Organisational Excellence | Skills Development/Training | To improve capacity of councillors by 30 June 2015 | Capacity building: councillors | 318600 | 550000 | 01/10/2014 | 30/06/2015 | Identification of councillors | Conduct need analysis and submit specification to SCM | Advertisement of tender and appointment of service provider | 100% councillors trained | CORPS
40 | Improved Governance and Organisational Excellence | Batho Pele | To implement Batho Pele principles by 31 March 2015 | Batho Pele strategies | 30798 | 30798 | 01/10/2014 | 12/12/2014 | n/a | n/a | Oraganise and ecelbrate Bathopele event | n/a | MM
40 | Improved Governance and Organisational Excellence | Bursary Scheme | To fund good performing student from the needy families | Bursary scheme council | R2 000 000 | R2 000 001 | 01/07/2014 | 30/06/2015 | n/a | Advertise for applications and pay costs- Payment of costs | Adjudication of all applications and payments of costs | Payment of costs | MM
54 | Improved Governance and Organisational Excellence | Humanitarian | To enhance humanitarian by 30 June 2014 | Humanitarian Aid | 100000 | 110000 | 01/07/2014 | 30/06/2015 | 25% | 50% | 75% | 100% | MM
40 | Improved Governance and Organisational Excellence | Communication | To issue 4 newsletters by 30/06/2015 | News letter | 350000 | 200000 | 01/07/2014 | 30/06/2015 | 1 | 1 | 1 | 1 | MM
40 | Improved Governance and Organisational Excellence | Communication | To purchase calenders and diaries by 30/09/2014 | Calendar and diaries | 20000 | 20000 | 01/07/2014 | 30/09/2014 | 100% | n/a | n/a | n/a | MM
40 | Improved Governance and Organisational Excellence | MM | Purchasing of Council vehicle for the Speaker by 31 March 2015 | Council Vehicle for the speaker | 700000 |  | 01/09/2014 | 31/09/2014 | Develop specifications and submit to SCM. Advertise and appointment of service providers | vehicle for the Speaker purchased | n/a | n/a | MM
40 | Improved Governance and Organisational Excellence | MM | Purchasing of two (2) gazebos by 30 September 2014 | 2 x Gazebos | 40000 | 40000 | 01/07/2014 | 30/09/2014 | Sourcing of quatations and appointment of service provider for supply , 2 Gazebos purchased | n/a | n/a | n/a | MM
40 | Improved Governance and Organisational Excellence | MM | Purchasing of a scanner by 30 September 2014 | Scanner | 5000 | 5000 | 01/07/2014 | 30/09/2014 | Sourcing of quatations and appointment of service provider for supply , Scanner purchased | n/a | n/a | n/a | MM
40 | Improved Governance and Organisational Excellence | MM | Purchasing of a Cooler box by 30 September 2014 | Cooler box | 5000 | 5000 | 01/07/2014 | 30/09/2014 | Sourcing of quatations and appointment of service provider for supply, Cooler box purchased | n/a | n/a | n/a | MM
54 | Improved Governance and Organisational Excellence | Property Services | Purchasing of 5 Aqua Coolers by 30 September 2014 | 5x Aqua coolers | 15000 | 15000 | 01/07/2014 | 30/09/2014 | Sourcing of quatations and appointment of service provider for supply, 5 Aqua Coolers purchased | n/a | n/a | n/a | CORPS
54 | Improved Governance and Organisational Excellence | Property Services | Purchasing of shredding machine for registry by 30 September 2014 | Shredding machine for registry | 8000 | 20000 | 01/07/2014 | 30/09/2014 | Sourcing of quatations and appointment of service provider for supply, Shredding machine purchased | n/a | n/a | n/a | MM
40 | Improved Governance and Organisational Excellence | Special Programmes | To facilitate youth development activities by 30 June 2015 | Youth desk activities | 280000 | 180000 | 01/07/2014 | 30/06/2015 | Develop youth desk activity program | facilitate youth development activities | facilitate youth development activities | facilitate youth development activities | MM
40 | Improved Governance and Organisational Excellence | Special Programmes | To facilitate gender desk activities by 30 June 2016 | Gender desk activities | 200000 | 250000 | 01/07/2014 | 30/06/2015 | Develop Gender desk activity program | facilitate Gender Desl activities | facilitate Gender Desl activities | facilitate Gender Desl activities | MM
54 | Improved Governance and Organisational Excellence | Special Programmes | To facilitate Disability desk activities by 30 June 2017 | Disability desk activities | 100000 | 177000 | 01/07/2014 | 30/06/2015 | Develop Disability desk activity program | facilitate Disability desk activities | facilitate Disability desk activities | facilitate Disability desk activities | MM
40 | Improved Governance and Organisational Excellence | Special Programmes | To facilitate HIV/AIDS Council activities by 30 June 2018 | HIV & AIDS Council activities | 95000 | 60000 | 01/07/2014 | 30/06/2015 | Develop HIV/AIDS Council activity program | Facilitae HIV/AIDS Council activities | Facilitae HIV/AIDS Council activities | Facilitae HIV/AIDS Council activities | MM
40 | Improved Governance and Organisational Excellence | Special Programmes | Supporting initiatives for youth empowerment | Youth empowerment projects | 200000 | 200000 | 01/07/2014 | 30/06/2015 | Support Youth empowerment | Support Youth empowerment | Support Youth empowerment | Support Youth empowerment | MM
14 | Access to Sustainable Basic Services | Libraries and Archives | Planning and designing of library for Shotong village by 30 June 2015 | Shotong Library | 300000 | 300000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Appoint service provider and designs resume | Designs Completed | Designs completed and submitted (Shotong) | INDEP / B & T
14 | Access to Sustainable Basic Services | Libraries and Archives | Planning and designing of library for Rotterdam village by 30 June 2015 | Rotterdam Library | 300000 | 300000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Appoint service provider and designs resume | Designs Completed | Develop, submit terms of reference to SCM and advertise for construction. | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Facilities | To do cemetry layout and fencing at Ga-Kgapane cemetry by 30 June 2015 | Kgapane Cemetry layout and fencing | 1500000 | 3000000 | 01/07/2014 | 30/06/2015 | Develop, submit terms of reference to SCM and advertise. | Appoint service provider | Construction resume | Construction completed | COMM
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of old age facility for Madumeleng village by 30 June 2015 | Madumeleng Old Age Facility | 220000 | 220000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Appoint service provider and designs progress at 30% | Complete designs | Develop, submit terms of reference to SCM and advertise for construction. | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of old age facility for Ga-Kgapane township by 30 June 2015 | Kgapane Old Age Facility | 220000 | 220000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Appoint service provider and designs resume | Complete designs | Develop, submit terms of reference to SCM and advertise for construction. | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of old age facility for Roerfontein village by 30 June 2015 | Roerfontein Old Age Facility | 220000 | 220000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Appoint service provider and designs resume | Complete designs | Develop, submit terms of reference to SCM and advertise for construction. | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Supply and erection of bus shelter at Mokwakwaila - Ga-Kgapane road by 31 March 2015 | Mokwakwaila to Kgapane Bus shelter | 75000 | 75000 | 01/07/2014 | 31/03/2015 | Develop and submit specifications to SCM and advertise | Appoint service provider and erection of bus shelter resume | Erection of bus shelter and complete | n/a | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Supply and erection of bus shelter at Malematsa - Rapitsi road by 31 March 2015 | Rapitsi to Malematsa Bus Shelter | 75000 | 75000 | 01/07/2014 | 31/03/2015 | Develop and submit specifications to SCM and advertise | Appoint service provider and erection of bus shelter resume | Erection of bus shelter and completed | n/a | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Supply and erection of bus shelter at Lemondokop - Mamaila road by 31 March 2015 | Lemondokop to Mamaila via Phooko Bus Shelter | 75000 | 75000 | 01/07/2014 | 31/03/2015 | Develop and submit specifications to SCM and advertise | Appoint service provider and erection of bus shelter resume | Erection of bus shelter and completed | n/a | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Supply and erection of bus shelter at Modjadji Head Kraal by 31 March 2015 | Modjadji Headkraal Bus Shelter | 75000 | 75000 | 01/07/2014 | 31/03/2015 | Develop and submit specifications to SCM and advertise | Appoint service provider and erection of bus shelter resume | Erection of bus shelter and completed | n/a | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Supply and erection of bus shelter at Goudplaats village by 31 March 2015 | Goudplaas Bus Shelter | 75000 | 75000 | 01/07/2014 | 31/03/2015 | Develop and submit specifications to SCM and advertise | Appoint service provider and erection of bus shelter resume. | Erection of bus shelter and completed | n/a | INDEP / B & T
28 | Roads & Transport | Vehicle Licencing and Test | Purchasing of twotraffic Blue lights by 30 September 2014 | Traffic Blue lights (2) | 20000 |  | 1/07/2014 | 30/09/2015 | Appointment of service provider and 2 Traffic Blue lights purchased. | n/a | n/a | n/a | COMM
28 | Roads & Transport | Vehicle Licencing and Test | Construction Of Testing room for learners Licences by 31 March 2015 | Testing room for learners Licence | 300000 |  | 01/07/2014 | 31/03/2015 | Submission of specifications and advertisement for service providers | Appoint service providers and construction resume | Constructio completed | n/a | COMM
28 | Roads & Transport | Vehicle Licencing and Test | Purchasing of Traffic Sedan by 12 December 2014 | Traffic Sedan | 350000 |  | 01/07/2014 | 12/12/2014 | Submission of specifications and advertisement for service providers | Appoint service provider and purchase of Traffic Sedan | n/a | n/a | COMM

## APPROVAL
2015/16 SERVICE DELIVERY BUDGET IMPLEMENTATION PLAN
Approval by the Mayor | The approval of the SDBIP is the competency of the Municipal Manager and the Mayor. The SDBIP is a management and monitoring tool for the implementation of the IDP and Budget that must be tabled to council for noting. Any adjustment that can be made on the SDBIP must be taken to Council for noting.
Monitoring the Implementation of the SDBIP | Progress against the objectives set out in the SDBIP will be monitored and reported on a monthly, quarterly and annual basis as per the Approved PMS Policy and Framework.
Signatures | SDBIP Compiled By: ----------------------------------- ----------------------------- Mrs TG Mashaba DATE Municipal Manager Greater-Letaba Muncipality SDBIP Approved By: -------------------------------------- ----------------------------- CLLR GH Modjadji DATE Mayor Greater-Letaba Muncipality