## COVER
GREATER LETABA MUNICIPALITY
SERVICE DELIVERY AND BUDGET
IMPLEMENTATION PLAN
1st Quarter Report 2014/2015

## INDEX
Table of Contents
Introduction | 3
Legislation | 3
Methodology and Contents | 4
Strategic Vision, Mission and Strategy Map | 5
Votes and Operational Objectives | 6
Municipal Transformation and Organisational Development KPI's | 7 to 11
Municipal Transformation and Organisational Development Projects | 12 to 14
Basic Service Delivery Projects | 15 to 25
Local Economic Development Projects | 26 to 29
Municipal Financial Viability KPI's | 30 to 30
Municipal Financial Viability Projects | 31 to 32
Good Governance and Public Participation KPI's | 33 to 34
Good Governance and Public Participation Projects | 35 to 37

## INTR AND LEGISLATION
Introduction | The development, implementation and monitoring of a Service Delivery and Budget Implementation Plan (SDBIP) is required by the Municipal Finance Management Act (MFMA). In terms of Circular 13 of National Treasury, “the SDBIP gives effect to the Integrated Development Plan (IDP) and budget of the municipality and will be possible if the IDP and budget are fully aligned with each other, as required by the MFMA.” As the budget gives effect to the strategic priorities of the municipality it is important to supplement the budget and the IDP with a management and implementation plan. The SDBIP serves as the commitment by the Municipality, which includes the administration, council and community, whereby the intended objectives and projected achievements are expressed in order to ensure that desired outcomes over the long term are achieved and these are implemented by the administration over the next twelve months.
The SDBIP provides the basis for measuring performance in service delivery against quarterly targets and implementing the budget based on monthly projections. Circular 13 further suggests that “the SDBIP provides the vital link between the mayor, council (executive) and the administration, and facilitates the process for holding management accountable for its performance. The SDBIP is a management, implementation and monitoring tool that will assist the mayor, councillors, municipal manager, senior managers and community.” The purpose of the SDBIP is to monitor the execution of the budget, performance of senior management and achievement of the strategic objectives set by council. It enables the municipal manager to monitor the performance of senior managers, the mayor to monitor the performance of the municipal manager, and for the community to monitor the performance of the municipality.
In the interests of good governance and better accountability, the SDBIP should therefore determine and be aligned with the performance agreements of the municipal manager and senior managers. The development, implementation and monitoring of a Service Delivery and Budget Implementation Plan (SDBIP) is required by the Municipal Finance Management Act (MFMA). In terms of Circular 13 of National Treasury, “the SDBIP gives effect to the Integrated Development Plan (IDP) and budget of the municipality and will be possible if the IDP and budget are fully aligned with each other, as required by the MFMA.”
Legislation | According to the Municipal Finance Act (MFMA) the definition of a SDBIP is: 'service delivery and budget implementation plan' means a detailed plan approved by the mayor of a municipality in terms of section 53 (1) (c) (ii) for implementing the municipality's delivery of municipal services and its annual budget, and which must indicate- (a) projections for each month; (i) revenue to be collected by source; (ii) operational and capital expenditure by vote; (b) service delivery targets and performance indicators for each quarter. Section 53 of the MFMA stipulates that the Mayor should approve the SDBIP within 28 days after the approval of the budget. The Mayor must also ensure that the revenue and expenditure projections for each month and the service delivery targets and performance indicators as set out in the SDBIP are made public within 14 days after their approval.
The following National Treasury prescriptions as minimum requirements that must form part of the SDBIP are applicable to the Municipality : (1) Monthly projections of revenue to be collected by source. (2) Monthly projections of expenditure (operating and capital) and revenue for each vote. (3) Quarterly projections of service delivery targets and performance indicators for each vote. (4) Ward information for expenditure and service delivery. (5) Detailed capital works plan broken down per ward for three years. * Section 1 of the MFMA defines a “vote” as: a) One of the main segments into which a budget of a municipality is divided for the appropriation of money for the different departments or functional areas of the municipality; and b) which specifies the total amount that is appropriated for the purposes of the department or functional area concerned.

## METHODOLOGY AND CONTENT
Methodology and Content | National Treasury directives are clear on the contents and methodology to derive at the SDBIP. As a first step, the IDP objectives need to be quantified and related into key performance indicators. The budget is aligned to the objectives, projects and activities to enable the SDBIP to serve as monitoring tool for service delivery. The SDBIP is described as a layered plan. The top layer deals with consolidated service delivery targets and time frames. Top Management is held accountable for the implementation of the consolidated projects and Key Performance Indicators. From the consolidated information, top management is expected to develop the next level of detail by breaking up outputs into smaller outputs and then linking and assigning responsibility to middle-level and junior managers.
The SDBIP of the Greater Letaba Municipality consists of strategic objectives derived from the IDP that are aligned with the strategic intent of the organisation. Strategic indicators with targets are set to measure the objectives. The Municipal Manager takes responsibility for the strategic indicators and objectives which will form part of his/her Performance Agreement and Plan. Projects and activities are aligned to the indicators with quarterly targets, time-frame and budget assigned to each. The Strategic Indicators give rise to the institutional indicators for which the Directors will take responsibility. These indicators will form part of the Performance Agreements and Plans of Senior Managers (Directors). Indicators are assigned quarterly targets and responsibilities to monitor performance. Derived from this, the next layer is developed, whereby the details with responsibilities for the next level of management is outlined and forms part of the Lower SDBIP. This lower SDBIP is a management tool for the S57 Managers and need not be made public and is a separate document for each internal department. The SDBIP serves as a management, implementation and monitoring tool that will assist the Mayor, Councilors, Municipal Manager and Directors in delivering services to the community

## STRATEGY
Vision and Mission | The strategic vision of the organisation sets the long term goal the Municipality wants to achieve. The vision of Greater Letaba Municipality is: "To be an outstanding agro-processing and eco-cultural tourism hub". The strategic mission speaks about what the purpose of Greater Letaba Municipality is: The mission of Greater Letaba Municipality is to ensure an effective, efficient and economically viable municipality through: Provision of accountable, transparent, consultative and co-operative governance. Improving the quality of life through economic development and poverty alleviation. Provision of sustainable services. Ensuring a safe and healthy environment.
Strategy map | The Strategy Map depicts the strategic objectives on how Greater Letaba Municipality will be able to become an outstanding agro-processing and eco-cultural tourism hub while providing sustainable and affordable services to all. These objectives were positioned in terms of the Balanced Scorecard Perspectives being: Learning and Growth; Institutional Processes; Financial results and Community Satisfaction. All operational outputs (projects, initiatives and process) as contained within the SDBIP are aligned to the attainment of one or more of these objectives.

## OPERATIONAL STRATEGIES
Votes and Operational objectives | Votes | Objectives and Targets
| Municipal Manager Office (Vote 040) | To lead, direct and manage a motivated and inspired administration and account to the Greater Letaba Municipal Council as Accounting Officer for long term municipal sustainability to achieve a good creditor rating within the requirements of the relevant legislation and whereas the following sections within the department, i.e. HIV/Aids, Youth, Disabled and Gender Desk, Communication and Internal Auditing is managed for integration, economic growth, marginalised poverty alleviation, efficient, economic and effective communication and service delivery.
| Finance (Vote 050) | To secure a sound and sustainable management of the financial affairs of Greater Letaba Municipality by managing the budget and treasury office and advising and if necessary assisting the Accounting Officer and the Directors in their duties and delegation contained in the MFMA. Ensuring that the Greater Letaba Municipality is 100% financially viable when it comes to cost coverage and to manage the grant revenue of the municipality so that no grant funding is foregone
| Community Services (Vote 028) | To co-ordinate Environmental Health Services, Sports Arts and Culture, Education, Libraries, Safety and Security, Environmental and Waste management, Health and Social development programmes as well as Disaster management to decrease community affected by disasters
| Infrastructure Development and Economic Planning (Votes 029 and 022) | To ensure that the service delivery requirements for roads are met and maintenance of water, sewerage and electricity are conducted for access to basic services as well as no less than an average of 100% MIG expenditure
To direct the Greater Letaba Municipality’s resources for advanced economic development and investment growth through appropriate town and infrastructure planning in order that an environment is created whereby all residents will have a sustainable income.
| Corporate Services (Vote 046 ) | To ensure efficient and effective operation of council services, human resources and management, legal services and the provision of high quality customer orientated administrative systems. Ensuring 100% compliance to the Skills Development Plan.

## MTOD KPI's
KPA 1 MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT
KEY PERFORMANCE INDICATORS
OUTCOME NINE (OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING, PLANNING AND SUPPORT, OUTPUT 4: ACTIONS SUPPORTIVE OF THE HUMAN SETTLEMENT OUTCOMES)
Vote Nr | Strategic Objective | Programmes | Measurable Objectives | Performance measures | Baseline / Status | Budget 2014/2015 | 1st Quarter target | Progress to date | Challenges | Intervention strategies | Expenditure | Project Owner
50 | Improved Quality of Life | Indigent Management | To ensure that all indigent applicants are registered in the indigent register within 14 days of receipt. | % of Indigent applications registered (# of applications received/# of indigent applicantions processed) | 1725 | Operational | 450 | 100% (521/521) | The existing customers are not collecting indigent support | Conduct awareness campaigns in all wards | 0 | CFO
22 | Integrated Sustainable Development | IDP | To ensure that draft IDP, Budget and SDBIP are adopted by 31 March 2015. | Draft IDP, budget and PMS adopted by 31 March 2015 | Adopted by 31 March 2015 | Operational | N/A | N/A | N/A | N/A | 0 | INDEP/CFO/MM
22 | Integrated Sustainable Development | IDP | To develop and implement IDP process plan by 30 June 2015. | IDP process plan adopted and implemented by 30 June 2015. | Adopted by 31 May 2015 | Operational | N/A | N/A | N/A | N/A | 0 | INDEP/CFO/MM
22 | Integrated Sustainable Development | IDP | To review, drive and monitor implementation of the IDP by 31 May 2015 | % achievement of milestones on IDP/Budget/PMS process plan. | 100% | Operational | 25% | 20% | Behind IDP/Budget process plan | Develop special catch-up plan | 0 | INDEP/MM
22 | Integrated and Sustainable Human Settlement | Spatial Planning | To submit housing demand database to COGHSTA by the 12 December 2014 | House demand database submitted by 12 December 2014 | Database submitted to COGHSTA by the 12 December 2014 | Operational | N/A | N/A | N/A | N/A | 0 | INDEP
22 | Integrated and Sustainable Human Settlement | Spatial Planning | To ensure that land use applications are processed within 90 days of receipt. | % of land use applications processed (# of applications received / # of land use applications processed) within 90 days of receipt | 100% | Operational | 100% | 100% | Most of the plans were not processed due to outstanding debts | The applicants to pay outstanding debts | 0 | INDEP
22 | Integrated and Sustainable Human Settlement | Annual Report | To compile the Draft Annual Report and submit to council by 12 December 2014 | Draft Annual Report adopted by Council on 12 December 2014 | Draft Annual Report adopted by Council on 12 December 2014 | Operational | N/A | N/A | N/A | N/A | 0 | MM/ All Directors
33 | Improved Governance and Organisational Excellence | Annual Report | To compile the Final Annual Report and submit to council by 31 January 2015 | Final Annual Report approved by council on 31 January 2015 | Final Annual Report approved by council on 31 January 2015 | Operational | N/A | N/A | N/A | N/A | 0 | MM / All Directors
33 | Improved Governance and Organisational Excellence | SDBIP | To ensure that SDBIP is finalised by 30 June 2015. | SDBIP approved by Mayor 28 days after adoption of the final Budget and IDP. | SDBIP approved by Mayor 28 days after adoption of Budget and IDP | Operational | N/A | N/A | N/A | N/A | 0 | PMS/MM
54 | Improved Governance and Organisational Excellence | OPMS | To ensure annual implementation of the performance management system in the organisation | # of Quarterly performance reports submitted to Council. | 4 | Operational | 1 | 1 Quarterly performance report submitted to Council | None | None | 0 | PMS/MM
54 | Improved Governance and Organisational Excellence | EPMS | To ensure that S57 Managers sign the performance agreements within 30 days after adoption of the final SDBIP. | # of S57 Managers with signed performance agreements within 30 days after adoption of the final SDBIP | 3 | Operational | 5 | 4 performance agreements signed within 30 days after adoption of the final SDBIP | 1 S57 post vacant (Director: Corporate Services) | To fill the post | 0 | MM
54 | Improved Governance and Organisational Excellence | EPMS | To ensure that annual assessments of S57 Managers is conducted within 30 days after the end of the fiancial year. | # of annual performance assessments conducted within 30 days after the end of the financial year. | 1 | Operational | 1 | 1 Annual performance asessment conducted within 30 days after the end of the financial year | None | None | 0 | PMS/MM
54 | Improved Governance and Organisational Excellence | EPMS | To ensure quartely assessments for S57 Managers is conducted within 30 days after the end of the quarter. | # of quarterly performance assessments conducted within 30 days after the end of the quarter. | 1 | Operational | N/A | N/A | N/A | N/A | 0 | PMS/MM
54 | Improved Governance and Organisational Excellence | Internal Audit | To ensure functionality of Audit committee within the financial year. | # of meetings held per quarter. | 4 | Operational | 1 | 1 x ordinary meeting 2 x special meeting (Audit Coommittee & AG) | None | None | 0 | Internal Audit /MM
54 | Improved Governance and Organisational Excellence | Risk | To ensure functionality of Risk committee within the financial year. | # of meetings held per quarter. | 4 | Operational | 1 | No Risk Committee meeting was held | Meeting not held because of other Municipal activities | Adhere to Risk Committee schedule | 0 | Risk/MM
54 | Improved Governance and Organisational Excellence | CORPS | To ensure functionality of Council committee within the financial year. | # of meetings held per quarter. | 4 | Operational | 1 | 1 ordinary Council 1 special Council meeting held | N/A | N/A | 0 | CORPS/MM
| Improved Governance and Organisational Excellence | CORPS | To ensure functionality of Exco committee within the financial year. | # of meetings held per quarter. | 4 | Operational | 1 | 1 ordinary Exco 1 special Exco meeting held | N/A | N/A | 0 | CORPS/MM
54 | Improved Governance and Organisational Excellence | Internal Audit | To conduct quarterly assessment on municipal performance information. | # of performance audit reports issued per quarter. | 4 | Operational | 1 | No performance audit report issued. 2 draft reports prepared but not yet issued. | None | None | 0 | Internal Audit
54 | Improved Governance and Organisational Excellence | Internal Audit | To develop annual year internal audit plan and implement by 30 June 2015. | Approved internal audit plan and % of the IA plan implementation. | 50% | Operational | 25% | No implementation. | Internal Audit Plan not approved | Finalisation of Risk Register | 0 | MM
54 | Improved Governance and Organisational Excellence | Operation clean audit | To attain Clean Audit by ensuring compliance to all governance; financial management and reporting requirements by 12 December 2014 | % of internal audit issues resolved (# of Internal Audit issues resolved / # of issues raised) | 12% | Operational | 50% | 7% (4 IA issues resolved / 30 issues reaised) | No implementation of IA queries | Place implementation of IA findings on the Performance Agreement of Directors. | 0 | All Directors/MM
54 | Improved Governance and Organisational Excellence | Operation clean audit | To attain Clean Audit by ensuring compliance to all governance; financial management and reporting requirements by 30 June 2015 | % of AG issues resolved (# of Auditor General issues resolved / # of issues raised) | 78% | Operational | N/A | N/A | N/A | N/A | 0 | All Directors/MM
54 | Improved Governance and Organisational Excellence | Risk management | To ensure efffective implementation of risk mitigations actions 30 June 2015. | % of Risk issues resolved (# Risk issues implemented / resolved / # of risks identified) | 100% | Operational | 25% | 0% (9 Risk issues raised/ 9 not resolved). . | Slow implementation of mitigation actions. | Management have developed mitigation actions to address the risks identified | 0 | Risk/MM

## MTOD PROJECTS
KPA 1 MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT PROJECTS
OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING, PLANNING AND SUPPORT, OUTPUT 4: ACTIONS SUPPORTIVE OF THE HUMAN SETTLEMENT OUTCOMES
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project / Initiative | Budget 2014/2015 | Start Date | Completion Date | Milestones Qtr Ending Sept 2014 | Progress to date | Challenges | Intervention strategies | Expenditure | Project Owner
46 | Improved Governance and Organisational Excellence | Risk Management | To organise 4 OHS risk assessment workshop by 30 June 2015 | Risk assessment: OHS | 9000 | 01/07/2014 | 30/06/2015 | 1 | 1 OHS Risk assessment workshop conducted. | None | None | 0 | MM
46 | Improved Governance and Organisational Excellence | OHS | To organise 4 Health and Safety awareness events 30 June 2015 | Health and safety awareness event | 40000 | 01/07/2014 | 30/06/2015 | 1 Health and Safety awareness events | 1 Health and Safety awareness events | none | none | 0 | CORPS
46 | Improved Governance and Organisational Excellence | OHS | To purchase OHS signs and posters by 30 September 2014 | OHS signs and posters | 12000 | 01/07/2014 | 30/09/2014 | Develop specification, submit to SCM, purchase and paste OHS sign posters | Specification submitted. OHS Posters not purchased | Wrong budgeting. Budgeted in operational instead of capital budget. | To be considered during budget adjustment | 0 | CORPS & CFO
46 | Improved Governance and Organisational Excellence | Furniture & Equipment | To purchase office signs and posters by 30 September 2014 | Four (4)signs and posters | 2000 | 01/07/2014 | 30/09/2014 | Develop specification, submit to SCM, purchase office signs and posters | Specification submitted. OHS Posters not purchased | Wrong budgeting. Budgeted in operational instead of capital budget. | To be considered during budget adjustment | 0 | CORPS & CFO
46 | Improved Governance and Organisational Excellence | OHS | To purchase First aid kit by 30 September 2014 | First Aid content | 5000 | 01/07/2014 | 30/09/2014 | Develop specification, submit to SCM, purchase first aid kit | Specification not submitted to SCM. First aid kit not purchased. | Delay in compiling specification. | To be procured by the end of December 2014. | 0 | CORPS & CFO
46 | Improved Governance and Organisational Excellence | Human Resources | To organise EWP day by 12 December 2014 | Employee wellness programme | 40000 | 01/10/2014 | 12/12/2014 | N/A | N/A | N/A | N/A | 0 | CORPS
54 | Improved Governance and Organisational Excellence | Property Services | Purchasing of a scanner by 30 September 2014 | Scanner | 5000 | 01/07/2014 | 30/09/2014 | Develop specification, submit to SCM, purchase scanner | Specifications developed and submitted to SCM. Scanner not purchased | Delay in specification processes | To purchase by the end December 2014 | 0 | CORPS
46 | Improved Governance and Organisational Excellence | Property Services | To develop and implement skills Developemnt programmes by 30 June 2015 | Skills development levy | 300000 | 01/07/2014 | 30/06/2015 | N/A | N/A | N/A | N/A | 0 | CORPS
46 | Improved Governance and Organisational Excellence | Human Resources | To award long service award to eligible employees timeously according to policy | Long service award | 169920 | 01/07/2014 | 30/06/2015 | 100% of the qualifying employees | 100% of the qualifying employees awarded long service award | N/A | N/A | 0 | CORPS
46 | Improved Governance and Organisational Excellence | IT | To rent network printer by 12 December 2014 | Rental of the network printer | 1101597 | 01/07/2014 | 12/12/2014 | Submit specifications to to SCM and advertise | Specifications developed and submitted to SCM. | Delay in specification processes | To purchase by the end December 2014 | 0 | CORPS
46 | Improved Governance and Organisational Excellence | IT | To network all GLM sub offices by 31 March 2015 | Networking of the sub-offices | 264000 | 01/07/2014 | 31/03/2015 | Submit specifications to to SCM and advertise | Specifications developed and submitted to SCM. | Delay in specification processes | To purchase by the end December 2014 | 0 | CORPS
39 | Improved Governance and Organisational Excellence | IT | Develop maintenance Plan for all IT Systems by 30 September 2014 | Maintenance Plan for all IT Systems | 10560 | 01/07/2014 | 30/09/2014 | Submit specifications to to SCM and advertise | Specifications not submitted | Under budgeting | To be considered during budget adjustment | 0 | CORPS
46 | Improved Governance and Organisational Excellence | IT | To purchase 4 Printers: Senwamokgope, Mokwakwaila, Kgapane and main office by 30 September 2014 | 4 Printers: Senwamokgope, Mokwakwaila, Kgapane and main office | 100000 | 01/07/2014 | 30/09/2014 | Develop specification, submit to SCM and purchase printers | Specifications developed and submitted to SCM. Printers not purchased. | Delay in specification processes | To purchase by the end December 2014 | 0 | CORPS & CFO
46 | Improved Governance and Organisational Excellence | Human Resources | Procument of 6 steel cabinets: Finance by 30 September 2014 | 6 x Steel Filling Cabinet: Finance | 30000 | 01/07/2014 | 30/09/2014 | Develop specification, submit to SCM and purchase steel filling cabinets | Specifications not submitted | Delay in the development of specification | To submit before end October 2014 | 0 | CORPS
46 | Improved Governance and Organisational Excellence | Human Resources | To purchase Office furniture by 12 December 2014 | Office furniture | 175000 | 01/07/2014 | 12/12/2014 | Develop specification, submit to SCM and advertise | Specifications developed and submitted to SCM. Not advertised | Delay in specification processes | To purchase by the end December 2014 | 0 | CORPS & CFO
46 | Improved Governance and Organisational Excellence | IT | To purchase Servers by 12 December 2014 | Servers | 100000 | 01/07/2014 | 12/12/2014 | Request quatations for procurement, appoint service provider, supply and installation of servers | Specifications developed and submitted to SCM. Servers not purchased | Delay in specification processes | To purchase by the end December 2014 | 0 | CORPS & CFO
46 | Improved Governance and Organisational Excellence | IT | To purchase Server room door by 12 December 2014 | Server room door | 50000 | 01/07/2014 | 12/12/2015 | Request quatations for procurement, appoint service provider, supply and installation of server room door | Specification not submitted. | Capacity | To request assistance from sevice providers | 0 | CORPS & CFO
46 | Improved Governance and Organisational Excellence | IT | To purchase 10 laptops by 30 September 2014 | 10 Laptops | 100000 | 01/07/2014 | 30/09/2014 | Develop specifications,submit to SCM and purchase laptops. | Specifications developed and submitted to SCM. Laptops not purchased. | Delay in specification processes | To purchase by the end December 2014 | 0 | CORPS & CFO
46 | Improved Governance and Organisational Excellence | IT | To develop and implement disaster recovery plan by 31 March 2015 | Disaster Recovery Plan and UPS | 300000 | 01/10/2014 | 31/03/2015 | Develop specification, submit to SCM and advertise | UPS Specifications developed and submitted to SCM. | Delay in specification processes | To purchase by the end December 2014 | 0 | CORPS & CFO
54 | Improved Governance and Organisational Excellence | Property Services | To purchase shelves for filling by 30 September 2014 | Shelves for filling | 30000 | 01/07/2014 | 30/09/2014 | Develop specification, submit to SCM and purchase | Specification not submitted. | Office space | To rellocate IT unit to another office | 0 | CORPS
54 | Improved Governance and Organisational Excellence | Property Services | Construction of parking area for 36 vehicles at main office by 31 March 2015 | Parking at Municipal Offices | 1000000 | 01/07/2014 | 31/03/2015 | Develop specifications, submit to SCM and advertise | Tender advertised | none | none | 0 | INDEP / B & T

## BSD PROJECTS
KPA 2 BASIC SERVICE DELIVERY AND INFRASTRUCTURE KEY PERFORMANCE INDICATORSPROJECTS OUTCOME NINE (OUTPUT 2: IMPROVING ACCESS TO BASIC SERVICES, OUTPUT 3: IMPLEMENTATION OF THE COMMUNITY WORK PROGRAMME)
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project / Initiative | Budget 2014/2015 | Start Date | Completion Date | Milestones Qtr Ending Sept 14 | Progress to date | Challenges | Intervention strategies |  | Project Owner
Expenditure
62 | Access to Sustainable Basic Services | Stormwater | Construction of pedestrian bridge at Ga-Kgapane (William Kgatla) by 31 March 2015 | Pedestrian William Kgatle Bridge | 150000 | 01/07/2014 | 31/03/2015 | Submit specifications to SCM for advertisement | Specifications submitted to SCM for advertisement. | None | None | 0 | INDEP / B & T
62 | Access to Sustainable Basic Services | Stormwater | Design and construction of low level bridges by 31 March 2015 | Low Level Bridges | 1500000 | 01/07/2014 | 31/03/2015 | Submit specifications to SCM and advertise | Specifications submitted to SCM. Tender not advertised. | Project not yet advertised | To be advertised in November 2014 | 0 | INDEP / B & T
62 | Access to Sustainable Basic Services | Stormwater | Design and construction of stormwater management channels in Modjadjiskloof by 31 March 2015 | Modjadjiskloof- Channels | 2000000 | 01/07/2014 | 31/03/2015 | Develop and submit terms of reference to SCM and advertise | Terms of reference submitted to SCM. Tender advertised. | None | None | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Purchasing of two TLB (Backhoe Loader) by 12 December 2014 | TLB (Backhoe Loader) | 1500000 | 01/07/2014 | 12/12/2014 | Develop, submit specifications to SCM and advertise | Terms of reference submitted to SCM. Tender advertised. | None | None | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Purchasing of a 2 tonner truck with quarter canopy for roads maintenance team by 12 December 2014 | 2 Tonner Truck with Quarter Canopy | 300000 | 01/07/2014 | 12/12/2014 | Develop, submit specifications to SCM and advertise | Specifications not developed and not submitted to SCM. Tender not advertised. | Delay in development of specifications. | To submit before end of October 2014. | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Purchasing of a plate compactor by 30 September 2014 | Plate compactor | 35000 | 01/07/2014 | 30/09/2014 | Develop, submit specifications to SCM and purchase | Specification developed and submitted to SCM. Quotations obtained. Plate Compactor not purchased. | Project not yet advertised | To be advertised in November 2014 | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Supply and installation of gabions for Sekgopo by 31 March 2015 | Gabions - Sekgopo | 1200000 | 01/07/2014 | 31/03/2015 | Develop and submit specifications to SCM and advertise | Specifications developed and submitted to SCM. Tender not advertised. | Project not yet advertised | To be advertised in November 2014 | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Upgrading of gravel to concrete paving blocks for 1.8 km at Mothobeki village by 31 March 2015 | Mothobeki Paving | 6500000 | 01/07/2014 | 31/03/2015 | Advertise for contractors | Tender not advertised for contractors | Designs are incomplete | Designs to be complete before end of November 2014. Advertise for contractors. | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Upgrading of gravel to concrete paving blocks for 1.8 km at Mamaila Phaphadi village by 31 March 2015 | Mamaila Phaphadi Paving | 6500000 | 01/07/2014 | 31/03/2015 | Advertise for contractors | Tender not advertised for contractors | Designs are incomplete | Designs to be complete before end of November 2014. Advertise for contractors. | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Upgrading of gravel to concrete paving blocks for 1.8 km at Phooko village by 31 March 2015 | Phooko Head Kraal Paving | 3200000 | 01/07/2014 | 31/03/2015 | Advertise for contractors | Tender not advertised for contractors | Designs are incomplete | Designs to be complete before end of November 2014. Advertise for contractors. | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Upgrading of gravel to concrete paving blocks for 1.8 km at Raphahlelo village by 31 March 2015 | Raphahlelo Head Kraal Paving | 6550000 | 01/07/2014 | 31/03/2015 | Advertise for contractors. | Tender not advertised for contractors. | Designs are incomplete. | Designs to be complete before end of November 2014. Advertise for contractors. | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Purchasing of 2 tipper trucks by 12 December 2014 | Tipper truck | 1380000 | 01/07/2014 | 12/12/2014 | Develop, submit specifications to SCM and advertise. | Specification developed and submitted to SCM. Tender advertised. | None | None | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Rehabilitation of 3 km of streets in Modjadjiskloof by 31 March 2015 | Rehabilitation of Modjadjiskloof Streets | 5500000 | 01/07/2014 | 31/03/2015 | Develop, submit specifications to SCM and advertise | Specifications developed and submitted to SCM. Tender not advertised. | Project not yet advertised | To be advertised in November 2014 | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Rehabilitation of 3 km of streets in Ga-Kgapane by 31 March 2015 | Rehabilitation of Ga-Kgapane Streets | 5500000 | 01/07/2014 | 31/03/2015 | Develop, submit specifications to SCM and advertise | Specifications developed and submitted to SCM. Tender not advertised. | Project not yet advertised | To be advertised in November 2014 | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Purchasing of quick cut machine by 30 September 2014 | Quick cut machine | 28000 | 01/07/2014 | 30/09/2014 | Develop, submit specifications to SCM and purchase | Specifications developed and submitted to SCM. Quotations obtained. Quick cut machine not purchased. | Project not yet advertised | To be advertised in November 2014 | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Construction of 3.5 km of sidewalks in Modjadjiskloof by 31 March 2015 | Modjadjiskloof Sidewalks | 3000000 | 01/07/2014 | 31/03/2015 | Develop, submit specifications to SCM and advertise | Specifications developed and submitted to SCM. Tender not advertised. | Project not yet advertised | To be advertised in November 2014 | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Construction of access road to Mokwakwaila Taxi Rank for 600m by 31 March 2015 | Access Road to Mokwakwaila Taxi Rank- Roll over | 3100000 | 01/07/2014 | 31/03/2015 | Advertise for contractors | Tender not advertised for contractors. | Designs are incomplete. | Designs to be complete before end of November 2014. Advertise for contractors. | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Planning and designing of street paving at Itieleng (Sekgosese) by 30 June 2015 | Itieleng- Sekgosese Street Paving | 450000 | 01/07/2014 | 30/06/2015 | Develop, submit terms of reference to SCM and advertise | Terms of reference developed and submitted to SCM. Tender advertised. | None | None | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Planning and designing of street paving at Lemondokop by 30 June 2015 | Lemondokop Street Paving | 450000 | 01/07/2014 | 30/06/2015 | Develop, submit terms of reference to SCM and advertise | Terms of reference developed and submitted to SCM. Tender advertised. | None | None | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Planning and designing of street paving at Refilwe village by 30 June 2015 | Refilwe Street Paving | 450000 | 01/07/2014 | 30/06/2015 | Develop, submit terms of reference to SCM and advertise | Terms of reference developed and submitted to SCM. Tender advertised. | None | None | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Planning and designing of street paving at Mamakata-Raselaka by 30 June 2015 | Mmamakata Raselaka Street Paving | 450000 | 01/07/2014 | 30/06/2015 | Develop, submit terms of reference to SCM and advertise | Terms of reference developed and submitted to SCM. Tender advertised. | None | None | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Planning and designing of Ivory-route street paving at Modjadji by 30 June 2015 | Modjadji Ivory -route Street Paving | 7000000 | 01/07/2014 | 30/06/2015 | Develop, submit terms of reference to SCM and advertise | Terms of reference developed and submitted to SCM. Tender advertised. | None | None | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Planning and designing of taxi rank at Khosotupa by 30 June 2015 | Khosutupa Taxi Rank | 220000 | 01/07/2014 | 30/06/2015 | Develop, submit terms of reference to SCM and advertise | Terms of reference developed and submitted to SCM. Tender advertised. | None | None | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Planning and designing of taxi rank at Wholesale by 30 June 2015 | Wholesale Taxi Rank | 220000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Terms of reference developed and submitted to SCM. Tender advertised. | None | None | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Planning and designing of taxi rank at Mamphakati by 30 June 2015 | Mamphakati Taxi Rank | 220000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Terms of reference developed and submitted to SCM. Tender advertised. | None | None | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of gravel to concrete paving blocks for 3 km at Ga-Kgapane by 31 March 2015 | Ga-Kgapane Street Upgrading | 8965000 | 01/07/2014 | 31/03/2015 | Advertise for contractors | Tender not advertised for contractors. | Designs are incomplete. | Designs to be complete before end of November 2014. Advertise for contractors. | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of gravel to concrete paving blocks for 1.8 km at Senwamokgope by 31 March 2015 | Senwamokgope Street Upgrading | 5400000 | 01/07/2014 | 30/03/2015 | Advertise for contractors | Tender not advertised for contractors. | Designs are incomplete. | Designs to be complete before end of November 2014. Advertise for contractors. | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of gravel to concrete paving blocks at Thakgalane by 30 September 2014 | Upgrading of streets - Thakgalane | 1500000 | 01/07/2014 | 30/09/2014 | Complete construction | Construction is at 75% complete. | Slow construction progress. | Put the Contractor on terms. | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of gravel to concrete paving blocks for 1.2 km at Kuranta by 31 March 2015 | Upgrading of streets -Kuranta | 3600000 | 01/07/2014 | 31/03/2015 | Complete designs, advertise and appoint contractors | Designs incomplete. Tender not advertised. Contractors not appointed. | Late appointment of consultants | Designs to be complete before end of November 2014. | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of gravel to concrete paving blocks for 2 km at Mokgoba by 31 March 2015 | Upgrading of streets -Mokgoba | 5950000 | 01/07/2014 | 31/03/2015 | Complete designs, advertise and appoint contractors | Designs incomplete. Tender not advertised. Contractors not appointed. | Late appointment of consultants | Designs to be complete before end of November 2014 | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of gravel to concrete paving blocks for 2 km at Modjadji Valley by 31 March 2015 | Upgrading of streets -Modjadji Valley | 5950000 | 01/07/2014 | 31/03/2015 | Complete designs, advertise and appoint contractors | Designs incomplete. Tender not advertised. Contractors not appointed. | Late appointment of consultants | Designs to be complete before end of November 2014 | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of gravel to concrete paving blocks for 2 km at Mandela park by 30 September 2014 | Mandela Park road | 2000000 | 01/07/2014 | 30/09/2014 | Complete construction | Construction is at 98% complete. | Delayed construction progress. | Follow up to hasten completion. | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of gravel to concrete paving blocks for 2 km at Modjadji Head Kraal by 30 September 2014 | Modjadji Head Kraal road | 1000000 | 01/07/2014 | 30/09/2014 | Complete construction | Construction is at 95% complete. | Delayed construction progress. | Follow up to hasten completion. | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of gravel to concrete paving blocks for 1.8 km at Ratjeke by 31 March 2015 | Ratjeke Street Paving | 5600000 | 01/07/2014 | 31/03/2015 | Advertise and appoint contractors | Designs incomplete. Tender not advertised. Contractors not appointed. | Late appointment of consultants | Designs to be complete before end of November 2014 | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of street paving at Seatlaleng village by 30 June 2015 | Seatlaleng Street Paving | 400000 | 01/07/2014 | 30/06/2015 | Develop, submit terms of reference to SCM and advertise. | Terms of reference developed and submitted to SCM.Tender advertised | None | None | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of street paving at Mohlakong village by 30 June 2015 | Mohlakong Street paving | 400000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Terms of reference developed and submitted to SCM.Tender advertised | None | None | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of street paving at Sephukubje village by 30 June 2015 | Sephukhubje Street Paving | 400000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Terms of reference developed and submitted to SCM.Tender advertised | None | None | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of street paving at Matshelapata village by 30 June 2015 | Matshelapata Street Paving | 400000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Terms of reference developed and submitted to SCM.Tender advertised | None | None | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of street paving at Shawela village by 30 June 2015 | Shawela Street Paving | 400000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Terms of reference developed and submitted to SCM.Tender advertised | None | None | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of street paving at Sekgop (Maboying) village by 30 June 2015 | Sekgopo Maboying Street Paving | 400000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Terms of reference developed and submitted to SCM.Tender advertised | None | None | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of street paving at Tlhotlhokwe village by 30 June 2015 | Tlhotlhokwe Street Paving | 400000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Terms of reference developed and submitted to SCM.Tender advertised | None | None | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of street paving at Shamfana village by 30 June 2015 | Shamfana Street Paving | 400000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Terms of reference developed and submitted to SCM.Tender advertised | None | None | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of street paving at Kherobene village by 30 June 2015 | Kherobeng Street Paving | 400000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Terms of reference developed and submitted to SCM.Tender advertised | None | None | 0 | INDEP / B & T
34 | Access to Sustainable Basic Services | Contribution from MIG | Construction of Sport complex at Shaamiriri Village by 12 December 2014. | Shaamiriri Sport Complex | 1700000 | 01/07/2014 | 12/12/2014 | Construction at 85% | Construction progress at 95% complete | None | None | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Construction of library at Senwamokgope township by 31 March 2015 | Senwamokgope library | 2100000 | 01/07/2014 | 31/03/2015 | Complete designs and advertise for contractors | Designs incomplete. Tender not advertised. Contractors not appointed. | Late appointment of consultants | Designs to be complete before end of November 2014 | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Construction of library at Sekgopo by 31 March 2015 | Sekgopo library | 2100000 | 01/07/2014 | 31/03/2015 | Complete designs and advertise for contractors | Designs incomplete. Tender not advertised. Contractors not appointed. | Late appointment of consultants | Designs to be complete before end of November 2014 | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of library at Mokwakwaila by 30 June 2015 | Mokwakwaila library | 375000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Terms of reference developed and submitted to SCM for advertisement | None | None | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of Ga-Kgapane stadium by 31 March 2015 | Kgapane stadium | 3600000 | 01/07/2014 | 31/03/2015 | Submit specifications and advertise for contractors | Specifications submitted. Tender not advertised. | Project not yet advertised | To be advertised in November 2014 | 0 | INDEP / B & T
54 | Access to Sustainable Basic Services | Property Services | Refurbish municipal workshop and stores by 12 December 2014 | Refurbishment of Municipal Workshop and stores | 500000 | 01/07/2014 | 12/12/2014 | Appointment of service provider. Project management and construction monitoring to achieve progress of 40% | Service provider not appointed. Progress at 0%. | Bids are above the budget | Allocate sufficient budget during budget adjustment and re-advertise the tender. | 0 | INDEP / B & T
54 | Access to Sustainable Basic Services | Property Services | Renovate 6 Rottaba Cottages in Modjadjiskloof by 31 March 2015 | Rehabilitation of Rotaba Cottages | 500000 | 01/10/2014 | 31/03/2015 | Develop and submit specifications to SCM for advertisement. Advertise for service providers | Specifications developed and submitted to SCM. Tender not advertised. | Project not yet advertised | To be advertised in November 2014 | 0 | INDEP / B & T
52 | Access to Sustainable Basic Services | Electricity Distribution | Upgrading of electricity infrastructure at Modjadjiskloof for compliance with NER by 31 March 2015 | Upgrade of Electricity to NER Standards | 5326472 | 01/07/2014 | 31/03/2015 | Advertise for contractors | Advertisement for contractors not done. | Project not yet advertised | To be advertised in November 2014 | 0 | INDEP / B & T
25 | Access to Sustainable Basic Services | Street Lighting | Erection of two (2) highmast lights at Moroatshehla village by 30 September 2014. | Moroatshehla Highmast Lights | 105000 | 01/07/2014 | 30/09/2014 | Erection of highmast lights | Highmast lights not erected. | Late appointment of contractors | Lights to be erected by mid November 2014 | 0 | INDEP / B & T
25 | Access to Sustainable Basic Services | Street Lighting | Erection of two (2) highmast lights at Thakgalang village by 30 September 2014 | Thakgalang Highmast Lights | 105000 | 01/07/2014 | 30/09/2014 | Erection of highmast lights | Highmast lights not erected. | Late appointment of contractors | Lights to be erected by mid November 2014 | 0 | INDEP / B & T
25 | Access to Sustainable Basic Services | Street Lighting | Erection of two (2) highmast lights at Mapaana village by 30 September 2014 | Mapaana Highmast Lights | 105000 | 01/07/2014 | 30/09/2014 | Erection of highmast lights | Highmast lights not erected. | Late appointment of contractors | Lights to be erected by mid November 2014 | 0 | INDEP / B & T
25 | Access to Sustainable Basic Services | Street Lighting | Erection of two (2) highmast lights at Shamfana village by 30 September 2014 | Shamfana Highmast Lights | 105000 | 01/07/2014 | 30/09/2014 | Erection of highmast lights | Highmast lights not erected. | Late appointment of contractors | Lights to be erected by mid November 2014 | 0 | INDEP / B & T
25 | Access to Sustainable Basic Services | Street Lighting | Erection of two (2) highmast lights at Mamokgadi village by 30 September 2014 | Mamokgadi Highmast Lights | 105000 | 01/07/2014 | 30/09/2014 | Erection of highmast lights | Highmast lights not erected. | Late appointment of contractors | Lights to be erected by mid November 2014 | 0 | INDEP / B & T
25 | Access to Sustainable Basic Services | Street Lighting | Erection of two (2) highmast lights at Malematja village by 30 September 2014 | Malematja Highmast Lights | 105000 | 01/07/2014 | 30/09/2014 | Erection of highmast lights | Highmast lights not erected. | Late appointment of contractors | Lights to be erected by mid November 2014 | 0 | INDEP / B & T
25 | Access to Sustainable Basic Services | Street Lighting | Erection of two (2) highmast lights at Mamphakathi village by 30 September 2014 | Mamphakati Highmast Lights | 105000 | 01/07/2014 | 30/09/2014 | Erection of highmast lights | Highmast lights not erected. | Late appointment of contractors | Lights to be erected by mid November 2014 | 0 | INDEP / B & T
25 | Access to Sustainable Basic Services | Street Lighting | Erection of ten(10) highmast lights in various villages by 30 September 2014 | Highmast Lights in 10 villages | 6000000 | 01/07/2014 | 30/09/2014 | Submit specifications for advertisement of contractors | Specifications submitted. Tender not advertised. | Project not yet advertised | To be advertised in November 2014 | 0 | INDEP / B & T
25 | Access to Sustainable Basic Services | Street Lighting | Erection of two (2) highmast lights at Abel village by 30 September 2014 | Abel Highmast Lights | 105000 | 01/07/2014 | 30/09/2014 | Erection of highmast lights | Highmast lights not erected. | Late appointment of contractors | Lights to be erected by mid November 2014 | 0 | INDEP / B & T
34 | Access to Sustainable Basic Services | Waste Management / Refuse removal | Construction of landfill site at Maphalle village by 31 March 2015 | Landfill Site | 5000000 | 01/07/2014 | 31/03/2015 | Submit specifications to SCM and advertise | Specifications submitted to SCM. Tender not advertised. | Project not yet advertised | To be advertised in November 2014 | 0 | INDEP / B & T
22 | Improved Local Economy | Community & Social | To organize and conduct environmental programme within the municipality quarterly | Environmental Programmes | 100000 | 01/07/2014 | 30/06/2015 | Coordinate and conduct enviromental related events and campaigns (1 per quarter) | 1 Enviromental related event and campaigns coordinated and conducted. | None | None | 0 | COMM
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Construction of paving and fence at Senwamokgope community hall by 31 March 2015 | Senwamokgope Comm Hall Paving and Fencing | 1500000 | 01/07/2014 | 31/03/2015 | Submit specifications to SCM for advertisement | Specifications submitted to SCM. Tender advertised. | None | None | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Planning and designing of community hall for Ward 2 by 31 March 2015 | Ward 2 Community Hall | 280000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Specifications developed and submitted to SCM.Tender advertised. | None | None | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Planning and designing of community hall for Ward 5 by 31 March 2015 | Ward 5 Community Hall | 280000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Specifications developed and submitted to SCM.Tender advertised. | None | None | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Planning and designing of community hall for Matswi village by 31 March 2015 | Matswi Community Hall | 280000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Specifications developed and submitted to SCM.Tender advertised. | None | None | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Planning and designing of community hall for Mohlele village by 31 March 2015 | Mohlele Community Hall | 280000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Specifications developed and submitted to SCM.Tender advertised. | None | None | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Planning and designing of community hall for Mamaila (Kolobetona) village by 31 March 2015 | Mamaila - Kolobetona Community Hall | 280000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Specifications developed and submitted to SCM.Tender advertised. | None | None | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Planning and designing of community hall for Shamfana village by 31 March 2015 | Shamfana Community Hall | 280000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Specifications developed and submitted to SCM.Tender advertised. | None | None | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Planning and designing of new community hall for Rotterdam by 31 March 2015 | Rotterdam (new Community hall) | 2400000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Specifications developed and submitted to SCM.Tender advertised. | None | None | 0 | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Construction of Ga-Kgapane Parks (Below Civic Centre and Mesopotamia) by 31 March 2015 | Ga-Kgapane Parks | 500000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Terms of reference developed and submitted to SCM. Tender advertised. | Late appointment of contractors | To be finalised by end of March 2014 | 0 | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Enhancement & Beautification of Modjadjiskloof Town Entrances by 30 June 2015 | Enhancement & Beautification of Town Entrances | 700000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Terms of reference not developed and submitted to SCM for advertisement | Late appointment of service provider for designs | Monitoring of the service provider to finalise the designs for advertisement | 0 | COMM
34 | Access to Sustainable Basic Services | Sports & Recreation | Installation of 3 outdoor gyms at GaKgapane, Modjadjiskloof and Senwamokgope by 31 March 2015 | Outdoor Gyms x3 (Kgapane, Senwamokgope &Modjadjiskloof) | 1600000 | 01/07/2014 | 31/03/2015 | Develop and submit terms of reference to SCM for advertisement. | Terms of reference developed and submitted to SCM. Tender advertised | None | None | 0 | COMM
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of sport complex for Mamanyoha village by 30 June 2015 | Mamanyoha Sports Complex | 500000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Terms of reference developed and submitted to SCM for advertisement | None | None | 0 | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of sport complex for Rotterdam village by 30 June 2015 | Rotterdam Sports Complex | 500000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Terms of reference developed and submitted to SCM for advertisement | None | None | 0 | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of youth centre for Sekgopo village by 30 June 2015 | Sekgopo Youth Centre | 320000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Terms of reference developed and submitted to SCM for advertisement | None | None | 0 | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of youth centre for Ga-Kgapane township by 30 June 2015 | Kgapane Youth Centre | 320000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Terms of reference developed and submitted to SCM for advertisement | None | None | 0 | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of youth centre for Mokwakwaila village by 30 June 2015 | Mokwakwaila Youth Centre | 320000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Terms of reference developed and submitted to SCM for advertisement | None | None | 0 | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of youth centre for Roerfontein village by 30 June 2015 | Roerfontein Youth Centre | 320000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Terms of reference developed and submitted for advertisement. | None | None | 0 | INDEP / B & T
31 | Access to Sustainable Basic Services | Sports & Recreation | Construction of outdoor gym at Maphalle by 31 March 2015 | Maphalle Outdoor gym | 550000 | 01/07/2014 | 31/03/2015 | Submission of specifications to SCM. Advertisement for service providers | Specifications submitted to SCM. Tender Advertised. | None | None | 0 | INDEP / B & T
31 | Access to Sustainable Basic Services | Sports & Recreation | Construction of outdoor gym at Sekgopo village by 31 March 2015 | Sekgopo Outdoor gym | 550000 | 01/07/2014 | 31/03/2015 | Submission of specifications to SCM. Advertisement for service providers | Specifications submitted to SCM. Tender Advertised. | None | None | 0 | INDEP / B & T
31 | Access to Sustainable Basic Services | Sports & Recreation | Construction of outdoor gym at Abel village by 31 March 2015 | Abel Outdoor gym | 550000 | 01/07/2014 | 31/03/2015 | Submission of specifications to SCM. Advertisement for service providers | Specifications submitted to SCM. Tender Advertised. | None | None | 0 | INDEP / B & T
31 | Access to Sustainable Basic Services | Sports & Recreation | Construction of outdoor gym at Ga-Kuranta village by 31 March 2015 | Kuranta Outdoor gym | 550000 | 01/07/2014 | 31/03/2015 | Submission of specifications to SCM. Advertisement for service providers | Specifications submitted to SCM. Tender Advertised. | None | None | 0 | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Design and construction of sports ground at Ga-Kgapane by 30 June 2015 | Kgapane Sports ground | 5000000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM and advertisement | Terms of reference developed and submitted to SCM. Tender not advertised. | Project not yet advertised | To be advertised in November 2014 | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Libraries and Archives | Procuring and installation of modular issue counters at Soetfontein library 31 March 2015 | Modular issue Counters (2) | 80000 | 01/07/2014 | 31/03/2015 | Develop and submit specifications to SCM for advertisement | Specification developed and submitted to SCM for advertisement | None | None | 0 | COMM

## LED PROJECTS
KPA 3 LOCAL ECONOMIC DEVELOPMENT PROJECTS OUTPUT 3: IMPLEMENTATION OF THE COMMUNITY WORK PROGRAMME
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project / Initiative | Budget 2014/2015 | Start Date | Completion Date | Milestones Qtr Ending Sept 14 | Progress to date | Challenges | Intervention strategies |  | Project Owner
Expenditure
22 | Access to Sustainable Basic Services | Planning and Development | Design and construction of fence and admin block at the new show ground by 30 June 2015 | GLM Show Ground | 6000000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM and advertisement. | Terms of reference developed and submitted to SCM. Tender not advertised. | Project not yet advertised | To be advertised in November 2014 | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Design and construction of market stalls at Sekgopo by 30 June 2015 | Sekgopo Market stalls | 800000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement | Terms of reference developed and submitted to SCM for advertisement. | None | None | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Design and construction of market stalls at Sekgosese by 30 June 2015 | Sekgosese Market stalls | 800000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM and advertisement | Terms of reference developed and submitted to SCM. Tender not advertised. | Project not yet advertised | To be advertised in November 2014 | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Design and construction of market stalls at Maphalle by 30 June 2015 | Maphalle Market stalls | 800000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement | Terms of reference developed and submitted to SCM for advertisement. | None | None | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Design and construction of market stalls at Ga-Kgapane by 30 June 2015 | Kgapane Market stalls | 800000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement | Terms of reference developed and submitted to SCM for advertisement. | None | None | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Design and construction of market stalls at Mamaila (Phaphadi) by 30 June 2015 | Mamaila-Phaphadi Market stalls | 800000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement | Terms of reference developed and submitted to SCM for advertisement. | None | None | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Design and construction of market stalls at Madumeleng by 30 June 2015 | Madumeleng Market stalls | 800000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement | Terms of reference developed and submitted to SCM for advertisement. | None | None | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Design and construction of market stalls at Khosuthopa by 30 June 2015 | Khosuthopa Market stalls | 800000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement | Terms of reference developed and submitted to SCM for advertisement. | None | None | 0 | INDEP / B & T
22 | Improved Local Economy | Local Economic Development | Identify and implement SMME support initiatives by 30 June 2015 | Support of SMMEs' | 200000 | 01/07/2014 | 30/06/2015 | Identify SMME support initiatives and submit to Portfolio Committee | Initiatives identified | Not yet adopted by portfolio committee | Initiatives to be considered by Portfolio Committee | 0 | INDEP
22 | Improved Local Economy | Local Economic Development | Participate in the annual Tourism Indaba by 30 June 2015 | Tourism Indaba | 150000 | 01/07/2014 | 30/06/2015 | Review of outcomes from previous Tourism Indaba event | Outcomes from previous Tourism Indaba event reviewed. | None | None | 0 | INDEP
22 | Improved Local Economy | Local Economic Development | Promote tourism activities within GLM by 30 June 2015 | Tourism Development | 400000 | 01/07/2014 | 30/06/2015 | Identify tourism development initiatives and submit to Portfolio Committee | Tourism development initiatives identified and submitted to Portfolio Committee | Not yet adopted by portfolio committee | Initiatives to be considered by Portfolio Committee | 0 | INDEP
22 | Improved Local Economy | Planning & Development | Implement agricultural development initiatives by 30 June 2015 | Agricultural development | 60000 | 01/07/2014 | 30/06/2015 | Development of terms of reference and submit to SCM | Terms of reference notdeveloped and submitted to SCM | None | None | 0 | INDEP / B & T
22 | Improved Local Economy | Planning & Development | Identify business support initiatives by 30 June 2015 | Business Support | 60000 | 01/07/2014 | 30/06/2015 | Identify business support initiatives and submit to Portfolio Committee | Business support initiatives identified and submitted to Portfolio Committee | None | None | 0 | INDEP
22 | Improved Local Economy | Planning & Development | Develop entrance and fencing for Manokwe cave by 30 June 2015 | Development of Manokwe cave | 400000 | 01/07/2014 | 30/06/2015 | Development of terms of reference and submit to SCM | Terms of reference were developed and submitted to SCM. | None | None | 0 | INDEP / B & T
22 | Improved Local Economy | Planning & Development | Support emerging piggery farmers within GLM by 30 June 2015 | GLM Piggery Project | 400000 | 01/07/2014 | 30/06/2015 | Identification of emerging farmers (beneficiaries) | The beneficiaries have been identified. A site visit was done to selected piggery farmers | None | None | 0 | INDEP
22 | Improved Local Economy | Planning & Development | Award performance in agricultural sector by 12 December 2014 | Agricultural Awards | 120000 | 01/07/2014 | 12/12/2014 | Implementation plan for awards | Implementation plan developed for the agricultural awards. | None | None | 0 | INDEP
22 | Improved Local Economy | Planning & Development | Compile feasibility study for picnic sites in GLM by 30 June 2015 | Feasibility Study for Picnic Sites | 400000 | 01/07/2014 | 12/12/2014 | Development of terms of reference and submit to SCM | Terms of reference were developed and submitted to SCM. | None | None | 0 | INDEP / B & T
34 | Improved Local Economy | Sports and Recreation | To organise the rainmaking ceremony by 12 December 2014 | Rain making ceremony | 100000 | 01/07/2014 | 12/12/2014 | Attend to preparatory meetings | Preparatory meeting attended | None | None | 0 | COMM
34 | Improved Local Economy | Sports and Recreation | To organise the Wolkberg sports day by 31 March 2015 | Wolkberg Sports day | 120000 | 01/07/2014 | 31/03/2015 | Preparatory meetings and development of Implementation plan. | Preparatory meeting held and implementation plan developed. | None | None | 0 | COMM
34 | Improved Local Economy | Sports and Recreation | To organise and host various sport codes by 30 June 2015 | Sports Activities | 200000 | 01/07/2014 | 30/06/2015 | Development of Implementation plan | Implementation plan developed | None | None | 0 | COMM
34 | Improved Local Economy | Sports and Recreation | To organise event for cultural activities by 31 March 2015 | Cultural Activities | 150000 | 01/07/2014 | 31/03/2015 | Development of Implementation plan | Implementation plan developed | None | None | 0 | COMM
34 | Improved Local Economy | Sports and Recreation | To organise Choral Music Competition by 31 March 2015 | Choral Music Competition | 100000 | 01/07/2014 | 31/03/2015 | Develop implementation plan and advertisement to invite participants | Implementation plan developed and participants invited. | None | None | 0 | COMM
22 | Improved Local Economy | Planning and Development | To demarcate and peg sites at Goudplaas by 31 March 2015 | Dermacation of sites (Goudplaas) | 700000 | 01/07/2014 | 31/03/2015 | Development of terms of reference, submit to SCM and advertise | Terms of refernce developed and submitted to SCM and advertised. | None | None | 0 | INDEP / B & T
22 | Improved Local Economy | Planning and Development | To demarcate and peg sites at Nooitedaght by 31 March 2015 | Dermacation of sites (Nooitedaght Farm) | 600000 | 01/07/2015 | 31/03/2015 | Development of terms of reference, submit to SCM and advertise | Terms of reference was developed. Motivation to engage the service provider who could not conclude demarcation at Sekgosese was approved. | None | None | 0 | INDEP / B & T
22 | Improved Local Economy | Planning & Development | Conveyance of unregistered municipal properties by 31 March 2015 | Conveyance of Unregistered GLM properties | 60000 | 01/07/2014 | 31/03/2015 | Development of terms of reference, submit to SCM and advertise | Terms of reference were developed and submitted to SCM. Tender not advertised. | Project not yet advertised | To be advertised in November 2014 | 0 | INDEP / B & T
22 | Improved Local Economy | Planning & Development | Implement Land-use Management Scheme by 30 June 2015 | Land-use Management | 500000 | 01/07/2014 | 30/06/2015 | 100% (# of complaints received / # of complaints resolved) | 0 % (7 complaints received / 0 complaints resolved) | In progress | To resolve them before the end of financial year | 0 | INDEP
22 | Improved Local Economy | Planning & Development | Planning for renewal of Modjadjiskloof CBD by 30 June 2015 | Modjadjiskloof Urban Renewal Plan | 400000 | 01/07/2014 | 30/06/2015 | Development of terms of reference, submit to SCM and advertise | Terms of reference were developed and submitted to SCM. Tender not advertised. | Project not yet advertised | To be advertised in November 2014 | 0 | INDEP / B & T
22 | Improved Local Economy | Planning & Development | Scan building plans for uploading in the GIS by 31 March 2015 | Scanning of building plans into GIS | 100000 | 01/10/2014 | 31/03/2015 | Compile and submit motivation for engaging service provider that designed the GIS | Motivation to engage the service provider who designed the existing GIS was submitted and awaits approval. | None | None | 0 | INDEP / B & T
Note on F15: Nomsa Makhubela:
Note on E16: Nomsa Makhubela: individuals

## MFMV KPI
KPA 4 MUNICIPAL FINANCIAL VIABILITY KEY PERFORMANCE INDICATORS OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY
Vote Nr | Strategic Objective | Progranmes | Measurable Objectives | Performance measures | Baseline / Status | Budget 2014/2015 | 1st Quarter target | Progress to date | Challenges | Intervention strategies | Expenditure | Responsible Person
50 | Sustainable Financial Institution | Budget and Reporting | To ensure that financial information is supplied to relevant authorities by 30 June 2015. | Financial information supplied to relevant authorities by 30 June 2015 | Information was submitted by 10 June 2015 | Operational | N/A | N/A | N/A | N/A | 0 | CFO
50 | Sustainable Financial Institution | Budget and Reporting | To ensure that quartely financial statements are prepared within 14 days after the end of each quarter. | # of quarterly financial statements and submitted to the relevant authorities | 25% | Operational | 1 financial statement (100%) | No quarterly financial statement compliled. | Lack of capacity | KPMG is in the process of transfering skills to municipal officials | 0 | CFO
50 | Sustainable Financial Institution | Supply Chain Management | To ensure payment of service providers within 30 days of the submission of invoices. | % of payments of service providers made within 30 days (# of invoices received / # of invoices paid. | 100% | Operational | 100% | 100% | None | None | 0 | CFO
50 | Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality within the financial year | % capital budget spent as approved by Council | 70% | Operational | 25% | 12% (R18 534 809 / R157 975 472) | Service Providers not yet appointed. | Expedite bidding process |  | CFO/INDEP/MM
50 | Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality within the financial year | % MIG expenditure | 70% | 46950000 | 25% | 14% (R7 649 679 / R53 440 000) | Service Providers not yet appointed. | Expedite bidding process | 5856875 | CFO/INDEP/MM
50 | Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality within the financial year | % FMG expenditure | 90% | 1550000 | 25% | 39% (R639 760.51 / R1 600 000) | None | None | 639760.51 | CFO/INDEP/MM
50 | Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality within the financial year | % MSIG expenditure | 100% | 890000 | 25% | 0% | None | To spend during the course of the year | 0 | CFO/INDEP/MM

## MFMV PROJECTS
KPA 4 MUNICIPAL FINANCIAL VIABILITY PROJECTS OUTCOME NINE (OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY)
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project / Initiative | Budget 2014/2015 | Start Date | Completion Date | Milestones Qtr Ending Sept 2014 | Progress to date | Challenges | Intervention strategies | Expenditure | Project Owner
50 | Sustainable Financial Institution | Budget and Treasury | Installation of GPS system and training of end users by 31 March 2015 | GPS system and training | 80000 | 01/07/2014 | 31/03/2015 | Tender advertisement for supply, delivery and training | Tender not advertised | Delay in specification proces | To advertise before end October 2014. | 0 | CFO
50 | Sustainable Financial Institution | Budget and Treasury | Installation of security glass at Senwamokgope sub-office by 30 September 2014 | Security glass at Senwamokgope sub office | 8000 | 01/07/2014 | 30/09/2014 | Request quatations for procurement, appoint service provider, supply and installation of security glass | Quatations not requested. Service Provider not appointed. Security glass not installed. | Delay in specification proces | To source 3 quatations and procure before end November 2014. | 0 | CFO
50 | Sustainable Financial Institution | Budget and Treasury | To conduct environmental impact assessment, purchase new tanks, pumps and shades by 31 March 2015 | New tanks, pumps and shades | 550000 | 01/07/2014 | 31/03/2015 | Tender advertisement and appointment. | Tender not advertised. Service Provider not appointed. | Delay in specification development | To advertise before end December 2014. | 0 | CFO
54 | Access to Sustainable Basic Services | Property Services | To purchase 1 concrete mixer by 30 September 2014 | Concrete Mixer | 20000 | 01/07/2014 | 30/09/2014 | Develop, submit specifications to SCM and purchase | Specification developed and submitted to SCM. Concrete mixer not purchased | Delay in specification development | To advertise before end December 2014. | 0 | INDEP / B & T
52 | Access to Sustainable Basic Services | Electricity Distribution | Purchasing of electrical tools and equipment by 30 September 2014 | Tools and equipment | 200000 | 01/07/2014 | 30/09/2014 | Develop, submit specifications to SCM and purchase | Specification not submitted to SCM. Tools and Equipments not purchased | Delay in specification development | To advertise before end December 2014. | 0 | INDEP / B & T
50 | Sustainable Financial Institution | Indigent Management | To register qualifying indigents 30 June 2014 | Updating of Indigent Register | Operational | 01/07/2014 | 30/06/2015 | Collection of information on indigent households and update the register | Information collected and indigent register updated | None | None | 0 | CFO
50 | Sustainable Financial Institution | Revenue Management | Review, adopt and implement Revenue Enhancement Strategy 30 June 2015 | Revenue Enhancement Strategy | Operational | 01/07/2014 | 30/06/2015 | Review and adoption of Draft Revenue Enhancement Strategy | Revenue Enhancement Strategy not reveiwed and adopted. | The Strategy was not reviewed because it was rejected by the Audit Committee. | Expedite the development of a new Enhancement Strategy | 0 | CFO
50 | Sustainable Financial Institution | Revenue Management | To update household billing system information 30 Sept 2014 and implement | Data cleansing | Operational | 01/07/2014 | 30/06/2015 | Update households information on billing system | Household information on billing system not fully updated | Slow process of updating | SEBATA to assist the municipality in updating household information. | 0 | CFO
50 | Sustainable Financial Institution | Asset Management | To monitor the process of unbundling and make progress report by 30 June 2015 | Unbundling of Infrastructure Assets to update the asset register | Operational | 01/07/2014 | 30/06/2015 | Tender advertisement | Tender no advertised | Delay in specification development. | To advertise by March 2015 | 0 | CFO
50 | Sustainable Financial Institution | Asset Management | Updating of valuation roll by 30 June 2015 | Valuation Roll | Operational | 01/07/2014 | 30/06/2015 | Conduct assessment of supplementary valuation roll. | No supplementary valuation roll conducted because ther was no new property reported to be valuated. | None | None | 0 | CFO

## GGPP KPI's
KPA 5 GOOD GOVERNANCE AND PUBLIC PARTICIPATION KEY PERFORMANCE INDICATORS OUTCOME 9 (OUTPUT 5: DEEPEN DEMOCRACY THROUGH A REFINED WARD COMMITTEE MODEL, OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY)
Vote Nr | Strategic Objective | Programmes | Measurable Objectives | Performance measures | Baseline / Status | Budget 2014/2015 | 1st Quarter target | Progress to date | Challenges | Intervention strategies | Responsible Person
54 | Improved Governance and Organisational Excellence | Ward Committee | To ensure full participation of ward committees in annual ward programmes within the financial year. | # of ward committee programmes evaluated per month. | 29 | Operational | 29 | 29 | None | None | MM/CORPS
54 | Improved Governance and Organisational Excellence | Ward Committee | To ensure that community complaints are resolved within time frames. | % of complaints attended per month (# of community complaints received/ # of complaints atteneded to). | 100% | Operational | 100% | 92% (13 complaints received / 12 complaints attended to) | 1 Complaint ( for a bridge) was forwarded to INDEP | None | MM
54 | Improved Governance and Organisational Excellence | Local Imbizos | To implement Mayoral outreach programme by 30 June 2015 | # of local imbizos held by the Mayor by 30 June 2015. | 4 | 1000000 | 1 | 1 Imbizo held | None | None | MM
54 | Improved Governance and Organisational Excellence | Local Imbizos | To ensure community participation in the affairs of the municipality within the financial year. | # of people who attend events | 100% | Operational | 100% | 659 people attended the loca imbizo | None | None | MM
54 | Improved Governance and Organisational Excellence | Traditional Leaders | To establish a good relationship with traditional leaders within the financial year. | # traditional leaders invited to take part in council meetings and activities. | 10 | Operational | 10 | 10 | None | None | MM
54 | Improved Governance and Organisational Excellence | IT | To publicise official documents in the website within legislated time frames (Budget, IDP, SDBIP) | # of official documents published. | 3 | Operational | 3 | 3 | None | None | IT
54 | Improved Governance and Organisational Excellence | Communication | To promote effective and efficient communication within the financial year. | # of articles issued to the media quartely. | 1 | Operational | 1 | 4 | None | None | Ass-Director (Mayor's office)/MM
54 | Improved Governance and Organisational Excellence | Communication | To promote effective and efficient communication within the financial year. | # of newslatters issued quarterly. | 4 | Operational | 1 | 0 | Delay in the development of the newsletter. | Publish duringthe second quarter | Ass-Director (Mayor's office)/MM
54 | Improved Governance and Organisational Excellence | Legal | To ensure proper contract management within the financial year. | % appointed service providers with Service Level Agreement (# of service providers appointed/# of service providers with service level agreement) | 100% | Operational | 100% | No appointments were made | None | None | CORPS/MM
46 | Improved Human Resource | Skills Development | To ensure effective implementation of the WSP within the financial year. | % employees trained as per the WSP | 100% | Operational | 25% | 35% (182/64) employees trained as per WSP | None | None | CORPS
46 | Improved Human Resource | OHS | To ensure a health and safe working environment | # of wellness and OHS campaigns conducted per quarter | 4 | Operational | 1 | 1 wellness and OHS campaign held | None | None | CORPS

## GGPP PROJECTS
KPA 5 GOOD GOVERNANCE AND PUBLIC PARTICIPATION PROJECTS OUTPUT 5: DEEPEN DEMOCRACY THROUGH A REFINED WARD COMMITTEE MODEL, OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY)
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project / Initiative | Budget 2014/2015 | Start Date | Completion Date | Milestones Qtr Ending Sept 2014 | Progress to date | Challenges | Intervention strategies | Expenditure | Project Owner
34 | Improved Governance and Organisational Excellence | Good Governance | Manage events effectively by 30 June 2015 | Communication and event management | 100000 | 01/07/2014 | 30/06/2015 | Manage events and 25% of the budget spent | No communication programme / event was done. | Budget not spend | To hold events before end of December 2014. | 0 | MM
40 | Improved Governance and Organisational Excellence | Good Governance | To award academic excellent performers by 30 June 2015 | Municipal Mayor’s excellent award | 200000 | 01/01/2015 | 31/03/2015 | N/A | N/A | N/A | N/A | 0 | MM
34 | Improved Governance and Organisational Excellence | Good Governance | Attending of conference and congresses | Conference and congresses | 100000 | 01/07/2014 | 30/06/2015 | Adrehence to procedures and attend conference and congresses | None | None | None | 0 | CORPS
46 | Improved Governance and Organisational Excellence | Skills Development/Training | To improve capacity of councillors by 30 June 2015 | Capacity building: councillors | 318600 | 01/10/2014 | 30/06/2015 | 100% of the identified councillors | None | None | None | 0 | CORPS
40 | Improved Governance and Organisational Excellence | Batho Pele | To implement Batho Pele principles by 31 March 2015 | Batho Pele strategies | 30798 | 01/10/2014 | 12/12/2014 | N/A | Bathopele event held concurrently with Local Imbizo | None | None | 18200 | MM
40 | Improved Governance and Organisational Excellence | Bursary Scheme | To fund good performing student from the needy families | Bursary scheme council | R2 000 000 | 01/07/2014 | 30/06/2015 | Payment of costs | No claim submitted | None | None | 0 | MM
54 | Improved Governance and Organisational Excellence | Humanitarian | To enhance humanitarian by 30 June 2014 | Humanitarian Aid | 100000 | 01/07/2014 | 30/06/2015 | 25% | No activity / spending on humanitarin aid | None | None | 0 | MM
40 | Improved Governance and Organisational Excellence | Communication | To issue 4 newsletters by 30/06/2015 | News letter | 350000 | 01/07/2014 | 30/06/2015 | 1 | No news letter was issued. | Delay in compiling the newsletter | To issue before theend December 2014 | 0 | MM
40 | Improved Governance and Organisational Excellence | Communication | To purchase calenders and diaries by 30/09/2014 | Calendar and diaries | 20000 | 01/07/2014 | 30/09/2014 | 100% | Calenders and diaries not purchased | Delay in specification processes | To procure before end December 2014 | 0 | MM
40 | Improved Governance and Organisational Excellence | MM | Purchasing of Council vehicle for the Speaker by 31 March 2015 | Council Vehicle for the speaker | 700000 | 01/09/2014 | 31/09/2014 | Develop specifications and submit to SCM. Advertise and appointment of service providers | Specifications not submitted to SCM. Service provider not appointed. | Late submission of specifications | To procure before end March 2015 | 0 | MM
40 | Improved Governance and Organisational Excellence | MM | Purchasing of two (2) gazebos by 30 September 2014 | 2 x Gazebos | 40000 | 01/07/2014 | 30/09/2014 | Sourcing of quatations and appointment of service provider for supply | Quatations not sourced. Service provider not appointed for supply | Delay submission of specifications | To source quatations and procure befor the end December 2014. | 0 | MM
40 | Improved Governance and Organisational Excellence | MM | Purchasing of a scanner by 30 September 2014 | Scanner | 5000 | 01/07/2014 | 30/09/2014 | Sourcing of quatations and appointment of service provider for supply | Specifications submitted to SCM. Quatations not sourced. Service provider not appointed for supply | Delay in specification processes | To procure before end December 2014 | 0 | MM
40 | Improved Governance and Organisational Excellence | MM | Purchasing of a Cooler box by 30 September 2014 | Cooler box | 5000 | 01/07/2014 | 30/09/2014 | Sourcing of quatations and appointment of service provider for supply | Quatations not sourced. Service provider not appointed for supply | Late submission of specifications | To source quatations and procure befor the end December 2014. | 0 | MM
54 | Improved Governance and Organisational Excellence | Property Services | Purchasing of 5 Aqua Coolers by 30 September 2014 | 5x Aqua coolers | 15000 | 01/07/2014 | 30/09/2014 | Sourcing of quatations and appointment of service provider for supply | Specifications submitted to SCM. Quatations not sourced. Service provider not appointed for supply | Delay in specification processes | To procure before end December 2014 | 0 | CORPS
54 | Improved Governance and Organisational Excellence | Property Services | Purchasing of shredding machine for registry by 30 September 2014 | Shredding machine for registry | 8000 | 01/07/2014 | 30/09/2014 | Sourcing of quatations and appointment of service provider for supply | Specifications not submitted to SCM. Quatations not sourced. Service provider not appointed for supply | Delay in submission of specification. | To procure before end December 2015 | 0 | MM
40 | Improved Governance and Organisational Excellence | Special Programmes | To facilitate youth development activities by 30 June 2015 | Youth desk activities | 280000 | 01/07/2014 | 30/06/2015 | Develop youth desk activity program | Youth desk activity program developed. | None | None | 0 | MM
40 | Improved Governance and Organisational Excellence | Special Programmes | To facilitate gender desk activities by 30 June 2016 | Gender desk activities | 200000 | 01/07/2014 | 30/06/2015 | Develop Gender desk activity program | Gender desk activity program developed. | None | None | 0 | MM
54 | Improved Governance and Organisational Excellence | Special Programmes | To facilitate Disability desk activities by 30 June 2017 | Disability desk activities | 100000 | 01/07/2014 | 30/06/2015 | Develop Disability desk activity program | Disability desk activity program developed. | None | None | 0 | MM
40 | Improved Governance and Organisational Excellence | Special Programmes | To facilitate HIV/AIDS Council activities by 30 June 2018 | HIV & AIDS Council activities | 95000 | 01/07/2014 | 30/06/2015 | Develop HIV/AIDS Council activity program | HIV/AIDS Council activity program developed. | None | None | 0 | MM
40 | Improved Governance and Organisational Excellence | Special Programmes | Supporting initiatives for youth empowerment | Youth empowerment projects | 200000 | 01/07/2014 | 30/06/2015 | Youth empowerment | Memorandum submitted. Requisitions for tools and equipments have been made | Project on hold | Resuscitation of the project | 0 | MM
14 | Access to Sustainable Basic Services | Libraries and Archives | Planning and designing of library for Shotong village by 30 June 2015 | Shotong Library | 300000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Terms of reference not submitted to SCM for advertisement | Late development of the terms of reference | To submit before end of October 2014 | 0 | INDEP / B & T
14 | Access to Sustainable Basic Services | Libraries and Archives | Planning and designing of library for Rotterdam village by 30 June 2015 | Rotterdam Library | 300000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Terms of reference not submitted to SCM for advertisement | Late development of the terms of reference | To submit before end of October 2015 | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Facilities | To do cemetry layout and fencing at Ga-Kgapane cemetry by 30 June 2015 | Kgapane Cemetry layout and fencing | 1500000 | 01/07/2014 | 30/06/2015 | Develop, submit terms of reference to SCM and advertise. | Specification not submitted to SCM | Service provider for designs not completed | Urge service provider to complete designs as a matter of urgency | 0 | COMM
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of old age facility for Madumeleng village by 30 June 2015 | Madumeleng Old Age Facility | 220000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Terms of reference submitted to SCM for advertisement | None | None | 0 | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of old age facility for Ga-Kgapane township by 30 June 2015 | Kgapane Old Age Facility | 220000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Terms of reference submitted to SCM for advertisement | None | None | 0 | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of old age facility for Roerfontein village by 30 June 2015 | Roerfontein Old Age Facility | 220000 | 01/07/2014 | 30/06/2015 | Develop and submit terms of reference to SCM for advertisement. | Terms of reference submitted to SCM for advertisement | None | None | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Supply and erection of bus shelter at Mokwakwaila - Ga-Kgapane road by 31 March 2015 | Mokwakwaila to Kgapane Bus shelter | 75000 | 01/07/2014 | 31/03/2015 | Develop and submit specifications to SCM and advertise | Specification submitted to SCM for advertisement | None | None | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Supply and erection of bus shelter at Malematsa - Rapitsi road by 31 March 2015 | Rapitsi to Malematsa Bus Shelter | 75000 | 01/07/2014 | 31/03/2015 | Develop and submit specifications to SCM and advertise | Specification submitted to SCM for advertisement | None | None | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Supply and erection of bus shelter at Lemondokop - Mamaila road by 31 March 2015 | Lemondokop to Mamaila via Phooko Bus Shelter | 75000 | 01/07/2014 | 31/03/2015 | Develop and submit specifications to SCM and advertise | Specification submitted to SCM for advertisement | None | None | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Supply and erection of bus shelter at Modjadji Head Kraal by 31 March 2015 | Modjadji Headkraal Bus Shelter | 75000 | 01/07/2014 | 31/03/2015 | Develop and submit specifications to SCM and advertise | Specification submitted to SCM for advertisement | None | None | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Supply and erection of bus shelter at Goudplaats village by 31 March 2015 | Goudplaas Bus Shelter | 75000 | 01/07/2014 | 31/03/2015 | Develop and submit specifications to SCM and advertise | Specification submitted to SCM for advertisement | None | None | 0 | INDEP / B & T
28 | Roads & Transport | Vehicle Licencing and Test | Purchasing of twotraffic Blue lights by 30 September 2014 | Traffic Blue lights (2) | 20000 | 1/07/2014 | 30/09/2015 | Appointment of service provider and procurement of goods | Specification submitted to SCM | None | None | 0 | COMM
28 | Roads & Transport | Vehicle Licencing and Test | Construction Of Testing room for learners Licences by 31 March 2015 | Testing room for learners Licence | 300000 | 01/07/2014 | 31/03/2015 | Submission of specifications and advertisement for service providers | Specification not submitted to SCM | None | None | 0 | COMM
28 | Roads & Transport | Vehicle Licencing and Test | Purchasing of Traffic Sedan by 12 December 2014 | Traffic Sedan | 350000 | 01/07/2014 | 12/12/2014 | Submission of specifications and advertisement for service providers | Specification submitted to SCM | None | None | 0 | COMM

## SUMMARY OF PERFORMANCE
OVERALL ORGANISATIONAL PERFORMANCE : ACHIEVEMENT
| No. of Applicable in Qtr1 | No. Achieved | % Achieved
MTOD | 33 | 12 | 36%
BSD | 85 | 44 | 52%
LED | 28 | 21 | 75%
MFMV | 16 | 4 | 25%
GGPP | 36 | 19 | 53%
OVERALL ORGANISATIONAL PERFORMANCE |  |  | 48%