## GLM CONTRACT REGISTER JUNE 2021
CONTRACT REGISTER FOR THE PERIOD ENDING JUNE 2021 |  |  | CONTRACT REGISTER AS AT JUNE 2021
Tender number | Service provider | Description | Amount R | Appointment date | Start date | End date | Expenditure to year end R | Variation amount R | Remaining contract amount R | SLA in place (Yes / No) | Comments
GLM011/2015PR | Uranus Consulting Engineers CC | Rottredam sports Complex | 5617383.08 | 2015-03-03 | 2015-03-03 | 2015-06-30 | 6087360.6 | 469977.52 | 4.6566e-10 | Yes
GLM020/2016C | Bagaphala projects trading | Construction of Rotterdam sports complex | 32867352.69 | 2017-05-29 | 2017-06-19 | 2019-06-30 | 31726816.2 |  | 1140536.49 | Yes
GLM027/2016-PR | Uranus Consulting Engineers CC | Design and supervision of Ga-Kgapane Stadium phase 3 | 295043.9814 | 2017-03-15 | 2017-03-20 | 2017-06-30 | 602373.82 | 712606.24 | 405276.4014 | Yes
GLM027/2016C | Bagaphala projects trading | Construction of Ga-Kgapane Stadium-Phase 03 | 35001708.63 | 2017-10-20 | 2017-11-20 | 2020-11-21 | 32080592.91 |  | 2921115.72 | Yes
GLM001/2017 | Uniqueco Property Valuers (PTY) LTD | Complilation and maintenacne of the general valuation roll and supplementary valuation related services for a period for five years | 964912.28 | 2017-01-12 | 2017-01-12 | 30 june 202 |  |  |  | Yes | The rates are charged as per BOQ
GLM007/2017-PR | Motau Engineers | Design and supervision for Upgrading of Street from gravel to Paving in Moshakge village | 342000 | 2017-03-17 | 23 mach 2017 | 2017-06-30 | 342000 |  | 0 | Yes
GLM010/2015PR | Bawelile Consulting Engineers | Mamanyoha Sports Complex | 6454920.89 | 2015-04-01 | 2015-04-01 | 2015-06-30 | 6624067.86 | 169146.97 | -6.6939e-10 | Yes
GLM038/2017C | Valcross Trading Enterprise | Construction of Mamanyoya Sports complex | 30419651.76 | 2017-06-30 | 2017-07-13 | 2018-05-30 | 30419651.76 |  | 0 | Yes
GLM005/2016 | Shaweni Consulting Engineers | Design and supervision of Lemondekop street paving | 2188972.8566 | 2017-02-22 | 2017-04-24 | 2017-06-30 | 2188972.89 |  | -0.0334 | Yes
GLM002/2016-PR | Maruputlela Consultancy cc | Designs and supervision of Itieleng Sekgosese Street Paving | 775558.61 | 2017-04-25 | 2017-05-22 | 2017-08-30 | 729825.45 |  | 45733.16 | Yes
GLM019/2016-PR | Morula Consulting Engineers | Design & supervision for construction of Thakgalane sports Ground | 5446801.73 | 2017-03-23 | 2017-05-09 | 2017-06-30 | 4140829.84 |  | 1305971.89 | Yes
GLM015/2017c | Lazwi Engineering 16cc | Planning and designs for construction of ward 5 community halls | 1222598.93 | 2017-02-26 | 2017-06-19 | 2017-09-18 | 928162.99 |  | 294435.94 | Yes
GLM 001/2018 | Cathu consulting incorporated | Compilation of GRAP compliant asset register and unbundling of municipal assets for 3 years | 4874820.21 | 2018-01-05 | 2018-01-10 | 2021-01-11 | 4874820.21 |  | 0 | Yes
GLM 047/2018 | Kunene Makopo Risk Solution | Provision for security services | 6659006.808 | 2018-07-19 | 2018-07-19 | 2021-07-18 | 8373115.95 | 1714109.14 | -0.002 | Yes
GLM 005/2019 | Kipp Consulting Engineers | Planning, design and supervision of Jokong street paving | 4676355.33 | 2018-09-17 | 2018-09-20 | 2021-12-31 | 4675186.24 |  | 1169.09 | Yes
GLM 019/2018 | Sello Ramothweala Civils CC/Beten JV | Thakgalane sports complex | 38308914.97 | 2018-09-06 | 2018-09-10 | 2021-03-10 | 24162792.88 |  | 14146122.09 | Yes
GLM 011/2019 | KHABOWD TRAVEL AGENCY | TRAVEL AGENCY FOR AIR TRAVEL AND ACCOMODATION ARRANGEMENT TO THE GLM OFFICIAL AND CONCILORS | 15% commission | 2018-09-21 | 2018-09-21 | 2021-09-21 |  |  |  | Yes | The rates are charged as per BOQ
GLM 011/2019 | QUANTUM LEAP TRAVEL | TRAVEL AGENCY FOR AIR TRAVEL AND ACCOMODATION ARRANGEMENT TO THE GLM OFFICIAL AND CONCILORS | 15% commission | 2018-09-21 | 2018-09-21 | 2021-09-21 |  |  |  | Yes | The rates are charged as per BOQ
GLM011/2019 | PEACE BIRD TRAVEL AGECY | TRAVEL AGENCY FOR AIR TRAVEL AND ACCOMODATION ARRANGEMENT TO THE GLM OFFICIAL AND CONCILORS | 15% commission | 2018-09-21 | 2018-09-21 | 2021-09-21 |  |  |  | Yes | The rates are charged as per BOQ
GLM 011/2019 | BABIRWA TRAVEL | TRAVEL AGENCY FOR AIR TRAVEL AND ACCOMODATION ARRANGEMENT TO THE GLM OFFICIAL AND CONCILORS | 15% commission | 2018-09-21 | 2018-09-21 | 2021-09-21 |  |  |  | Yes | The rates are charged as per BOQ
GLM002/2019 | MASHELENI TRADING & PROJECT | PROCUREMENT OF PANEL OF SERVICES PROVIDERS FOR PRESENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROAD ROAD TO BE APPOINED ON AS WHEN "'REGUIRED BASIS FOR THE PERIOD OF THREE(3)YEARS(KGAPANE CLUSTER) | R121825 per BOQ | 2018-10-12 | 2018-10-26 | 2021-10-26 |  |  |  | Yes | The rates are charged as per BOQ
GLM002/2019 | T TLOU INVESTMEMT | PROCUREMENT OF PANEL OF SERVICES PROVIDERS FOR PRESENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROAD ROAD TO BE APPOINED ON AS WHEN "'REGUIRED BASIS FOR THE PERIOD OF THREE(3)YEARS(KGAPANE CLUSTER) | R121825 per BOQ | 2018-10-12 | 2018-10-26 | 2021-10-26 |  |  |  | Yes | The rates are charged as per BOQ
GLM002/2019 | BOSELE INDUSTRIES | PROCUREMENT OF PANEL OF SERVICES PROVIDERS FOR PRESENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROAD ROAD TO BE APPOINED ON AS WHEN "'REGUIRED BASIS FOR THE PERIOD OF THREE(3)YEARS(KGAPANE CLUSTER) | R121825 per BOQ | 2018-10-12 | 2018-10-26 | 2021-10-26 |  |  |  | Yes | The rates are charged as per BOQ
GLM002/2019 | MOKE CONTRUCTION & PROJECT | PROCUREMENT OF PANEL OF SERVICES PROVIDERS FOR PRESENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROAD ROAD TO BE APPOINED ON AS WHEN "'REGUIRED BASIS FOR THE PERIOD OF THREE(3)YEARS(KGAPANE CLUSTER) | R121825 per BOQ | 2018-10-12 | 2018-10-26 | 2021-10-26 |  |  |  | Yes | The rates are charged as per BOQ
GLM 002/2019 | SELBY CONSTRUCTION | PROCUREMENT OF PANEL OF SERVICES PROVIDERS FOR PRESENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROAD ROAD TO BE APPOINED ON AS WHEN "'REGUIRED BASIS FOR THE PERIOD OF THREE(3)YEARS(KGAPANE CLUSTER) | R121825 per BOQ | 2018-10-12 | 2018-10-26 | 2021-10-26 |  |  |  | Yes | The rates are charged as per BOQ
GLM 001/2019 | QUALITY PLANT HIRE | PROCUREMENT OF PANEL OF SERVICES PROVIDERS FOR PRESENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROAD ROAD TO BE APPOINED ON AS WHEN "'REGUIRED BASIS FOR THE PERIOD OF THREE(3)YEARS(BELIVIEW CLUSTER) | R154768.96 per BOQ | 2018-10-26 | 2018-10-26 | 2021-10-26 |  |  |  | Yes | The rates are charged as per BOQ
GLM 001/2019 | LEBP CONSTRUCTION | PROCUREMENT OF PANEL OF SERVICES PROVIDERS FOR PRESENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROAD ROAD TO BE APPOINED ON AS WHEN "'REGUIRED BASIS FOR THE PERIOD OF THREE(3)YEARS(BELIVIEW CLUSTER) | R154768.96 per BOQ | 2018-10-26 | 2018-10-26 | 2021-10-26 |  |  |  | Yes | The rates are charged as per BOQ
GLM 001/2019 | LA MOSEKEDILE JV PERFECT ZONE | PROCUREMENT OF PANEL OF SERVICES PROVIDERS FOR PRESENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROAD ROAD TO BE APPOINED ON AS WHEN "'REGUIRED BASIS FOR THE PERIOD OF THREE(3)YEARS(BELIVIEW CLUSTER) | R154768.96 per BOQ | 2018-10-26 | 2018-10-26 | 2021-10-26 |  |  |  | Yes | The rates are charged as per BOQ
GLM 001/2019 | ARCHIBOLD HOLDINGS | PROCUREMENT OF PANEL OF SERVICES PROVIDERS FOR PRESENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROAD ROAD TO BE APPOINED ON AS WHEN "'REGUIRED BASIS FOR THE PERIOD OF THREE(3)YEARS(BELIVIEW CLUSTER) | R154768.96 per BOQ | 2018-10-26 | 2018-10-26 | 2021-10-26 |  |  |  | Yes | The rates are charged as per BOQ
GLM 001/2019 | GPWG ENGINEERING(PTY)LTD | PROCUREMENT OF PANEL OF SERVICES PROVIDERS FOR PRESENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROAD ROAD TO BE APPOINED ON AS WHEN "'REGUIRED BASIS FOR THE PERIOD OF THREE(3)YEARS(BELIVIEW CLUSTER) | R154768.96 per BOQ | 2018-10-26 | 2018-10-26 | 2021-10-26 |  |  |  | Yes | The rates are charged as per BOQ
GLM003/2019 | MELROSE CIVIL AND BUILDING CONSTRUCTION | PROCUREMENT OF PANEL OF SERVICES PROVIDERS FOR PRESENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROAD ROAD TO BE APPOINED ON AS WHEN "'REGUIRED BASIS FOR THE PERIOD OF THREE(3)YEARS(MOKWAKWAILA CLUSTER) | R144841 per BOQ | 2018-10-26 | 2018-10-26 | 2021-10-26 |  |  |  | Yes | The rates are charged as per BOQ
GLM003/2019 | LOKOLANG TRADING AND PROJECTS | PROCUREMENT OF PANEL OF SERVICES PROVIDERS FOR PRESENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROAD ROAD TO BE APPOINED ON AS WHEN "'REGUIRED BASIS FOR THE PERIOD OF THREE(3)YEARS(MOKWAKWAILA CLUSTER) | R144841 per BOQ | 2018-10-26 | 2018-10-26 | 2021-10-26 |  |  |  | Yes | The rates are charged as per BOQ
GLM003/2019 | CATECO TRADING ENTERPRISE | PROCUREMENT OF PANEL OF SERVICES PROVIDERS FOR PRESENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROAD ROAD TO BE APPOINED ON AS WHEN "'REGUIRED BASIS FOR THE PERIOD OF THREE(3)YEARS(MOKWAKWAILA CLUSTER) | R144841 per BOQ | 2018-10-26 | 2018-10-26 | 2021-10-26 |  |  |  | Yes | The rates are charged as per BOQ
GLM003/2019 | XILEPFU TRADING PROJECT | PROCUREMENT OF PANEL OF SERVICES PROVIDERS FOR PRESENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROAD ROAD TO BE APPOINED ON AS WHEN "'REGUIRED BASIS FOR THE PERIOD OF THREE(3)YEARS(MOKWAKWAILA CLUSTER) | R144841 per BOQ | 2018-10-26 | 2018-10-26 | 2021-10-26 |  |  |  | Yes | The rates are charged as per BOQ
GLM003/2019 | SELLO RAMOTHWALA CIVILS CC/BETEN JV | PROCUREMENT OF PANEL OF SERVICES PROVIDERS FOR PRESENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROAD ROAD TO BE APPOINED ON AS WHEN "'REGUIRED BASIS FOR THE PERIOD OF THREE(3)YEARS(MOKWAKWAILA CLUSTER) | R144841 per BOQ | 2018-10-26 | 2018-10-26 | 2021-10-26 |  |  |  | Yes | The rates are charged as per BOQ
GLM004/2019 | Sheboneth trading enterprise | PROCUREMENT OF PANEL OF SERVICES PROVIDERS FOR PRESENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROAD ROAD TO BE APPOINED ON AS WHEN "'REGUIRED BASIS FOR THE PERIOD OF THREE(3)YEARS(SENWAMOKGOPE CLUSTER) | R157230.65 per BOQ | 2018-10-26 | 2018-10-26 | 2021-10-26 |  |  |  | Yes | The rates are charged as per BOQ
GLM004/2019 | Zevofusion (pty)Ltd | PROCUREMENT OF PANEL OF SERVICES PROVIDERS FOR PRESENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROAD ROAD TO BE APPOINED ON AS WHEN "'REGUIRED BASIS FOR THE PERIOD OF THREE(3)YEARS(SENWAMOKGOPE CLUSTER) | R157230.65 per BOQ | 2018-10-26 | 2018-10-26 | 2021-10-26 |  |  |  | Yes | The rates are charged as per BOQ
GLM004/2019 | Expectra 388 Bk | PROCUREMENT OF PANEL OF SERVICES PROVIDERS FOR PRESENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROAD ROAD TO BE APPOINED ON AS WHEN "'REGUIRED BASIS FOR THE PERIOD OF THREE(3)YEARS(SENWAMOKGOPE CLUSTER) | R157230.65 per BOQ | 2018-10-26 | 2018-10-26 | 2021-10-26 |  |  |  | Yes | The rates are charged as per BOQ
GLM004/2019 | Shao Holdings | PROCUREMENT OF PANEL OF SERVICES PROVIDERS FOR PRESENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROAD ROAD TO BE APPOINED ON AS WHEN "'REGUIRED BASIS FOR THE PERIOD OF THREE(3)YEARS(SENWAMOKGOPE CLUSTER) | R157230.65 per BOQ | 2018-10-26 | 2018-10-26 | 2021-10-26 |  |  |  | Yes | The rates are charged as per BOQ
GLM004/2019 | Perrizin Homes | PROCUREMENT OF PANEL OF SERVICES PROVIDERS FOR PRESENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROAD ROAD TO BE APPOINED ON AS WHEN "'REGUIRED BASIS FOR THE PERIOD OF THREE(3)YEARS(SENWAMOKGOPE CLUSTER) | R157230.65 per BOQ | 2018-10-26 | 2018-10-26 | 2021-10-26 |  |  |  | Yes | The rates are charged as per BOQ
GLM012/2019 | Sesula Kgomo ya Bekwa trading and project | Procurement of panel of service providers for supply and delivery of stationery for a period of 36 months | R156475.72 per BOQ | 2018-11-29 | 2018-12-05 | 2021-12-04 |  |  |  | Yes | The rates are charged as per BOQ
GLM012/2019 | Tsoga mamokgopo trading and Projects | Procurement of panel of service providers for supply and delivery of stationery for a period of 36 months | R156475.72 per BOQ | 2018-11-29 | 2018-12-05 | 2021-12-04 |  |  |  | Yes | The rates are charged as per BOQ
GLM012/2019 | Thaba Morula trading | Procurement of panel of service providers for supply and delivery of stationery for a period of 36 months | R156475.72 per BOQ | 2018-11-29 | 2018-12-05 | 2021-12-04 |  |  |  | Yes | The rates are charged as per BOQ
GLM012/2019 | Lera2 Trading | Procurement of panel of service providers for supply and delivery of stationery for a period of 36 months | R156475.72 per BOQ | 2018-11-29 | 2018-12-05 | 2021-12-04 |  |  |  | Yes | The rates are charged as per BOQ
GLM030/2019 | AFRICAN POINT JV MPHEPHU | PANEL OF MAINTAINANCE OF FACILITIES | R693799 per BOQ | 2019-01-06 | 2019-01-13 | 2022-01-12 |  |  |  | Yes | The rates are charged as per BOQ
GLM030/2019 | MOON AND EARTH TRADING AND PROJECTS 371 JV | PANEL OF MAINTAINANCE OF FACILITIES | R693799 per BOQ | 2019-01-06 | 2019-01-13 | 2022-01-12 |  |  |  | Yes | The rates are charged as per BOQ
GLM030/2019 | PATANZA/MAKOVHAFOLA JV | PANEL OF MAINTAINANCE OF FACILITIES | R693799 per BOQ | 2019-01-06 | 2019-01-13 | 2022-01-12 |  |  |  | Yes | The rates are charged as per BOQ
GLM030/2019 | AFRICAN STRAGETIC | PANEL OF MAINTAINANCE OF FACILITIES | R693799 per BOQ | 2019-01-06 | 2019-01-13 | 2022-01-12 |  |  |  | Yes | The rates are charged as per BOQ
GLM013/2019 | SERATHI TRADING ENTERPRISE | SUPPLY AND FITTINGS OF TYRES AND BATTERIES TO GLM FLEET,WHEEL BALANCING AND WHEEL ALIGNMENT FOR PERIOD OF 36 MONTHS | R704620 per BOQ | 2019-02-06 | 2019-02-11 | 2022-02-26 |  |  |  | Yes | The rates are charged as per BOQ
GLM013/2019 | SEHLABANE MUITI PROJECTS | SUPPLY AND FITTINGS OF TYRES AND BATTERIES TO GLM FLEET,WHEEL BALANCING AND WHEEL ALIGNMENT FOR PERIOD OF 36 MONTHS | R704620 per BOQ | 2019-02-06 | 2019-02-11 | 2022-02-26 |  |  |  | Yes | The rates are charged as per BOQ
GLM013/2019 | WM FACILITY MANAGEMENT PTY LTD | SUPPLY AND FITTINGS OF TYRES AND BATTERIES TO GLM FLEET,WHEEL BALANCING AND WHEEL ALIGNMENT FOR PERIOD OF 36 MONTHS | R704620 per BOQ | 2019-02-06 | 2019-02-11 | 2022-02-26 |  |  |  | Yes | The rates are charged as per BOQ
GLM013/2019 | MALAHLE TRADING ENETERPRISE | SUPPLY AND FITTINGS OF TYRES AND BATTERIES TO GLM FLEET,WHEEL BALANCING AND WHEEL ALIGNMENT FOR PERIOD OF 36 MONTHS | R704620 per BOQ | 2019-02-06 | 2019-02-11 | 2022-02-26 |  |  |  | Yes | The rates are charged as per BOQ
GLM007/2017-PR | Sheboneth Trading Enterprise | Upgrading of streets from gravel to paving in Moshakga village | 13972461.03 | 2018-10-12 | 2018-10-23 | 2019-02-28 | 13972461.03 |  | 0 | Yes
GLM 019/2016 | Maduke Trading (Pty) Ltd | Madumeleng/Shotong sports complex | 40890407.81 | 2018-09-06 | 2018-09-10 | 2021-03-10 | 26669784.94 |  | 14220622.87 | Yes
GLM018/2016-PR | T2-Tech Engineers (pty)Ltd | Design & supervision for construction of Madumeleng/shotong sports complex | 6011815.33 | 2017-02-28 | 2017-05-08 | 2017-06-30 | 4449982.71 |  | 1561832.62 | Yes
GLM006/2019 | Nsuku Consulting | Planning, designs and supervision of Rasewane and Lenoko street paving | 1694007.66 | 2018-10-25 | 2018-10-30 | 2019-01-30 | 1917877.75 | 223870.086 | -0.004 | Yes
GLM006/2019C | Sheboneth Trading Enterprise | Rasewane and Lenoko street paving | 12100054.71 | 2019-06-30 | 2019-07-06 | 2021-08-30 | 12339305.8 | 509077.0435 | 269825.9535 | Yes
GLM007/2019 | 2MC Consulting Engineers | Planning, Designs and Supervision of Manningburg Street Paving | 1239125 | 2018-10-25 | 2018-11-01 | 2019-01-30 | 1198709.94 |  | 40415.06 | Yes
GLM 010/2018 | Rivisi Electrical Contractors | Electrification of 5 villages | 5982973 | 2018-09-17 | 2018-09-20 | 2019-04-30 | 5982973 |  | 0 | Yes
GLM008/2018 | T2-Tech Engineers (Pty) Ltd | Rehabilitation of Modjadjiskloof internal streets (Uitsicht street) | 339122.81 | 2018-10-26 | 2018-11-01 | 2019-06-30 | 271687.74 |  | 67435.07 | Yes
GLM007/2019 | Lokolang Trading and Projects | Manningburg street paving | 11344294.07 | 2019-04-16 | 2019-05-06 | 2021-06-30 | 11158069.05 | 346288 | 532513.02 | Yes
GLM031/2019 | Murendwa Consulting | Fleet management system for 36 months | 2000000 | 2019-02-06 | 2019-02-11 | 2022-02-26 | 2000000 |  | 0 | Yes
GLM005/2019C | LebP Construction | Construction of Jokong street paving | 30589812.01 | 2019-02-22 | 2019-04-01 | 31 June 2021 | 23742061.72 |  | 6847750.29 | Yes
GLM035/2019 | Burika ITC solution (Pty) Ltd | Supply, installation and training ITC | 746991.72 | 2019-04-16 | 2019-09-30 | 2022-09-30 | 497954.47 |  | 249037.25 | Yes
GLM029/2019 | FIRST NATIONAL BANK | PROVISION OF BANKING SERVICES OF GLM FOR 3 YEARS | R26161.08 per BOQ | 2019-04-30 | 2019-02-01 | 2024-01-31 |  |  |  | Yes | The rates are charged as per BOQ
GLM067/2019 | Shumba Inc | Preparation of GRAP compliant Annual Financial Statements for period of 24 months | 3329581.6 | 2019-04-30 | 2019-05-13 | 2021-05-29 | 3340825.1 |  | -11243.5 | Yes
GLM066/2019 | Kgosi Monene General | Provision for security services | 37553911.12 | 2019-05-02 | 2019-05-04 | 2022-05-03 | 29553953.94 |  | 7999957.18 | Yes
GLM002/2016C | MADUKE TRADING | Construction of Itieleng Street Paving | 11740823.17 | 2019-08-01 | 2019-08-12 | 2021-06-30 | 11688140.5 |  | 52682.67 | Yes
GLM005/2016C | AFRICAN STRATEGIC COOPERATION | Lemondokop Street Paving | 12896951.1 | 2019-11-27 | 2019-12-02 | 2021-06-30 | 13498750.7 | 601799.6 | 0 | Yes
GLM015/2016C | NTSHIZAS TECHNICAL SERVICES | Ward 5 Community Hall | 7456464.28 | 2019-11-27 | 2019-12-04 | 2021-06-30 | 2359888.77 |  | 5096575.51 | Yes
GLM006/2017C | HLULANI CIVILS (PTY) LTD JV FJRIC CONSTRUCTION AND PROJECTS | Construction of Mokwasele Street Paving | 13719508.74 | 2020-01-16 | 2020-02-10 | 2022-06-30 | 14015892.12 | 352045.69 | 55662.31 | Yes
GLM006/2017-PR | HLAYELENI CONSULTING ENGINEERS | Design and supervision for upgrading of street from gravel to paving at Mokwasela village | 2332316.49 | 2017-03-17 | 2017-03-20 | 2017-06-30 | 2099084.83 |  | 233231.66 | Yes
GLM038/2019 | TSAPOKGO SECURITY | Supply and delivery of personal protective clothing - labourers and EPWP | R22150 per BOQ | 2019-04-16 | 2019-05-01 | 2022-04-30 |  |  |  | Yes | The rates are charged as per BOQ
GLM038/2019 | GLOBAL SAFETY CORPORATION (PTY) LTD | Supply and delivery of personal protective clothing - labourers and EPWP | R22150 per BOQ | 2019-04-16 | 2019-05-01 | 2022-04-30 |  |  |  | Yes | The rates are charged as per BOQ
GLM038/2019 | DITIRO TSAKA SECURITY | Supply and delivery of personal protective clothing - labourers and EPWP | R22150 per BOQ | 2019-04-16 | 2019-05-01 | 2022-04-30 |  |  |  | Yes | The rates are charged as per BOQ
GLM068/2019 | ACUTE INNOVATION (PTY) LTD | Panel of town planning consultants for implementation of various projects | 8467000 | 2019-04-29 | 2019-05-01 | 2022-04-30 | 889998.99 |  | 7577001.01 | Yes
GLM068/2019 | MAHLORI DEVELOPMENT | Panel of town planning consultants for implementation of various projects | 8467000 | 2019-04-29 | 2019-05-01 | 2022-04-30 | 5192250 |  | 3274750 | Yes
GLM068/2019 | MATETE AND ASSOCIATES | Panel of town planning consultants for implementation of various projects | 8467000 | 2019-04-29 | 2019-05-01 | 2022-04-30 | 2763725 |  | 5703275 | Yes
GLM012/2020 | FIVE STAR TRADING ENTERPRISE | Auction of Municipal Assets for 2 Years | R0.0402 per BOQ | 2020-01-17 | [5 empty] | Yes | The rates are charged as per BOQ
GLM055/2019 | MATHAKALA TRADING | Low level bridge Ward 10 Motseketla | 370244 | 2020-01-17 | 2020-01-20 | 2020-06-30 | 358780.42 |  | 11463.58 | Yes
GLM059/2019 | MPHEPHU INVESTMENT (PTY) LTD | Low level bridge Ward 14 Lemondokop | 296490.7 | 2020-01-17 | 2020-01-20 | 2020-06-30 | 296487.24 |  | 3.46 | Yes
GLM062/2019 | TSWARAGANANG DEVELOPMENT | Low level bridge Ward 07 Seatlaleng and Mollong | 382513 | 2020-01-17 | 2020-01-20 | 2020-04-30 | 378490.3 |  | 4022.7 | Yes
GLM013/2020 | CAPOTEX TRADING ENTERPRISE cc | Modjadjiskloof LV Network Refurbishment | 2646612.72 | 2020-01-20 | 2020-02-20 | 2020-06-30 | 3127040.57 | 232166.6 | -248261.25 | Yes
GLM014/2020 | LEFAMAFA ELECTRICAL AND CONSTRUCTION | Upgrading of Doreen Street 11KV HT Overhead line | 1863623.3 | 2020-01-20 | 2020-02-20 | 2020-06-30 | 1623791.74 |  | 239831.56 | Yes
GLM016/2020 | TJM GREENTECH (PTY) LTD | Service provider to plan and implement Energy Efficiency Demand side Management (EEDSM) with Greater Letaba Local Muncipality | 3000106.66 | 2020-01-31 | 2020-01-31 | 2020-06-30 | 5000106.18 | 1999999.52 | 0 | Yes
GLM054/2019 | SAMWORTH CONSTRUCTION | Low level bridge Ward 17 Mamaila to Kolobetona | 375874.51 | 2020-01-17 | 2020-01-20 | 2020-04-20 | 352097.42 |  | 23777.09 | Yes
GLM060/2019 | MOLOTOTSI TRANSPORT AND CONSTRUCTION | Low level bridge Ward 22 Nakampe | 348769.3 | 2020-01-17 | 2020-01-20 | 2020-04-30 | 389533.13 | 41325 | 561.17 | Yes
GLM017/2020 | MUNSOFT PTY LTD | Appointment of proposal for integrated financial management and internal control system | 7949409.5 | 2020-02-21 | 2020-08-01 | 2023-07-30 | 4082142.9 |  | 3867266.6 | Yes
GLM008/2019 | MATSEKA CONSTRUCTION AND PROJECTS | Rehabilation of internal street (Uitzicht system) | 3000000 | 2020-02-20 | 2020-02-24 | 2020-06-30 | 3591801.02 | 591801.02 | 0 | Yes
GLM020/2020 | ANAKA GROUP | Rental of printers for 36 months | 4948447.61 | 2020-07-27 | 2020-09-01 | 2023-08-31 | 3312995.48 |  | 1635452.13 | Yes
GLM021/2020 | FIDELITY CASH SOLUTIONS | Provision of cash in transit for 36 months | 1284161.76 | 2020-09-01 | 2020-09-01 | 2023-08-31 | 321040.53 |  | 963121.23 | Yes
GLM018/2020 | MAHUMANI INCORPORATED | Panel of Legal Firms (6) for provision of legal services for a period of 36 months | R1170,00 per BOQ | 2020-10-06 | 2020-10-14 | 2023-10-14 |  |  |  | Yes | The rates are charged as per BOQ
GLM018/2020 | MOHALE INCORPORATED | Panel of Legal Firms (6) for provision of legal services for a period of 36 months | R1170,00 per BOQ | 2020-10-06 | 2020-10-14 | 2023-10-14 |  |  |  | Yes | The rates are charged as per BOQ
GLM018/2020 | MOSIRE TSIANE ATTORNEYS | Panel of Legal Firms (6) for provision of legal services for a period of 36 months | R1170,00 per BOQ | 2020-10-06 | 2020-10-14 | 2023-10-14 |  |  |  | Yes | The rates are charged as per BOQ
GLM018/2020 | MACHABA INC ATTORNEYS | Panel of Legal Firms (6) for provision of legal services for a period of 36 months | R1170,00 per BOQ | 2020-10-06 | 2020-10-14 | 2023-10-14 |  |  |  | Yes | The rates are charged as per BOQ
GLM018/2020 | FLIP COETZER INCORPORATED | Panel of Legal Firms (6) for provision of legal services for a period of 36 months | R1170,00 per BOQ | 2020-10-06 | 2020-10-14 | 2023-10-14 |  |  |  | Yes | The rates are charged as per BOQ
GLM018/2020 | MODJADJI RAPHESU INC ATTORNEYS | Panel of Legal Firms (6) for provision of legal services for a period of 36 months | R1170,00 per BOQ | 2020-10-06 | 2020-10-14 | 2023-10-14 |  |  |  | Yes | The rates are charged as per BOQ
GLM001/2021 | ZEVOFUSION (PTY) LTD | Supply and delivery of Backhoe Loader TLB | 1391500 | 2020-10-19 | 2020-10-26 | 2021-04-26 | 1391500 |  | 0 | Yes
GLM002/2021 | MONA EATING HOUSE BUSINESS ENTERPRISE | Supply and delivery of 6 Ton Tipper Truck (single differential Truck) | 1383747.6 | 2020-10-19 | 2020-10-26 | 2021-04-26 | 1383747.6 |  | 0 | Yes
GLM003/2021 | ITUMIRANDA (PTY) LTD | Supply and delivery of 1 Ton quarter canopy Truck | 728500 | 2020-10-19 | 2020-10-26 | 2021-04-26 | 728500 |  | 0 | Yes
GLM004/2021 | MOON AND EARTH TRADING AND PROJECTS 371 | Supply and delivery of 2 water tanker truck (single differential truck) | 2395900 | 2020-10-19 | 2020-10-26 | 2021-04-26 | 2395900 |  | 0 | Yes
GLM005/2021 | MOTSHITSHIRI TRADING | Supply and delivery of 4X4 single cab for workshop | 450000 | 2020-10-19 | 2020-10-26 | 2021-04-26 |  |  | 0 | Yes | Surrended
GLM006/2021 | LAYTONS PROJECTS (PTY) LTD | Supply and delivery of a self-propelled road sweeper | 490000 | 2020-10-20 | 2020-10-26 | 2021-04-26 |  |  | 0 | Yes | Surrended
GLM007/2021 | TRITASTAR (PTY) LTD JV ENDLANI CIVILS | Supply and delivery of Grader | 2972750 | 2020-11-25 | 2020-10-26 | 2021-04-26 |  |  | 0 | Yes | Surrended
GLM008/2021 | MORWAMAITE (PTY) LTD | Supply and delivery of cleaning materials for a period of 36 months | R66 972,00 per BOQ | 2020-10-05 | 2020-10-09 | 2023-10-09 |  |  |  | Yes | The rates are charged as per BOQ
GLM008/2021 | MAMOSHE INVESTMENT GROUP (PTY) LTD | Supply and delivery of cleaning materials for a period of 36 months | R66 972,00 per BOQ | 2020-10-05 | 2020-10-09 | 2023-10-09 |  |  |  | Yes | The rates are charged as per BOQ
GLM008/2021 | BOSESHOKA TRADING ENTERPRISE | Supply and delivery of cleaning materials for a period of 36 months | R66 972,00 per BOQ | 2020-10-05 | 2020-10-09 | 2023-10-09 |  |  |  | Yes | The rates are charged as per BOQ
GLM009/2021 | WARONA CONSULTING ENGINEERS | Planning, Design and Construction Supervision until Project Commissioning of Ramodumo Street Paving | 1150000 | 2020-11-25 | 2020-11-26 | 2023-10-26 | 1146833.31 |  | 3166.69 | Yes
GLM009/2021 | TM AFRICA ENGINEERING SERVICES | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 |  |  |  | Yes
GLM009/2021 | BATATISE CONSULTING ENGINEERS | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 |  |  |  | Yes
GLM009/2021 | NSUKU CONSULTING ENGINEERS | Planning, Design and Construction Supervision until Project Commissioning of Makhuthukwe Street Paving | 2767884.38 | 2020-11-25 | 2020-11-26 | 2023-10-26 | 1494926.77 |  | 1272957.61 | Yes
GLM009/2021 | BLACK CREED | Planning, Design and Construction Supervision until Project Commissioning of Sephukubje Street Paving | 3669859.01 | 2020-11-25 | 2020-11-26 | 2023-10-26 | 2589901.31 |  | 1079957.7 | Yes
GLM009/2021 | SHUMBA ENGINEERING SERVICES | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 |  |  |  | Yes
GLM009/2021 | MAJOR QUALITY | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 |  |  |  | Yes
GLM009/2021 | AES CONSULTING | Planning, Design and Construction Supervision until Project Commissioning of Rampepe Acess Bridge | 908771.93 | 2020-11-25 | 2020-11-26 | 2023-10-26 | 486154.57 |  | 422617.36 | Yes
GLM009/2021 | VCL COMSULTING ENGINEERS | Planning, Design and Construction Supervision until Project Commissioning of Senwamokgope Street Paving | 1000000 | 2020-11-25 | 2020-11-26 | 2023-10-26 | 998850 |  | 1150 | Yes
GLM009/2021 | IMPUMELELO CONSULTING | Planning, Design and Construction Supervision until Project Commissioning of Mamokgadi Street Paving | 1100000 | 2020-11-25 | 2020-11-26 | 2023-10-26 | 1101000 |  | -1000 | Yes
GLM009/2021 | VUXAKA CONSULTING ENGINEERS | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 |  |  |  | Yes
GLM009/2021 | MORULA CONSULTING ENGINEERS | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 |  |  |  | Yes
GLM009/2021 | SHAWENI CONSULTING ENGINEERS | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 |  |  |  | Yes
GLM009/2021 | T2-TECH ENGINNERS (PTY) LTD | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 |  |  |  | Yes
GLM009/2021 | MORWA CONSULTING ENGINEERS | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 |  |  |  | Yes
GLM009/2021 | DOLMEN ENGINEERS | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 |  |  |  | Yes
GLM009/2021 | LEPALATHABENI INVESTMENTS | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 |  |  |  | Yes
GLM009/2021 | MAPOXE CONSULTING ENGINEERS | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 |  |  |  | Yes
GLM009/2021 | CLEAR WATER CONSULTING ENGINEERS (PTY) LTD | Planning, Design and Construction Supervision until Project Commissioning of Meloding Stormwater Canal | 400000 | 2020-11-25 | 2020-11-26 | 2023-10-26 | 369550.21 |  | 30449.79 | Yes
GLM009/2021 | LAZWI ENGINEERING 16 CC | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 |  |  |  | Yes
GLM009/2021 | SKY HIGH CONSULTING ENGINEERS | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 |  |  |  | Yes
GLM009/2021 | KAGO CONSULTING ENGINEERS | Planning, Design and Construction Supervision until Project Commissioning of Ga-Kgapane New Cemetry | 1998461.65 | 2020-11-25 | 2020-11-26 | 2023-10-26 | 992377.66 |  | 1006083.99 | Yes
GLM009/2021 | MARUNGANE PROJECTS (PTY) LTD | Planning, Design and Construction Supervision until Project Commissioning of Abel Street Paving | 1149877.97 | 2020-11-25 | 2020-11-26 | 2023-10-26 | 1149877.97 |  | 0 | Yes
GLM009/2021 | TSHASHU CONSULTING AND PROJECTS MANAGERS | Design and Supervision of Raphahlelo/Phooko Street Paving | 3994804.76 | 2020-11-25 | 2020-11-26 | 2023-10-26 | 1267741.54 |  | 2727063.22 | Yes
GLM009/2021 | 2MC CONSULTING ENGINEERS | Design and Supoervision of Malematja Street Paving | 1150000 | 2020-11-25 | 2020-11-26 | 2023-10-26 | 1150000 |  | 0 | Yes
GLM009/2021 | HLAYELANI CONSULTING ENGINEERS | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 |  |  |  | Yes
GLM009/2021 | VUTANI CONSULTING SERVICES CC/NAPE MULTI PROFESSIONALS (PTY) LTD JV | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 |  |  |  | Yes
GLM009/2021 | KIPP CONSULTING ENGINEERS | Planning, Design and Construction Supervision until Project Commissioning of Mohlabaneng Street Paving | 4945240.01 | 2020-11-25 | 2020-11-26 | 2023-10-26 | 2101727 |  | 2843513.01 | Yes
GLM009/2021 | SADC PROJECTS CONSULTING (PTY) LTD JV ORBITALS TRADING | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 |  |  |  | Yes
GLM009/2021 | MOSOMO CONSULTING CIVIL ENGINEERS | Design and Supervision of Tshabela Matswale Street Paving | 2261005.64 | 2020-11-25 | 2020-11-26 | 2023-10-26 | 1307355.23 |  | 953650.41 | Yes
GLM011/2021 | RIVISI ELECTRICAL CONTRACTORS | Electrification of 6 villages at Ramatiti, Mohlabaneng,New castle, Taolome, Kobe/Khebefe & Hlobila-Paji | 6196000 | 2020-10-20 | 2020-11-01 | 2021-05-31 | 6196000 |  | 0 | Yes
GLM012/2021 | TJM GREENTECH | Appointment of a service provider to plan and implement Energy Efficiency Demand Side Management (EEDSM) for a period of 3 years | 3599294.31 | 2020-10-20 | 2020-11-01 | 2021-05-30 | 3599294.31 |  | 0 | Yes
GLM013/2021 | DIVENTIA INVESTMENTS (PTY) LTD | Supply and delivery of 60 laptops at Greater Letaba Municipality | 960059.1 | 2020-10-20 | 2020-10-24 | 2021-04-23 | 960059.1 |  | 0 | Yes
GLM014/2021 | SHIDILA TRADING ENTERPRISE | Panel of supplies for communication and events Management work for GLM for a period of 36 months | R1 029 480,00 per BOQ | 2020-11-25 | 2020-12-01 | 2023-11-30 |  |  |  | Yes | The rates are charged as per BOQ
GLM014/2021 | WHITE HALL TRADING AND PROJECTS 64 | Panel of supplies for communication and events Management work for GLM for a period of 36 months | R1 029 480,00 per BOQ | 2020-11-25 | 2020-12-01 | 2023-11-30 |  |  |  | Yes | The rates are charged as per BOQ
GLM014/2021 | MONA EATING HOUSE BUSINESS ENTERPRISE | Panel of supplies for communication and events Management work for GLM for a period of 36 months | R1 029 480,00 per BOQ | 2020-11-25 | 2020-12-01 | 2023-11-30 |  |  |  | Yes | The rates are charged as per BOQ
GLM014/2021 | MOLOGIRL TRADING ENTERPRISE AND PROJECTS | Panel of supplies for communication and events Management work for GLM for a period of 36 months | R1 029 480,00 per BOQ | 2020-11-25 | 2020-12-01 | 2023-11-30 |  |  |  | Yes | The rates are charged as per BOQ
GLM016/2021 | CATHU CONSULTING INC | Unbundling of Municipal Assets and complilation of GRAP compliance Asset register for a period of 36 months | 4884728.22 | 2020-11-25 | 2021-03-01 | 2023-02-28 | 402780.42 |  | 4481947.8 | Yes
GLM017/2021 | JEREMIAH T29 MANAGEMENT SERVICES JV LANDE CONSULTING INC | Provision of Advisory services within the Finance department of the Municipality for a period of 2 years | 3013500 | 2020-11-25 | 2021-03-01 | 2023-02-28 | 616500 |  | 2397000 | Yes
GLM010/2021 | RISIMA PROJECT MANAGEMENT | Ga-Kgapane Extension 12 (Mooiplaas 434-LT) Professional services for Electrical engineering Bulk Infrastructure | 1998179.99 | 2020-11-26 | 2020-11-26 | 2023-10-26 | 1240869.77 |  | 757310.22 | Yes
GLM010/2021 | SKOTANE DEVELOPMENT CONSULTANTS | Panel of Electrical Engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-26 | 2020-11-26 | 2023-10-26 |  |  | 0 | Yes
GLM010/2021 | A-M CONSULTING ENGINEERS | Panel of Electrical Engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-26 | 2020-11-26 | 2023-10-26 |  |  | 0 | Yes
GLM010/2021 | BATATISE CONSULTING ENGINEERS | Panel of Electrical Engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-26 | 2020-11-26 | 2023-10-26 |  |  | 0 | Yes
GLM010/2021 | VUXAKA CONSULTING ENGINEERS | Panel of Electrical Engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-26 | 2020-11-26 | 2023-10-26 |  |  | 0 | Yes
GLM010/2021 | SHUMBA ENGINEERING SERVICES | Panel of Electrical Engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-26 | 2020-11-26 | 2023-10-26 |  |  | 0 | Yes
GLM010/2021 | AES CONSULTING | Panel of Electrical Engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-26 | 2020-11-26 | 2023-10-26 |  |  | 0 | Yes
GLM010/2021 | MANE GROUP | Panel of Electrical Engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-26 | 2020-11-26 | 2023-10-26 |  |  | 0 | Yes
GLM010/2021 | MAJOR QUALITY INVESTMENT | Panel of Electrical Engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-26 | 2020-11-26 | 2023-10-26 |  |  | 0 | Yes
GLM010/2021 | MOGALEMOLE CONSULTING ENGINEERS | Panel of Electrical Engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-26 | 2020-11-26 | 2023-10-26 |  |  | 0 | Yes
GLM010/2021 | EMC ASSOCIATES | Panel of Electrical Engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-26 | 2020-11-26 | 2023-10-26 |  |  | 0 | Yes
GLM010/2021 | HI-END GROUP ELECTRICAL | Panel of Electrical Engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-26 | 2020-11-26 | 2023-10-26 |  |  | 0 | Yes
GLM021/2021 | PETRA INSTITUTE OF DEVELOPMENT (PTY) LTD | Municipal Finance Management Programme Training (MFMP) | 1996400 | 2021-01-28 | 2021-02-01 | 2021-08-31 | 1996400 |  | 0 | Yes
GLM018/2021 | MOLMAL TRADING | Supply and delivery of 30 X 6m3 Skip Bins | 990000 | 2021-02-01 | 2021-02-08 | 2021-08-08 | 990000 |  | 0 | Yes
GLM019/2021 | LIMPRO SECURITIES (PTY) LTD | Supply and delivery of T5,95 Tractor | 498982.56 | 2021-02-18 | 2021-02-25 | 2021-08-24 | 498982.56 |  | 0 | Yes
GLM020/2021 | PATM MECHENICAL AND ELECTRICAL CONTRACTORS | Panel for the supply and delivery of electrical spares for a period of 36 months | R7 806 503,47 per BOQ | 2021-02-19 | 2021-02-25 | 2024-02-24 |  |  |  | Yes | The rates are charged as per BOQ
GLM020/2021 | OTS ELECTRICAL | Panel for the supply and delivery of electrical spares for a period of 36 months | R7 806 503,47 per BOQ | 2021-02-19 | 2021-02-25 | 2024-02-24 |  |  |  | Yes | The rates are charged as per BOQ
GLM020/2021 | ROORIV CONSTRUCTION (PTY) LTD | Panel for the supply and delivery of electrical spares for a period of 36 months | R7 806 503,47 per BOQ | 2021-02-19 | 2021-02-25 | 2024-02-24 |  |  |  | Yes | The rates are charged as per BOQ
GLM022/2021 | PK FINANCIAL CONSULTANTS | Vat Recovery for a period of 36 months | 0.12 | 2021-02-19 | 2021-03-01 | 2024-02-28 |  |  |  | Yes | The rates are charged as per BOQ
GLM023/2021 | ZERO TWO FUEL DISTRIBUTORS | Supply and delivery of Diesel, Petrol and Oil for a period of 36 months | 1459.21 | 2021-03-23 | 2021-03-25 | 2024-02-24 |  |  |  | Yes | The rates are charged as per BOQ
GLM024/2021 | DIVENTIA INVESTMENTS (PTY) LTD | Supply and Delivery of mini ballie | 300000 | 2021-05-19 | 2021-05-26 | 2021-11-25 | 300000 |  | 0 | Yes
GLM025/2021 | MBHAZIMA HOLDINGS (PTY) LTD | Supply and install checkpoint firewall annual software license renewal with maintanence hours | 282814.79 | 2021-05-19 | 2021-05-26 | 2022-05-25 | 0 |  | 282814.79 | Yes
GLM029/2021 | KHATHOLA MOHALE (PTY) LTD | Installation of cubicles and bullet proof glass at Modjadjskool DLTC | 376399.2 | 2021-05-19 | 2021-05-26 | 2021-11-25 | 0 |  | 376399.2 | Yes
GLM030/2021 | LESELENG CIVIL WORKS AND SUPPLIES (PTY) LTD | Supply and Delivery of Two (2) Traffic Patrol Vehicles | 640000 | 2021-05-19 | 2021-05-26 | 2021-11-25 | 0 |  | 640000 | Yes
GLM009/2021/6-C | PERRIZIN HOMES CC | Ga-kgapane Cemetery | 12490385.3 | 2021-05-28 | 2021-06-14 | 2023-06-13 |  |  | 12490385.3 | Yes
GLM027/2021 | Moremasefoko Trading cc | Appointment of a Service Provider to Upgrading of LV Electricity Network to NERSA Standard | 800000 | 2021-05-28 | 2021-06-07 | 2021-12-06 | 0 |  | 800000 | Yes
GLM007/2021 | UTAH TRADING (PTY) LTD | Supply and Delivery of Grader | 4750000 | 2021-05-28 | 2021-06-07 | 2021-12-06 | 4750000 |  | 0 | Yes
GLM009/2021/1-C | LEBP CONSTRUCTION AND PROJECTS | Mohlabaneng Street Paving | 29089647.11 | 2021-06-03 | 2021-06-14 | 2023-06-13 | 1233109.44 |  | 27856537.67 | Yes
GLM009/2021/2-C | MAMOMAMA TRADING | Makhuthukwe Street Paving | 16281672.8 | 2021-06-04 | 2021-06-14 | 2023-06-13 | 1659208.5 |  | 14622464.3 | Yes
GLM009/2021/3-C | ZEVOFUSION (PTY) LTD JV DZUNGENI GROUP JV MACHABA TAU CONSTRUCTION | Raphahlelo/Phooko Street Paving | 23498851.55 | 2021-06-03 | 2021-06-14 | 2023-06-13 | 666666.67 |  | 22832184.88 | Yes
GLM009/2021/4-C | SELLO RAMOTHWALA CIVILS | Sephukubje Street Paving | 21763876.5 | 2021-06-03 | 2021-06-14 | 2023-06-13 | 1833191.54 |  | 19930684.96 | Yes
GLM009/2021/5-C | MATSEKA CONSTRUCTION AND PROJECTS CC | Tshabela Matswele Street Paving | 12690234.38 | 2021-06-02 | 2021-06-14 | 2023-06-13 | 995197.36 |  | 11695037.02 | Yes
GLM031/2021 | LESELENG CIVIL WORKS AND SUPPLIES (PTY) LTD | Supply and Delivery of Double Cab 4X4 Diesel Bakkie for Electrical | 800000 | 2021-06-11 | 2021-06-14 | 2021-12-13 | 0 |  | 800000 | Yes
GLM032/2021 | DITLOU GROUP ENTERPRISE | Supply and delivery of 4x2 double cab bakkie for plumbing | 759870 | 2021-06-11 | 2021-06-14 | 2021-12-13 | 0 |  | 759870 | Yes
GLM005/2021 | TTS LES HOLDINGS | Supply and Delivery of 4 X 4 Single Cab for Workshop | 797071 | 2021-06-11 | 2021-06-14 | 2021-12-13 | 0 |  | 797071 | Yes
GLM034/2021 | CS2M CONSTRUCTION AND PROJECTS (PTY) LTD | Supply and Delivery of Skip Truck | 1200000 | 2021-06-11 | 2021-06-14 | 2021-12-13 | 0 |  | 1200000 | Yes
GLM033/2021 | JAN ADELAIDE CONSTRUCTION AND SERVICES (PTY) LTD | Supply and Delivery of 20 X Notebook/Laptops | 345000 | 2021-06-11 | 2021-06-14 | 2021-12-13 | 0 |  | 345000 | Yes
Note on D15: Tsakani Mtebule: 2017/18 1 500 000.00 2018/19 1 700 532.21 2019/20 1 674 288.00
Note on E15: Tsakani Mtebule: Check SLA for dates. Advertise after July 2019
Note on D56: Tsakani Mtebule: 2018/19 5 593 206.00 2019/20 17 000 000.00 2020/21 18 297 201.81
Note on D64: Tsakani Mtebule: 2018/2019 600 000 2019/2020 700 000 2020/2021 700 000
Note on E64: Tsakani Mtebule: contract ends February 2022 Check dates SLA