## 2023-2024 REGISTER
CONTRACT REGISTER FOR THE PERIOD ENDING JUNE 2024
No. | Tender number | Service provider | Description | Amount R | Appointment date | Start date | End date | Expenditure to year end R | Variation amount R | Remaining contract amount R | SLA in place (Yes / No) | Comments
1 | GLM014/2022 | Nkomazi Lemetja JV | Construction of Buqa Low Level Bridge | 900378.55 | 2023-06-15 | 2023-07-01 | 2023-11-30 | Yes |  |  | Yes
2 | GLM014/2022 | Xalamuka Built Environment JV | Construction of Roerfontein Low Level Bridge | 847579.3 | 2023-06-27 | 2023-07-01 | 2023-11-30 | Yes |  |  | Yes
3 | GLM023/2023 | A New Awekening Trading cc | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
4 | GLM023/2023 | GPMVR Multi Projects | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
5 | GLM023/2023 | Moilalehlaka Investment (Pty) Ltd JV Phadu Holdings | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
6 | GLM023/2023 | Oramac Civil Construction | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
7 | GLM023/2023 | Afri Point Solutions (Pty) Ltd | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
8 | GLM023/2023 | Letsimane trading & Projects JV Bokamoso | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
9 | GLM023/2023 | Forshaken Construction cc | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
10 | GLM023/2023 | Leboneng North Investments | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
11 | GLM023/2023 | Chango Business Enterprise cc | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
12 | GLM023/2023 | Telgoplex (Pty) Ltd | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
13 | GLM023/2023 | Sunay Trading & Projects 240 cc | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
14 | GLM023/2023 | Basia ke Balobedu Holding | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
15 | GLM023/2023 | Bosvark Development (Pty) Ltd | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
16 | GLM023/2023 | Firm Early Constructions | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
17 | GLM023/2023 | Quintax 212 JV FJRIC Construction Projects | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
18 | GLM023/2023 | Kamela ya Tshwale | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
19 | GLM023/2023 | Mikat 8279 Trading | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
20 | GLM023/2023 | Nax Most Construction cc | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22

## RFQ 2023-2024
No. | RFQ number | Service provider | Description | Amount R | Appointment date | Order Number | Expenditure to year end R | Variation amount R | Remaining contract amount R | Comments
1 | RFQ001/2024 | Seboch Group (Pty) Ltd | Supply and Delivery of 5 Air Conditioners | 166132.9 | 2023-08-31 | 43141
2
3
4
5
6
7
8
9
10

## GLM CONTRACTS
CONTRACT REGISTER FOR THE PERIOD ENDING JUNE 2024
Tender number | Service provider | Description | Amount R | Appointment date | Start date | End date | SLA in place (Yes / No) | Comments
GLM011/2015PR | Uranus Consulting Engineers CC | Rottredam sports Complex | 5617383.08 | 2015-03-03 | 2015-03-03 | 2015-06-30 | Yes
GLM020/2016C | Bagaphala projects trading | Construction of Rotterdam sports complex | 32867352.69 | 2017-05-29 | 2017-06-19 | 2019-06-30 | Yes
GLM027/2016-PR | Uranus Consulting Engineers CC | Design and supervision of Ga-Kgapane Stadium phase 3 | 295043.9814 | 2017-03-15 | 2017-03-20 | 2017-06-30 | Yes
GLM027/2016C | Bagaphala projects trading | Construction of Ga-Kgapane Stadium-Phase 03 | 35001708.63 | 2017-10-20 | 2017-11-20 | 2020-11-21 | Yes
GLM019/2016-PR | Morula Consulting Engineers | Design & supervision for construction of Thakgalane sports Ground | 5446801.73 | 2017-03-23 | 2017-05-09 | 2017-06-30 | Yes
GLM015/2017c | Lazwi Engineering 16cc | Planning and designs for construction of ward 5 community halls | 1222598.93 | 2017-02-26 | 2017-06-19 | 2017-09-18 | Yes
GLM 005/2019 | Kipp Consulting Engineers | Planning, design and supervision of Jokong street paving | 4676355.33 | 2018-09-17 | 2018-09-20 | 2021-12-31 | Yes
GLM 019/2018 | Sello Ramothweala Civils CC/Beten JV | Thakgalane sports complex | 38308914.97 | 2018-09-06 | 2018-09-10 | 2021-03-10 | Yes
GLM 019/2016 | Maduke Trading (Pty) Ltd | Madumeleng/Shotong sports complex | 40890407.81 | 2018-09-06 | 2018-09-10 | 2021-03-10 | Yes
GLM018/2016-PR | T2-Tech Engineers (pty)Ltd | Design & supervision for construction of Madumeleng/shotong sports complex | 6011815.33 | 2017-02-28 | 2017-05-08 | 2017-06-30 | Yes
GLM005/2019C | LebP Construction | Construction of Jokong street paving | 30589812.01 | 2019-02-22 | 2019-04-01 | 31 June 2021 | Yes
GLM035/2019 | Burika ITC solution (Pty) Ltd | Supply, installation and training ITC | 746991.72 | 2019-04-16 | 2019-09-30 | 2022-09-30 | Yes
GLM029/2019 | FIRST NATIONAL BANK | PROVISION OF BANKING SERVICES OF GLM FOR 3 YEARS | R26161.08 per BOQ | 2019-04-30 | 2019-02-01 | 2024-01-31 | Yes | The rates are charged as per BOQ
GLM002/2016C | MADUKE TRADING | Construction of Itieleng Street Paving | 11740823.17 | 2019-08-01 | 2019-08-12 | 2021-06-30 | Yes
GLM005/2016C | AFRICAN STRATEGIC COOPERATION | Lemondokop Street Paving | 12896951.1 | 2019-11-27 | 2019-12-02 | 2021-06-30 | Yes
GLM015/2016C | NTSHIZAS TECHNICAL SERVICES | Ward 5 Community Hall | 7456464.28 | 2019-11-27 | 2019-12-04 | 2021-06-30 | Yes
GLM055/2019 | MATHAKALA TRADING | Low level bridge Ward 10 Motseketla | 370244 | 2020-01-17 | 2020-01-20 | 2020-06-30 | Yes
GLM059/2019 | MPHEPHU INVESTMENT (PTY) LTD | Low level bridge Ward 14 Lemondokop | 296490.7 | 2020-01-17 | 2020-01-20 | 2020-06-30 | Yes
GLM062/2019 | TSWARAGANANG DEVELOPMENT | Low level bridge Ward 07 Seatlaleng and Mollong | 382513 | 2020-01-17 | 2020-01-20 | 2020-04-30 | Yes
GLM054/2019 | SAMWORTH CONSTRUCTION | Low level bridge Ward 17 Mamaila to Kolobetona | 375874.51 | 2020-01-17 | 2020-01-20 | 2020-04-20 | Yes
GLM060/2019 | MOLOTOTSI TRANSPORT AND CONSTRUCTION | Low level bridge Ward 22 Nakampe | 348769.3 | 2020-01-17 | 2020-01-20 | 2020-04-30 | Yes
GLM017/2020 | MUNSOFT PTY LTD | Appointment of proposal for integrated financial management and internal control system | 7949409.5 | 2020-02-21 | 2020-08-01 | 2023-07-30 | Yes
GLM008/2019 | MATSEKA CONSTRUCTION AND PROJECTS | Rehabilation of internal street (Uitzicht system) | 3000000 | 2020-02-20 | 2020-02-24 | 2020-06-30 | Yes
GLM020/2020 | ANAKA GROUP | Rental of printers for 36 months | 4948447.61 | 2020-07-27 | 2020-09-01 | 2023-08-31 | Yes |  | Expired and extended on a month to month basis
GLM021/2020 | FIDELITY CASH SOLUTIONS | Provision of cash in transit for 36 months | 1284161.76 | 2020-09-01 | 2020-09-01 | 2023-08-31 | Yes |  | Expired and extended on a month to month basis
GLM018/2020 | MAHUMANI INCORPORATED | Panel of Legal Firms (6) for provision of legal services for a period of 36 months | R1170,00 per BOQ | 2020-10-06 | 2020-10-14 | 2023-10-14 | Yes | The rates are charged as per BOQ | Expired
GLM018/2020 | MOHALE INCORPORATED | Panel of Legal Firms (6) for provision of legal services for a period of 36 months | R1170,00 per BOQ | 2020-10-06 | 2020-10-14 | 2023-10-14 | Yes | The rates are charged as per BOQ | Expired
GLM018/2020 | MOSIRE TSIANE ATTORNEYS | Panel of Legal Firms (6) for provision of legal services for a period of 36 months | R1170,00 per BOQ | 2020-10-06 | 2020-10-14 | 2023-10-14 | Yes | The rates are charged as per BOQ | Expired
GLM018/2020 | MACHABA INC ATTORNEYS | Panel of Legal Firms (6) for provision of legal services for a period of 36 months | R1170,00 per BOQ | 2020-10-06 | 2020-10-14 | 2023-10-14 | Yes | The rates are charged as per BOQ | Expired
GLM018/2020 | FLIP COETZER INCORPORATED | Panel of Legal Firms (6) for provision of legal services for a period of 36 months | R1170,00 per BOQ | 2020-10-06 | 2020-10-14 | 2023-10-14 | Yes | The rates are charged as per BOQ | Expired
GLM018/2020 | MODJADJI RAPHESU INC ATTORNEYS | Panel of Legal Firms (6) for provision of legal services for a period of 36 months | R1170,00 per BOQ | 2020-10-06 | 2020-10-14 | 2023-10-14 | Yes | The rates are charged as per BOQ | Expired
GLM008/2021 | MORWAMAITE (PTY) LTD | Supply and delivery of cleaning materials for a period of 36 months | R66 972,00 per BOQ | 2020-10-05 | 2020-10-09 | 2023-10-09 | Yes | The rates are charged as per BOQ | Expired
GLM008/2021 | MAMOSHE INVESTMENT GROUP (PTY) LTD | Supply and delivery of cleaning materials for a period of 36 months | R66 972,00 per BOQ | 2020-10-05 | 2020-10-09 | 2023-10-09 | Yes | The rates are charged as per BOQ | Expired
GLM008/2021 | BOSESHOKA TRADING ENTERPRISE | Supply and delivery of cleaning materials for a period of 36 months | R66 972,00 per BOQ | 2020-10-05 | 2020-10-09 | 2023-10-09 | Yes | The rates are charged as per BOQ | Expired
GLM009/2021 | WARONA CONSULTING ENGINEERS | Planning, Design and Construction Supervision until Project Commissioning of Ramodumo Street Paving | 1150000 | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | TM AFRICA ENGINEERING SERVICES | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | BATATISE CONSULTING ENGINEERS | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | NSUKU CONSULTING ENGINEERS | Planning, Design and Construction Supervision until Project Commissioning of Makhuthukwe Street Paving | 2767884.38 | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | BLACK CREED | Planning, Design and Construction Supervision until Project Commissioning of Sephukubje Street Paving | 3669859.01 | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | SHUMBA ENGINEERING SERVICES | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | MAJOR QUALITY | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | AES CONSULTING | Planning, Design and Construction Supervision until Project Commissioning of Rampepe Acess Bridge | 908771.93 | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | VCL COMSULTING ENGINEERS | Planning, Design and Construction Supervision until Project Commissioning of Senwamokgope Street Paving | 1000000 | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | IMPUMELELO CONSULTING | Planning, Design and Construction Supervision until Project Commissioning of Mamokgadi Street Paving | 1100000 | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | VUXAKA CONSULTING ENGINEERS | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | MORULA CONSULTING ENGINEERS | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | SHAWENI CONSULTING ENGINEERS | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | T2-TECH ENGINNERS (PTY) LTD | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | MORWA CONSULTING ENGINEERS | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | DOLMEN ENGINEERS | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | LEPALATHABENI INVESTMENTS | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | MAPOXE CONSULTING ENGINEERS | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | CLEAR WATER CONSULTING ENGINEERS (PTY) LTD | Planning, Design and Construction Supervision until Project Commissioning of Meloding Stormwater Canal | 400000 | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | LAZWI ENGINEERING 16 CC | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | SKY HIGH CONSULTING ENGINEERS | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | KAGO CONSULTING ENGINEERS | Planning, Design and Construction Supervision until Project Commissioning of Ga-Kgapane New Cemetry | 1998461.65 | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | MARUNGANE PROJECTS (PTY) LTD | Planning, Design and Construction Supervision until Project Commissioning of Abel Street Paving | 1149877.97 | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | TSHASHU CONSULTING AND PROJECTS MANAGERS | Design and Supervision of Raphahlelo/Phooko Street Paving | 3994804.76 | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | 2MC CONSULTING ENGINEERS | Design and Supoervision of Malematja Street Paving | 1150000 | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | HLAYELANI CONSULTING ENGINEERS | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | VUTANI CONSULTING SERVICES CC/NAPE MULTI PROFESSIONALS (PTY) LTD JV | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | KIPP CONSULTING ENGINEERS | Planning, Design and Construction Supervision until Project Commissioning of Mohlabaneng Street Paving | 4945240.01 | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | SADC PROJECTS CONSULTING (PTY) LTD JV ORBITALS TRADING | Panel of civil engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM009/2021 | MOSOMO CONSULTING CIVIL ENGINEERS | Design and Supervision of Tshabela Matswale Street Paving | 2261005.64 | 2020-11-25 | 2020-11-26 | 2023-10-26 | Yes
GLM011/2021 | RIVISI ELECTRICAL CONTRACTORS | Electrification of 6 villages at Ramatiti, Mohlabaneng,New castle, Taolome, Kobe/Khebefe & Hlobila-Paji | 6196000 | 2020-10-20 | 2020-11-01 | 2021-05-31 | Yes
GLM012/2021 | TJM GREENTECH | Appointment of a service provider to plan and implement Energy Efficiency Demand Side Management (EEDSM) for a period of 3 years | 3599294.31 | 2020-10-20 | 2020-11-01 | 2021-05-30 | Yes
GLM014/2021 | SHIDILA TRADING ENTERPRISE | Panel of supplies for communication and events Management work for GLM for a period of 36 months | R1 029 480,00 per BOQ | 2020-11-25 | 2020-12-01 | 2023-11-30 | Yes | The rates are charged as per BOQ
GLM014/2021 | WHITE HALL TRADING AND PROJECTS 64 | Panel of supplies for communication and events Management work for GLM for a period of 36 months | R1 029 480,00 per BOQ | 2020-11-25 | 2020-12-01 | 2023-11-30 | Yes | The rates are charged as per BOQ
GLM014/2021 | MONA EATING HOUSE BUSINESS ENTERPRISE | Panel of supplies for communication and events Management work for GLM for a period of 36 months | R1 029 480,00 per BOQ | 2020-11-25 | 2020-12-01 | 2023-11-30 | Yes | The rates are charged as per BOQ
GLM014/2021 | DINEO TSA BOTSHELO | Panel of supplies for communication and events Management work for GLM for a period of 36 months | R1 029 480,00 per BOQ | 2020-11-25 | 2020-12-01 | 2023-11-30 | Yes | The rates are charged as per BOQ
GLM016/2021 | CATHU CONSULTING INC | Unbundling of Municipal Assets and complilation of GRAP compliance Asset register for a period of 36 months | 4884728.22 | 2020-11-25 | 2021-03-01 | 2024-02-28 | Yes
GLM010/2021 | RISIMA PROJECT MANAGEMENT | Ga-Kgapane Extension 12 (Mooiplaas 434-LT) Professional services for Electrical engineering Bulk Infrastructure | 1998179.99 | 2020-11-26 | 2020-11-26 | 2023-10-26 | Yes
GLM010/2021 | SKOTANE DEVELOPMENT CONSULTANTS | Panel of Electrical Engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-26 | 2020-11-26 | 2023-10-26 | Yes
GLM010/2021 | A-M CONSULTING ENGINEERS | Panel of Electrical Engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-26 | 2020-11-26 | 2023-10-26 | Yes
GLM010/2021 | BATATISE CONSULTING ENGINEERS | Panel of Electrical Engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-26 | 2020-11-26 | 2023-10-26 | Yes
GLM010/2021 | VUXAKA CONSULTING ENGINEERS | Panel of Electrical Engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-26 | 2020-11-26 | 2023-10-26 | Yes
GLM010/2021 | SHUMBA ENGINEERING SERVICES | Panel of Electrical Engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-26 | 2020-11-26 | 2023-10-26 | Yes
GLM010/2021 | AES CONSULTING | Panel of Electrical Engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-26 | 2020-11-26 | 2023-10-26 | Yes
GLM010/2021 | MANE GROUP | Panel of Electrical Engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-26 | 2020-11-26 | 2023-10-26 | Yes
GLM010/2021 | MAJOR QUALITY INVESTMENT | Panel of Electrical Engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-26 | 2020-11-26 | 2023-10-26 | Yes
GLM010/2021 | MOGALEMOLE CONSULTING ENGINEERS | Panel of Electrical Engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-26 | 2020-11-26 | 2023-10-26 | Yes
GLM010/2021 | EMC ASSOCIATES | Panel of Electrical Engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-26 | 2020-11-26 | 2023-10-26 | Yes
GLM010/2021 | HI-END GROUP ELECTRICAL | Panel of Electrical Engineering services for rendering professional services on as and when required basis for a period of 3 years |  | 2020-11-26 | 2020-11-26 | 2023-10-26 | Yes
GLM020/2021 | PATM MECHENICAL AND ELECTRICAL CONTRACTORS | Panel for the supply and delivery of electrical spares for a period of 36 months | R7 806 503,47 per BOQ | 2021-02-19 | 2021-02-25 | 2024-02-24 | Yes | The rates are charged as per BOQ
GLM020/2021 | OTS ELECTRICAL | Panel for the supply and delivery of electrical spares for a period of 36 months | R7 806 503,47 per BOQ | 2021-02-19 | 2021-02-25 | 2024-02-24 | Yes | The rates are charged as per BOQ
GLM020/2021 | ROORIV CONSTRUCTION (PTY) LTD | Panel for the supply and delivery of electrical spares for a period of 36 months | R7 806 503,47 per BOQ | 2021-02-19 | 2021-02-25 | 2024-02-24 | Yes | The rates are charged as per BOQ
GLM023/2021 | ZERO TWO FUEL DISTRIBUTORS | Supply and delivery of Diesel, Petrol and Oil for a period of 36 months | 1459.21 | 2021-03-23 | 2021-03-25 | 2024-02-24 | Yes | The rates are charged as per BOQ
GLM009/2021/6-C | PERRIZIN HOMES CC | Ga-kgapane Cemetery | 12490385.3 | 2021-05-28 | 2021-06-14 | 2023-06-13 | Yes
GLM009/2021/1-C | LEBP CONSTRUCTION AND PROJECTS | Mohlabaneng Street Paving | 29089647.11 | 2021-06-03 | 2021-06-14 | 2023-06-13 | Yes
GLM009/2021/2-C | MAMOMAMA TRADING | Makhuthukwe Street Paving | 16281672.8 | 2021-06-04 | 2021-06-14 | 2023-06-13 | Yes
GLM009/2021/3-C | ZEVOFUSION (PTY) LTD JV DZUNGENI GROUP JV MACHABA TAU CONSTRUCTION | Raphahlelo/Phooko Street Paving | 23498851.55 | 2021-06-03 | 2021-06-14 | 2023-06-13 | Yes
GLM009/2021/4-C | SELLO RAMOTHWALA CIVILS | Sephukubje Street Paving | 21763876.5 | 2021-06-03 | 2021-06-14 | 2023-06-13 | Yes
GLM009/2021/5-C | MATSEKA CONSTRUCTION AND PROJECTS CC | Tshabela Matswele Street Paving | 12690234.38 | 2021-06-02 | 2021-06-14 | 2023-06-13 | Yes
GLM035/2021 | KUNENE MAKOPO RISK SOLUTION | PROVISION OF INSURANCE SERVICES AT GLM FOR A PERIOD OF 36 MONTHS | 612350 | 2021-07-29 | 2021-08-01 | 2024-07-31 | Yes | The rates are charged as per BOQ
GLM001/2022 | MADZ ELECTRICAL | ELECTRIFICATION OF FIVE VILLAGES AT KHUDUTHAMAGA, LAS VEGAS, MAMOKGADI, SEKGOPO MABOKE AND SHAMFANA | 16509522.36 | 2021-12-01 | 2021-12-13 | 2023-12-12 | Yes
GLM005/2022 | TELGOPLEX (PTY) LTD | CONSTRUCTION OF PHOOKO LOW LEVEL BRIDGE | 2424490.75 | 2021-12-02 | 2021-12-07 | 2022-06-06 | Yes
GLM006/2022 | GPMVR MULTI PROJECTS | MELODING STORMWATER CANAL | 8598516.57 | 2021-12-02 | 2021-12-07 | 2022-06-06 | Yes
GLM007/2022 | SARATHI TRADING ENTERPRISE JV OTS ELECTRICAL | SUPPLY, DELIVERY AND INSTALLATION OF TWO (2) HIGHMAST LIGHTS | 749950 | 2021-12-03 | 2021-12-06 | 2022-06-05 | Yes
GLM003/2022 | LERA 2 TRADING | BEAUTIFICATION OF MODJADJISKLOOF TOWN ENTRANCE | 2735372.5 | 2021-12-08 | 2021-12-13 | 2022-06-13 | Yes
GLM008/2022 | KOPANEGO TRAVEL | PANEL OF SERVICE PROVIDERS RENDERING A SERVICE IN RESPECT OF TRAVEL AGENCY FOR AIR TRAVEL AND ACCOMODATION ARRANGEMENTS TO THE GLM OFFICIALS FOR A PERIOD OF 36 MONTHS | 18% | 2021-12-09 | 2021-12-14 | 2024-12-13 | Yes
GLM008/2022 | PHETHO TRAVEL | PANEL OF SERVICE PROVIDERS RENDERING A SERVICE IN RESPECT OF TRAVEL AGENCY FOR AIR TRAVEL AND ACCOMODATION ARRANGEMENTS TO THE GLM OFFICIALS FOR A PERIOD OF 36 MONTHS | 25% | 2021-12-09 | 2021-12-14 | 2024-12-13 | Yes
GLM008/2022 | QUANTUM LEAP TRAVEL | PANEL OF SERVICE PROVIDERS RENDERING A SERVICE IN RESPECT OF TRAVEL AGENCY FOR AIR TRAVEL AND ACCOMODATION ARRANGEMENTS TO THE GLM OFFICIALS FOR A PERIOD OF 36 MONTHS | 25% | 2021-12-09 | 2021-12-14 | 2024-12-13 | Yes
GLM008/2022 | REAKGONA TRAVEL SERVICES | PANEL OF SERVICE PROVIDERS RENDERING A SERVICE IN RESPECT OF TRAVEL AGENCY FOR AIR TRAVEL AND ACCOMODATION ARRANGEMENTS TO THE GLM OFFICIALS FOR A PERIOD OF 36 MONTHS | 25% | 2021-12-09 | 2021-12-14 | 2024-12-13 | Yes
GLM002/2022 | FNM SECURITY SERVICES | PANEL OF SERVICE PROVIDERS FOR DE-BUSHING AND MAINTENANCE OF GLM FACILITIES FOR A PERIOD OF 36 MONTHS | 99100 | 2021-12-09 | 2021-12-14 | 2024-12-13 | Yes | The rates are charged as per BOQ
GLM002/2022 | MMATSHEPE HOLDINGS (PTY) LTD | PANEL OF SERVICE PROVIDERS FOR DE-BUSHING AND MAINTENANCE OF GLM FACILITIES FOR A PERIOD OF 36 MONTHS | 99100 | 2021-12-09 | 2021-12-14 | 2024-12-13 | Yes | The rates are charged as per BOQ
GLM002/2022 | PHAREPHARE SECURITY SERVICES | PANEL OF SERVICE PROVIDERS FOR DE-BUSHING AND MAINTENANCE OF GLM FACILITIES FOR A PERIOD OF 36 MONTHS | 99100 | 2021-12-09 | 2021-12-14 | 2024-12-13 | Yes | The rates are charged as per BOQ
GLM002/2022 | LEBONENG NORTH INVESTMENT | PANEL OF SERVICE PROVIDERS FOR DE-BUSHING AND MAINTENANCE OF GLM FACILITIES FOR A PERIOD OF 36 MONTHS | 99100 | 2021-12-09 | 2021-12-14 | 2024-12-13 | Yes | The rates are charged as per BOQ
GLM002/2022 | MABOROTHO TRADING | PANEL OF SERVICE PROVIDERS FOR DE-BUSHING AND MAINTENANCE OF GLM FACILITIES FOR A PERIOD OF 36 MONTHS | 99100 | 2021-12-09 | 2021-12-14 | 2024-12-13 | Yes | The rates are charged as per BOQ
GLM002/2022 | KHATHOLA MOHALE (PTY) LTD | PANEL OF SERVICE PROVIDERS FOR DE-BUSHING AND MAINTENANCE OF GLM FACILITIES FOR A PERIOD OF 36 MONTHS | 99100 | 2021-12-09 | 2021-12-14 | 2024-12-13 | Yes | The rates are charged as per BOQ
GLM002/2022 | MOD J PROJECTS & INVESTMENTS | PANEL OF SERVICE PROVIDERS FOR DE-BUSHING AND MAINTENANCE OF GLM FACILITIES FOR A PERIOD OF 36 MONTHS | 99100 | 2021-12-09 | 2021-12-14 | 2024-12-13 | Yes | The rates are charged as per BOQ
GLM002/2022 | KINGBEE TECHNOLOGIES | PANEL OF SERVICE PROVIDERS FOR DE-BUSHING AND MAINTENANCE OF GLM FACILITIES FOR A PERIOD OF 36 MONTHS | 99100 | 2021-12-09 | 2021-12-14 | 2024-12-13 | Yes | The rates are charged as per BOQ
GLM002/2022 | M4 PROJECTS | PANEL OF SERVICE PROVIDERS FOR DE-BUSHING AND MAINTENANCE OF GLM FACILITIES FOR A PERIOD OF 36 MONTHS | 88750 | 2021-12-09 | 2021-12-14 | 2024-12-13 | Yes | The rates are charged as per BOQ
GLM004/2022 | TSOGA MAMOKGOPO TRADING AND PROJECTS | SUPPLY AND DELIVERYOF 2200 X 240 LITRE WHEELED REFUSE CONTAINERS | 1758 | 2021-12-09 | 2021-12-14 | 2022-06-30 | Yes | The rates are charged as per BOQ
GLM004/2022 | ALJ STORE | SUPPLY AND DELIVERYOF 2200 X 240 LITRE WHEELED REFUSE CONTAINERS | 1600 | 2021-12-09 | 2021-12-14 | 2022-06-30 | Yes | The rates are charged as per BOQ
GLM004/2022 | LEMETJA CIVILS | SUPPLY AND DELIVERYOF 2200 X 240 LITRE WHEELED REFUSE CONTAINERS | 1362.75 | 2021-12-09 | 2021-12-14 | 2022-06-30 | Yes | The rates are charged as per BOQ
GLM004/2022 | MABOROTHO TRADING | SUPPLY AND DELIVERYOF 2200 X 240 LITRE WHEELED REFUSE CONTAINERS | 1758 | 2021-12-09 | 2021-12-14 | 2022-06-30 | Yes | The rates are charged as per BOQ
GLM004/2022 | NWATASI BUSINESS | SUPPLY AND DELIVERYOF 2200 X 240 LITRE WHEELED REFUSE CONTAINERS | 1758 | 2021-12-09 | 2021-12-14 | 2022-06-30 | Yes | The rates are charged as per BOQ
GLM004/2022 | PHADU HOLDINGS | SUPPLY AND DELIVERYOF 2200 X 240 LITRE WHEELED REFUSE CONTAINERS | 1758 | 2021-12-09 | 2021-12-14 | 2022-06-30 | Yes | The rates are charged as per BOQ
GLM013/2022 | TZANEEN AFRI INVESTMENT (PTY) LTD | CONSTRUCTION OF RAMPEPE ACCESS BRIDGE FOR GREATER LETABA MUNICIPALITY | 8754765.38 | 2022-02-28 | 2022-04-11 | 2022-10-31 | Yes
GLM012/2022 | MARTMOL TRADING | CONSTRUCTION OF MAMOKGADI STREET PAVING | 18017269.55 | 2022-02-25 | 2022-04-01 | 2022-10-31 | Yes
GLM014/2022 | TEMPE TRADING AND PROJECT | PROCUREMENT OF TWENTT (20) PANEL SERVICES PROVIDERS FOR PREVENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROADS TO BE APPIONTED ON AN AS AND WHEN REQUIRED BASIS FOR THE PERIOD OF THREE (03) YEARS | R192,136,19 | 2022-03-30 | 2022-04-04 | 2025-04-03 | Yes | The rates are charged as per BOQ
GLM014/2022 | SARATHI TRADING ENTERPRISE | PROCUREMENT OF TWENTT (20) PANEL SERVICES PROVIDERS FOR PREVENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROADS TO BE APPIONTED ON AN AS AND WHEN REQUIRED BASIS FOR THE PERIOD OF THREE (03) YEARS | R192,136,19 | 2022-03-30 | 2022-04-04 | 2025-04-03 | Yes | The rates are charged as per BOQ
GLM014/2022 | PHAREPHARE CONSTRUCTION | PROCUREMENT OF TWENTT (20) PANEL SERVICES PROVIDERS FOR PREVENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROADS TO BE APPIONTED ON AN AS AND WHEN REQUIRED BASIS FOR THE PERIOD OF THREE (03) YEARS | R192,136,19 | 2022-03-30 | 2022-04-04 | 2025-04-03 | Yes | The rates are charged as per BOQ
GLM014/2022 | PERRIZIN HOMES | PROCUREMENT OF TWENTT (20) PANEL SERVICES PROVIDERS FOR PREVENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROADS TO BE APPIONTED ON AN AS AND WHEN REQUIRED BASIS FOR THE PERIOD OF THREE (03) YEARS | R192,136,19 | 2022-03-30 | 2022-04-04 | 2025-04-03 | Yes | The rates are charged as per BOQ
GLM014/2022 | NKUMANI MULTI PROJECTS (Pty) Ltd | PROCUREMENT OF TWENTT (20) PANEL SERVICES PROVIDERS FOR PREVENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROADS TO BE APPIONTED ON AN AS AND WHEN REQUIRED BASIS FOR THE PERIOD OF THREE (03) YEARS | R192,136,19 | 2022-03-30 | 2022-04-04 | 2025-04-03 | Yes | The rates are charged as per BOQ
GLM014/2022 | NKOMAZI LEMETJA JV | PROCUREMENT OF TWENTT (20) PANEL SERVICES PROVIDERS FOR PREVENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROADS TO BE APPIONTED ON AN AS AND WHEN REQUIRED BASIS FOR THE PERIOD OF THREE (03) YEARS | R192,136,19 | 2022-03-30 | 2022-04-04 | 2025-04-03 | Yes | The rates are charged as per BOQ
GLM014/2022 | MOTHIKENI INVESTMENTS | PROCUREMENT OF TWENTT (20) PANEL SERVICES PROVIDERS FOR PREVENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROADS TO BE APPIONTED ON AN AS AND WHEN REQUIRED BASIS FOR THE PERIOD OF THREE (03) YEARS | R192,136,19 | 2022-03-30 | 2022-04-04 | 2025-04-03 | Yes | The rates are charged as per BOQ
GLM014/2022 | MATHPOWER TRADING AND PROJECTS (Pty)Ltd | PROCUREMENT OF TWENTT (20) PANEL SERVICES PROVIDERS FOR PREVENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROADS TO BE APPIONTED ON AN AS AND WHEN REQUIRED BASIS FOR THE PERIOD OF THREE (03) YEARS | R192,136,19 | 2022-03-30 | 2022-04-04 | 2025-04-03 | Yes | The rates are charged as per BOQ
GLM014/2022 | MARTMOL TRADING | PROCUREMENT OF TWENTT (20) PANEL SERVICES PROVIDERS FOR PREVENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROADS TO BE APPIONTED ON AN AS AND WHEN REQUIRED BASIS FOR THE PERIOD OF THREE (03) YEARS | R192,136,19 | 2022-03-30 | 2022-04-04 | 2025-04-03 | Yes | The rates are charged as per BOQ
GLM014/2022 | MAEKU'S (Pty)Ltd | PROCUREMENT OF TWENTT (20) PANEL SERVICES PROVIDERS FOR PREVENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROADS TO BE APPIONTED ON AN AS AND WHEN REQUIRED BASIS FOR THE PERIOD OF THREE (03) YEARS | R192,136,19 | 2022-03-30 | 2022-04-04 | 2025-04-03 | Yes | The rates are charged as per BOQ
GLM014/2022 | LESWIKA ROADS | PROCUREMENT OF TWENTT (20) PANEL SERVICES PROVIDERS FOR PREVENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROADS TO BE APPIONTED ON AN AS AND WHEN REQUIRED BASIS FOR THE PERIOD OF THREE (03) YEARS | R164,580,00 | 2022-03-30 | 2022-04-04 | 2025-04-03 | Yes | The rates are charged as per BOQ
GLM014/2022 | GROUP 33 CIVIL CONSTRACTOR (Pty) Ltd | PROCUREMENT OF TWENTT (20) PANEL SERVICES PROVIDERS FOR PREVENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROADS TO BE APPIONTED ON AN AS AND WHEN REQUIRED BASIS FOR THE PERIOD OF THREE (03) YEARS | R192,136,19 | 2022-03-30 | 2022-04-04 | 2025-04-03 | Yes | The rates are charged as per BOQ
GLM014/2022 | GPMVR MULTI PROJECTS | PROCUREMENT OF TWENTT (20) PANEL SERVICES PROVIDERS FOR PREVENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROADS TO BE APPIONTED ON AN AS AND WHEN REQUIRED BASIS FOR THE PERIOD OF THREE (03) YEARS | R192,136,19 | 2022-03-30 | 2022-04-04 | 2025-04-03 | Yes | The rates are charged as per BOQ
GLM014/2022 | FJRIC CONTRUCTION AND PROJECTS | PROCUREMENT OF TWENTT (20) PANEL SERVICES PROVIDERS FOR PREVENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROADS TO BE APPIONTED ON AN AS AND WHEN REQUIRED BASIS FOR THE PERIOD OF THREE (03) YEARS | R192,136,19 | 2022-03-30 | 2022-04-04 | 2025-04-03 | Yes | The rates are charged as per BOQ
GLM014/2022 | DOUBLE HOT SPOT | PROCUREMENT OF TWENTT (20) PANEL SERVICES PROVIDERS FOR PREVENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROADS TO BE APPIONTED ON AN AS AND WHEN REQUIRED BASIS FOR THE PERIOD OF THREE (03) YEARS | R192,136,19 | 2022-03-30 | 2022-04-04 | 2025-04-03 | Yes | The rates are charged as per BOQ
GLM014/2022 | BTECH CONSULTING JV EASYTECH | PROCUREMENT OF TWENTT (20) PANEL SERVICES PROVIDERS FOR PREVENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROADS TO BE APPIONTED ON AN AS AND WHEN REQUIRED BASIS FOR THE PERIOD OF THREE (03) YEARS | R192,136,19 | 2022-03-30 | 2022-04-04 | 2025-04-03 | Yes | The rates are charged as per BOQ
GLM014/2022 | BILMOD TRADING AND CONTRUCTION | PROCUREMENT OF TWENTT (20) PANEL SERVICES PROVIDERS FOR PREVENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROADS TO BE APPIONTED ON AN AS AND WHEN REQUIRED BASIS FOR THE PERIOD OF THREE (03) YEARS | R192,136,19 | 2022-03-30 | 2022-04-04 | 2025-04-03 | Yes | The rates are charged as per BOQ
GLM014/2022 | BROOKLYN PROJECTS 21 | PROCUREMENT OF TWENTT (20) PANEL SERVICES PROVIDERS FOR PREVENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROADS TO BE APPIONTED ON AN AS AND WHEN REQUIRED BASIS FOR THE PERIOD OF THREE (03) YEARS | R192,136,19 | 2022-03-30 | 2022-04-04 | 2025-04-03 | Yes | The rates are charged as per BOQ
GLM014/2022 | XALAMUKA BUILT ENVIRONMENT JV | PROCUREMENT OF TWENTT (20) PANEL SERVICES PROVIDERS FOR PREVENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROADS TO BE APPIONTED ON AN AS AND WHEN REQUIRED BASIS FOR THE PERIOD OF THREE (03) YEARS | R190,193,33 | 2022-03-30 | 2022-04-04 | 2025-04-03 | Yes | The rates are charged as per BOQ
GLM014/2022 | CARPUS CONSTRUCTION AND PROJECTS | PROCUREMENT OF TWENTT (20) PANEL SERVICES PROVIDERS FOR PREVENTATIVE MAINTENANCE OF GRAVEL AND SURFACED ROADS TO BE APPIONTED ON AN AS AND WHEN REQUIRED BASIS FOR THE PERIOD OF THREE (03) YEARS | R192,136,19 | 2022-03-30 | 2022-04-04 | 2025-04-03 | Yes | The rates are charged as per BOQ
GLM017/2022 | Makoma Violet Business Enterprise (Pty) Ltd | Panel of service providers rendering a service in respect of panel of four of fitting of tyres and battery for municipal vehicles for a period of 36 months | 432917 | 2022-07-21 | 2022-07-29 | 2025-07-28 | Yes | The rates are charged as per BOQ
GLM017/2022 | Molototsi Tyres and spares (Pty) Ltd | Panel of service providers rendering a service in respect of panel of four of fitting of tyres and battery for municipal vehicles for a period of 36 months | 432917 | 2022-07-21 | 2022-07-29 | 2025-07-28 | Yes | The rates are charged as per BOQ
GLM017/2022 | Kingbee Technology (Pty) Ltd | Panel of service providers rendering a service in respect of panel of four of fitting of tyres and battery for municipal vehicles for a period of 36 months | 432917 | 2022-07-21 | 2022-07-29 | 2025-07-28 | Yes | The rates are charged as per BOQ
GLM017/2022 | Mod J Projects (Pty) Ltd | Panel of service providers rendering a service in respect of panel of four of fitting of tyres and battery for municipal vehicles for a period of 36 months | 432917 | 2022-07-21 | 2022-07-29 | 2025-07-28 | Yes | The rates are charged as per BOQ
GLM003/2023 | GPMVR Multi Projects cc JV Mothikeni Investments (Pty) Ltd | Construction of Ramodumo Street Paving | 29251034.82 | 2022-09-07 | 2022-09-19 | 2025-09-18 | Yes
GLM020/2022 | Ntirano (PTY) LTD | Auction of Municipal Assets for a period of 36 months | 10.5% | 2022-09-20 | 2022-10-01 | 2025-09-30 | Yes | The rates are charged as per BOQ
GLM002/2023 | Mod Hope Properties cc | Complilation and maintanance of the General Valuation roll supplementary valuation and related services for a period of five (5) years | 1500175 | 2022-09-20 | 2022-10-01 | 2027-09-30 | Yes
GLM007/2023 | Martmol Trading cc | Construction of Motsinoni Street Paving | 17630551.85 | 2022-09-22 | 2022-10-01 | 2025-09-30 | Yes
GLM008/2023 | Double Hot Spot (Pty) LTD | Construction of Thibeni Street Paving | 19053477.7 | 2022-09-22 | 2022-10-01 | 2025-09-30 | Yes
GLM011/2022 | Ice Cloud SA | Online Electric Vending System and third-party vending for a period of 36 months. | 2.875% | 2022-09-22 | 2022-10-01 | 2025-09-30 | Yes | The rates are charged as per BOQ
GLM018/2022 | Tshumisano Global | Fleet Management System for a period of 36 months | 11430 | 2022-09-22 | 2022-10-01 | 2025-09-30 | Yes | The rates are charged as per BOQ
GLM001/2023 | Ntlhapeng Trading Enterprise | Panel of service providers rendering a service in respect of panel of six (6) for supply and delivery of personal protective clothing for a period of 36 months | 27353.17 | 2022-09-19 | 2022-09-26 | 2025-09-26 | Yes | The rates are charged as per BOQ
GLM001/2023 | GEBR Schroder GMBH (PTY) LTD | Panel of service providers rendering a service in respect of panel of six (6) for supply and delivery of personal protective clothing for a period of 36 months | 27353.17 | 2022-09-19 | 2022-09-26 | 2025-09-26 | Yes | The rates are charged as per BOQ
GLM001/2023 | Phadu Holdings (PTY) LTD | Panel of service providers rendering a service in respect of panel of six (6) for supply and delivery of personal protective clothing for a period of 36 months | 27353.17 | 2022-09-19 | 2022-09-26 | 2025-09-26 | Yes | The rates are charged as per BOQ
GLM001/2023 | Sampule (PTY) LTD | Panel of service providers rendering a service in respect of panel of six (6) for supply and delivery of personal protective clothing for a period of 36 months | 27353.17 | 2022-09-19 | 2022-09-26 | 2025-09-26 | Yes | The rates are charged as per BOQ
GLM001/2023 | Maeku's (PTY) LTD | Panel of service providers rendering a service in respect of panel of six (6) for supply and delivery of personal protective clothing for a period of 36 months | 27353.17 | 2022-09-19 | 2022-09-26 | 2025-09-26 | Yes | The rates are charged as per BOQ
GLM001/2023 | Tsoga Mamogopo Trading and Projects | Panel of service providers rendering a service in respect of panel of six (6) for supply and delivery of personal protective clothing for a period of 36 months | 27353.17 | 2022-09-19 | 2022-09-26 | 2025-09-26 | Yes | The rates are charged as per BOQ
GLM019/2022 | Seboch Group (PTY) LTD | Panel of service providers rendering a service in respect of panel of six (4) for supply and delivery of stationery for a period of 36 months | 301255.65 | 2022-10-20 | 2022-10-27 | 24-0ct-2025 | Yes | The rates are charged as per BOQ
GLM019/2022 | Serakwa Assessor Consultants | Panel of service providers rendering a service in respect of panel of six (4) for supply and delivery of stationery for a period of 36 months | 301255.65 | 2022-10-20 | 2022-10-27 | 24-0ct-2025 | Yes | The rates are charged as per BOQ
GLM019/2022 | Sylmako Group | Panel of service providers rendering a service in respect of panel of six (4) for supply and delivery of stationery for a period of 36 months | 301255.65 | 2022-10-20 | 2022-10-27 | 24-0ct-2025 | Yes | The rates are charged as per BOQ
GLM019/2022 | Kea Authentic Trading and Projects | Panel of service providers rendering a service in respect of panel of six (4) for supply and delivery of stationery for a period of 36 months | 301255.65 | 2022-10-20 | 2022-10-27 | 24-0ct-2025 | Yes | The rates are charged as per BOQ
O/N 42850 | Hoshani Security Services | Rendering of security services for GLM facilities | 11307375 | 2022-08-31 | 2022-09-01 | 2022-11-30 | Yes
GLM011/2023 | Risima Project Management | Electrification of Two Villages (Lebepane and Rotterdam) | 9555546 | 2022-12-14 | 2023-01-18 | 2023-05-31 | Yes
GLM012/2023 | Bilmond Trading and Construction | Electrification of Three Villages (Mpepule, Lehalreng & Rajeke) | 6512841 | 2022-12-14 | 2023-01-18 | 2023-05-31 | Yes
GLM013/2023 | Manco Business Enterprise | Electrification of Three Villages (Iketleng, Lekgwareng & Makhurupetse) | 6803412 | 2022-12-14 | 2023-01-18 | 2023-05-31 | Yes
GLM016/2023 | NNC Propeties PTY LTD | Supply, Delivery and Installation of Four (4) Highmast Lights in Bellevue Cluster | 1494773.25 | 2022-12-14 | 2023-01-18 | 2023-05-31 | Yes | The rates are charged as per BOQ
GLM017/2023 | Thotogelo MP Construction and Projects | Supply, Delivery and Installation of Four (4) Highmast Lights in Kgapane Cluster | 1494759.75 | 2022-12-14 | 2023-01-18 | 2023-05-31 | Yes | The rates are charged as per BOQ
GLM018/2023 | OTS Electrical | Supply, Delivery and Installation of Four (4) Highmast Lights in Mokwakwaila Cluster | 1494773.25 | 2022-12-14 | 2023-01-18 | 2023-05-31 | Yes | The rates are charged as per BOQ
GLM019/2023 | Mfumu Trading and Projects | Supply, Delivery and Installation of Four (4) Highmast Lights in Sekgosese Cluster | 1494773.25 | 2022-12-14 | 2023-01-18 | 2023-05-31 | Yes | The rates are charged as per BOQ
GLM028/2023 | Cathu Consulting Inc | Provision of Advisory services within Finance department of the municipality for a period of two (2) years | 3431496.5 | 2023-04-04 | 2023-05-01 | 2025-04-30 | Yes
GLM018/2023 | Mfumu Trading and Projects | Supply, Delivery and Installation of Four (4) Highmast Lights in Mokwakwaila Cluster | 1542322.5 | 2023-05-26 | 2023-01-18 | 2024-06-30 | Yes
GLM026/2023 | Dignity Supply and Projects | Procrement of Panel of Service Providers for Training and Development for a period of 36 months to be appointed on an "as and when" required basis for the period of 36 months | Quotation based | 2023-06-19 | 2023-06-23 | 2026-06-22 | Yes | Quotation based
GLM026/2023 | Growth Management Consulting | Procrement of Panel of Service Providers for Training and Development for a period of 36 months to be appointed on an "as and when" required basis for the period of 36 months | Quotation based | 2023-06-19 | 2023-06-23 | 2026-06-22 | Yes | Quotation based
GLM026/2023 | Paseka Business Enterprise | Procrement of Panel of Service Providers for Training and Development for a period of 36 months to be appointed on an "as and when" required basis for the period of 36 months | Quotation based | 2023-06-19 | 2023-06-23 | 2026-06-22 | Yes | Quotation based
GLM026/2023 | Thansa Trading (Pty) Ltd | Procrement of Panel of Service Providers for Training and Development for a period of 36 months to be appointed on an "as and when" required basis for the period of 36 months | Quotation based | 2023-06-19 | 2023-06-23 | 2026-06-22 | Yes | Quotation based
GLM026/2023 | GNS Training Consultants | Procrement of Panel of Service Providers for Training and Development for a period of 36 months to be appointed on an "as and when" required basis for the period of 36 months | Quotation based | 2023-06-19 | 2023-06-23 | 2026-06-22 | Yes | Quotation based
GLM026/2023 | Masikila Training Solution | Procrement of Panel of Service Providers for Training and Development for a period of 36 months to be appointed on an "as and when" required basis for the period of 36 months | Quotation based | 2023-06-19 | 2023-06-23 | 2026-06-22 | Yes | Quotation based
GLM026/2023 | Starplex 408 (Pty) Ltd | Procrement of Panel of Service Providers for Training and Development for a period of 36 months to be appointed on an "as and when" required basis for the period of 36 months | Quotation based | 2023-06-19 | 2023-06-23 | 2026-06-22 | Yes | Quotation based
GLM026/2023 | Mawasha Chemicals | Procrement of Panel of Service Providers for Training and Development for a period of 36 months to be appointed on an "as and when" required basis for the period of 36 months | Quotation based | 2023-06-19 | 2023-06-23 | 2026-06-22 | Yes | Quotation based
GLM026/2023 | Dithoriso Phepo Hlweko Services | Procrement of Panel of Service Providers for Training and Development for a period of 36 months to be appointed on an "as and when" required basis for the period of 36 months | Quotation based | 2023-06-19 | 2023-06-23 | 2026-06-22 | Yes | Quotation based
GLM026/2023 | P. MAB Managers and Projects | Procrement of Panel of Service Providers for Training and Development for a period of 36 months to be appointed on an "as and when" required basis for the period of 36 months | Quotation based | 2023-06-19 | 2023-06-23 | 2026-06-22 | Yes | Quotation based
GLM026/2023 | Nyankwavi Investment cc | Procrement of Panel of Service Providers for Training and Development for a period of 36 months to be appointed on an "as and when" required basis for the period of 36 months | Quotation based | 2023-06-19 | 2023-06-23 | 2026-06-22 | Yes | Quotation based
GLM026/2023 | International Business Training College | Procrement of Panel of Service Providers for Training and Development for a period of 36 months to be appointed on an "as and when" required basis for the period of 36 months | Quotation based | 2023-06-19 | 2023-06-23 | 2026-06-22 | Yes | Quotation based
GLM026/2023 | MMK Services (Pty) Ltd | Procrement of Panel of Service Providers for Training and Development for a period of 36 months to be appointed on an "as and when" required basis for the period of 36 months | Quotation based | 2023-06-19 | 2023-06-23 | 2026-06-22 | Yes | Quotation based
GLM027/2023 | The Five Star Trading and Projects | Procurement of Supply, Delivery and installation of uniterrupted power through inverters, lithium battery, and solar inverter, battery, and solar for ICT network cabinets | 599886 | 2023-06-20 | 2023-07-01 | 2023-10-30 | Yes
GLM029/2023 | Daily Breez (Pty) Ltd | Procurement of Supply and Delivery of 22 X 6m3 Skip Bins | 940000 | 2023-06-27 | 2023-07-01 | 2023-10-30 | Yes
GLM030/2023 | B2 Fuel (Pty) Ltd | Procurement of Supply and Delivery of Fuel, Diesel, Petrol and oil for a period of 36 months | 1647.08 | 2023-06-20 | 2023-07-01 | 2026-06-30 | Yes | Per BOQ
GLM030/2023 | Afripoint Fuel (Pty0 Ltd | Procurement of Supply and Delivery of Fuel, Diesel, Petrol and oil for a period of 36 months | 1693 | 2023-06-20 | 2023-07-01 | 2026-06-30 | Yes | Per BOQ
GLM024/2025 | Liberty Town Planners | Panel of Town Planning consultants for a period of three (3) years | 7925225 | 2023-06-20 | 2023-07-01 | 2026-06-30 | Yes | Per BOQ
GLM024/2025 | Matete and Associates Consultants | Panel of Town Planning consultants for a period of three (3) years | 7925225 | 2023-06-20 | 2023-07-01 | 2026-06-30 | Yes | Per BOQ
GLM024/2025 | Techni Plano Development Strategists | Panel of Town Planning consultants for a period of three (3) years | 7925225 | 2023-06-20 | 2023-07-01 | 2026-06-30 | Yes | Per BOQ
GLM025/2023 | Matete and Associates Consultants | Panel of land surveying consultants for a period of three (03) years | 1447160 | 2023-06-20 | 2023-07-01 | 2026-06-30 | Yes | Per BOQ
GLM025/2023 | MM Geomatics (Pty) Ltd | Panel of land surveying consultants for a period of three (03) years | 1447160 | 2023-06-20 | 2023-07-01 | 2026-06-30 | Yes | Per BOQ
GLM025/2023 | N Khoza Land Surveyors | Panel of land surveying consultants for a period of three (03) years | 1447160 | 2023-06-20 | 2023-07-01 | 2026-06-30 | Yes | Per BOQ
GLM014/2022 | Nkomazi Lemetja JV | Construction of Buqa Low Level Bridge | 900378.55 | 2023-06-15 | 2023-07-01 | 2023-11-30 | Yes
GLM014/2022 | Xalamuka Built Environment JV | Construction of Roerfontein Low Level Bridge | 847579.3 | 2023-06-27 | 2023-07-01 | 2023-11-30 | Yes
GLM023/2023 | A New Awekening Trading cc | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
GLM023/2023 | GPMVR Multi Projects | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
GLM023/2023 | Moilalehlaka Investment (Pty) Ltd JV Phadu Holdings | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
GLM023/2023 | Oramac Civil Construction | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
GLM023/2023 | Afri Point Solutions (Pty) Ltd | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
GLM023/2023 | Letsimane trading & Projects JV Bokamoso | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
GLM023/2023 | Forshaken Construction cc | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
GLM023/2023 | Leboneng North Investments | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
GLM023/2023 | Chango Business Enterprise cc | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
GLM023/2023 | Telgoplex (Pty) Ltd | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
GLM023/2023 | Sunay Trading & Projects 240 cc | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
GLM023/2023 | Basia ke Balobedu Holding | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
GLM023/2023 | Bosvark Development (Pty) Ltd | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
GLM023/2023 | Firm Early Constructions | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
GLM023/2023 | Quintax 212 JV FJRIC Construction Projects | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
GLM023/2023 | Kamela ya Tshwale | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
GLM023/2023 | Mikat 8279 Trading | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22
GLM023/2023 | Nax Most Construction cc | Procurement of twenty (20) panel service providers (contractors) for preventative maintenance of municipal facilities within Greater Letaba Local Municipality for a period of three (03) years. | 1179274.08 | 2023-09-22