## COVER
GREATER LETABA MUNICIPALITY
SDBIP MID-YEAR BUDGET AND
PERFORMANCE REPORT
2014/2015
MFMA Section 72

## Table of Content
Table of Contents
Introduction | 2
Other Legislations | 3
Strategic Vision, Mission and Strategy Map | 4
Municipal Transformation and Organisational Development KPIs | 6
Municipal Transformation and Organisational Development Projects | 10
Basic Service Delivery Projects | 13
Local Economic Development Projects | 24
Municipal Financial Viability KPI's | 28
Municipal Financial Viability Projects | 29
Good Governance and Public Participation Projects | 31
Good Governance and Public Participation KPIs | 36
Rollover Projects | 38
Service Delivery Performance Summary and Analysis | 41
Mid Year Financial Performance | 42
Progress on resolving problems identified in the 2013/2014 Annual Report | 60
Conclusion | 61
Aproval | 62

## Introduction
1. INTRODUCTION
This report encompasses the 2013/2014 Mid-year Budget and Performance Assessment Report which has been compiled in accordance with Section 72 of the Municipal Finance Management Act, Act 56 of 2003 (MFMA). The report provides an overview of the applicable legislative framework and the manner in which the Municipality has performed with regard to Service Delivery Implementation Plan.
2. LEGISLATIVE BACKGROUND
2.1. Municipal Finance Management Act, 2003
Section 72, of the MFMA 2003, says the following regarding the mid-year budget and performance assessment:
The Accounting Officer of a municipality must by 25 January of each year;
Assess the performance of the municipality during the first half of the financial year, taking into account:
The monthly statements
Municipality’s service delivery performance during the first half of the financial year- service delivery targets and performance indicators set in the Service Delivery and Budget Implementation Plan
The past year’s annual report and progress on resolving problems identified in the annual report.
The Accounting Officer is expected to submit a report on such assessment to the Mayor of the municipality, the National Treasury and the relevant Provincial Treasury.

## Other Legislations
2.2. OTHER LEGISLATIONS
o National Government-Wide program for local government: the 5 YR Local Government Strategic Agenda is a national program of the government that was approved by the Cabinet Lekgotla in January 2006. The goal of the program over the medium term is accelerate basic service provision and to meet the targets set for universal access as outlined in the Vision 2014 and other targets for basic services. The goal presupposes that municipalities are effective and capable of achieving their constitutional mandates for a developmental local government. This is based on the premise that local government should have the fiscal resources and powers to recruit, absorb, and retain appropriate managerial, professional, and technical skills into their establishments. Linked to this is the assumption that the other spheres have the appropriate capacity to play their part in cooperative government and to discharge their responsibilities to monitor, support and regulate local government.
o Executive Oversight on the implementation of the local government strategic agenda: The five year strategic agenda serves as a standing item in Intergovernmental forums in all spheres of government. The National Parliament and the Provincial Legislature uses the Five Year Strategic Agenda to assess the support role played by the National/ Provincial Departments in municipalities. Therefore the specific IGR structures are the Presidential Coordinating Council (PCC); the Premiers Coordinating Forum; District Coordinating Forum.
o Government-Wide Monitoring and Evaluation: the monitoring and evaluation of the local government strategic agenda forms part of the Government-Wide Monitoring and Evaluation Implementation Plan.
o National Targets: the implementation plan to be developed by the municipalities on the implementation of the Five Year Local Government Strategic Agenda should be informed by the national targets set for the government in the VISION 2014 Manifesto as approved by Cabinet.
o Five Key Performance Area: the Local Government Strategic Agenda is structured into five Key Performance Areas, from which the targets and performance indicators are based, namely:
o KPA 1: Municipal Transformation and Organisational Development
o KPA 2: Basic Service Delivery
o KPA 3: Local Economic Development
o KPA 4: Municipal Financial Viability and Management
o KPA 5: Good Governance and Public Participation

## Strategy
Vision and Mission | The strategic vision of the organisation sets the long term goal the Municipality intends to achieve. The vision of Greater Letaba Municipality is: "To be an outstanding agro-processing and eco-cultural tourism hub. The strategic Mission Speaks about what the purpose of Greater Letaba Municipality is: The mission of Greater Letaba Municipality is to ensure an effective, efficient and economically viable municipality through: Provision of accountable, transparent, consultative and co-operative governance Improving the quality of life through economic development and poverty alleviation Provision of sustainable services Ensuring a safe and healthy environment
Strategy map | The Strategy Map depicts the Strategic Objectives on how Greater Letaba Municipality will be able to become an outstanding agro-processing and eco-cultural tourism hub while providing sustainable and affordable services to all. These objectives were positioned in terms of the Balanced Scorecard Perspectives being: Learning and Growth; Institutional Processes; Financial results and Community Satisfaction. All operational outputs (projects, initiatives and process) as contained within the SDBIP are aligned to the attainment of one or more of these objectives.

## MTOD KPI's
KPA 1 MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT
KEY PERFORMANCE INDICATORS
OUTCOME NINE (OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING, PLANNING AND SUPPORT, OUTPUT 4: ACTIONS SUPPORTIVE OF THE HUMAN SETTLEMENT OUTCOMES)
Vote Nr | Strategic Objective | Programmes | Measurable Objectives | Performance measures | Baseline / Status | Budget 2014/2015 | Midyear target end Dec 2014 | Achievements / Progress Midyear Ending Dec 2014 | Challenges | Interventions | Expenditure | Responsible Person
50 | Improved Quality of Life | Indigent Management | To ensure that all indigent applicants are registered in the indigent register within 14 days of receipt. | % of Indigent applications registered (# of applications received/# of indigent applicantions processed) | 1725 | Operational | 900 | Target not achieved. 721 indigents applications received and processed. | Number of applications made were less than the targeted number | Conduct awareness campaigns in all wards | 154257 | CFO
22 | Integrated Sustainable Development | IDP | To ensure that draft IDP, Budget and SDBIP are adopted by 31 March 2015. | Draft IDP, budget and PMS adopted by 31 March 2015 | Adopted by 31 March 2015 | Operational | n/a | n/a | n/a | n/a | Operational | INDEP/CFO/MM
22 | Integrated Sustainable Development | IDP | To develop and implement IDP process plan by 30 June 2015. | IDP process plan adopted and implemented by 30 June 2015. | Adopted by 31 May 2015 | Operational | n/a | n/a | n/a | n/a | Operational | INDEP/CFO/MM
22 | Integrated Sustainable Development | IDP | To review, drive and monitor implementation of the IDP by 31 May 2015 | % achievement of milestones on IDP/Budget/PMS process plan. | 100% | Operational | 50% | Target achieved. Process plan at 50% | n/a | n/a | Operational | INDEP/MM
22 | Integrated and Sustainable Human Settlement | Spatial Planning | To submit housing demand database to COGHSTA by the 12 December 2014 | House demand database submitted by 12 December 2014 | Database submitted to COGHSTA by the 12 December 2014 | Operational | Database submitted to COGHSTA by the 12 December 2014 | Target achieved. Database submitted to COGHSTA by the 12 December 2015 | n/a | n/a | Operational | INDEP
22 | Integrated and Sustainable Human Settlement | Spatial Planning | To ensure that land use applications are processed within 90 days of receipt. | % of land use applications processed (# of applications received / # of land use applications processed) within 90 days of receipt | 100% | Operational | 100% | Target achieved. 100% land use applications processed (21 land use applications received /21 land use applications processed) | None | None | Operational | INDEP
22 | Integrated and Sustainable Human Settlement | Annual Report | To compile the Draft Annual Report and submit to council by 12 December 2014 | Draft Annual Report adopted by Council on 12 December 2014 | Draft Annual Report adopted by Council on 12 December 2014 | Operational | Draft Annual Report adopted by Council on 12 December 2014 | Target achieved. Annual performance report submitted to Council on 11 August 2014 | n/a | n/a | Operational | MM/ All Directors
33 | Improved Governance and Organisational Excellence | Annual Report | To compile the Final Annual Report and submit to council by 31 January 2015 | Final Annual Report approved by council on 31 January 2015 | Final Annual Report approved by council on 31 January 2015 | Operational | n/a | n/a | n/a | n/a | Operational | MM / All Directors
33 | Improved Governance and Organisational Excellence | SDBIP | To ensure that SDBIP is finalised by 30 June 2015. | SDBIP approved by Mayor 28 days after adoption of the final Budget and IDP. | SDBIP approved by Mayor 28 days after adoption of Budget and IDP | Operational | n/a | n/a | n/a | n/a | Operational | PMS/MM
54 | Improved Governance and Organisational Excellence | OPMS | To ensure annual implementation of the performance management system in the organisation | # of Quarterly performance reports submitted to Council. | 4 | Operational | 2 Quarterly performance reports submitted to Council | Target achieved. 2 x Quarterly performance reports submitted to Council | n/a | n/a | Operational | PMS/MM
54 | Improved Governance and Organisational Excellence | EPMS | To ensure that S57 Managers sign the performance agreements within 30 days after adoption of the final SDBIP. | # of S57 Managers with signed performance agreements within 30 days after adoption of the final SDBIP | 5 | Operational | 5 x performance agreements signed within 30 days after adoption of the final SDBIP | Target not achieved. 4 performance agreements signed within 30 days after adoption of the final SDBIP | Post of Director: Corporate Services was not yet filled. | The incumbent appointed will sign performance agreement within 30 days of appointment. | Operational | MM
54 | Improved Governance and Organisational Excellence | EPMS | To ensure that annual assessments of S57 Managers is conducted within 30 days after the end of the fiancial year. | # of annual performance assessments conducted within 30 days after the end of the fiancial year. | 1 | Operational | 2 x Annual performance asessments | Target achieved. Annual performance asessment conducted. | n/a | n/a | Operational | PMS/MM
54 | Improved Governance and Organisational Excellence | EPMS | To ensure quartely assessments for S57 Managers is conducted within 30 days after the end of the quarter. | # of quarterly performance assessments conducted within 30 days after the end of the quarter. | 1 | Operational | 1 x performance assessment | Target not achieved. | Qtr1 assessment not done. | Conduct only formal assessment : midyear and annual. | Operational | PMS/MM
54 | Improved Governance and Organisational Excellence | Internal Audit | To ensure functionality of Audit committee within the financial year. | # of meetings held per quarter. | 4 | Operational | 2 x meetings | Target achieved. 2 x ordinary meetings; 2 x special Audit Committee meeting held | n/a | n/a | Operational | Internal Audit /MM
54 | Improved Governance and Organisational Excellence | Risk | To ensure functionality of Risk committee within the financial year. | # of meetings held per quarter. | 4 | Operational | 2 x risk committee meetings | Target not achieved. 1x Risk Committee meetings held | Meeting postponed due to other official commitments | Adherence to Risk Committee meeting schedule |  | Risk/MM
54 | Improved Governance and Organisational Excellence | CORPS | To ensure functionality of Council committee within the financial year. | # of meetings held per quarter. | 4 | Operational | 2 x Council meetings | Target achieved. 1 x ordinary 4 x meetings held. | n/a | n/a | Operational | CORPS/MM
| Improved Governance and Organisational Excellence | CORPS | To ensure functionality of Exco committee within the financial year. | # of meetings held per quarter. | 4 | Operational | 2 x Exco meetings | Target achieved. 1 x ordinary 4 x meetings held. | n/a | n/a | Operational | CORPS/MM
54 | Improved Governance and Organisational Excellence | Internal Audit | To conduct quarterly assessment on municipal performance information. | # of performance audit reports issued per quarter. | 4 | Operational | 2 x performance audit reports | Target achieved. 2 x performance audit reports issued. | n/a | n/a | Operational | Internal Audit
54 | Improved Governance and Organisational Excellence | Internal Audit | To develop annual year internal audit plan and implement by 30 June 2015. | Approved internal audit plan and % of the IA plan implementation. | 50% | Operational | 50% | Target not achieved. 0% internal audit plan implemented | Internal Audit Plan not approved | Finalisation of Risk Register | Operational | MM
54 | Improved Governance and Organisational Excellence | Operation clean audit | To attain Clean Audit by ensuring compliance to all governance; financial management and reporting requirements by 12 December 2014 | % of internal audit issues resolved (# of Internal Audit issues resolved / # of issues raised) | 12% | Operational | 100% | Target not achieved. 7% (4 IA issues resolved / 30 issues reaised) | Non-implementation of IA queries | Place implementation of IA findings on the Performance Agreement of Directors. | Operational | All Directors/MM
54 | Improved Governance and Organisational Excellence | Operation clean audit | To attain Clean Audit by ensuring compliance to all governance; financial management and reporting requirements by 30 June 2015 | % of AG issues resolved (# of Auditor-General issues resolved / # of issues raised) | 78% | Operational | n/a | n/a | n/a | n/a | Operational | All Directors/MM
54 | Improved Governance and Organisational Excellence | Risk management | To ensure efffective implementation of risk mitigations actions 30 June 2015. | % of Risk issues resolved (# Risk issues implemented / resolved / # of risks identified) | 100% | Operational | 50% | Target not achieved. 0% (9 Risk issues raised/ 9 not resolved). . | Slow implementation of mitigation actions. | Management have developed mitigation actions to address the risks identified | Operational | Risk/MM

## MTOD PROJECTS
KPA 1 MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT PROJECTS
OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING, PLANNING AND SUPPORT, OUTPUT 4: ACTIONS SUPPORTIVE OF THE HUMAN SETTLEMENT OUTCOMES
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project / Initiative | Budget 2014/2015 | Start Date | Completion Date | Midyear target end Dec 2014 | Achievements / Progress Midyear Ending Dec 2014 | Challenges | Interventions | Expenditure | Project Owner
46 | Improved Governance and Organisational Excellence | Risk Management | To organise 4 OHS risk assessment workshop by 30 June 2015 | Risk assessment: OHS | 9000 | 01/07/2014 | 30/06/2015 | 2 | Target achieved. 2 x OHS Risk assessment workshops conducted. | n/a | n/a | 7895 | MM
46 | Improved Governance and Organisational Excellence | OHS | To organise 4 Health and Safety awareness events 30 June 2015 | Health and safety awareness event | 40000 | 01/07/2014 | 30/06/2015 | 2 Health and Safety awareness events | Target achieved. 2x Health and safety awareness events held | n/a | n/a | 1200 | CORPS
46 | Improved Governance and Organisational Excellence | OHS | To purchase OHS signs and posters by 30 September 2014 | OHS signs and posters | 12000 | 01/07/2014 | 30/09/2014 | Develop specification, submit to SCM, purchase and paste OHS sign posters | Target not achieved. Specification submitted. OHS Posters not purchased | Non adherence to procurement plan | To purchase in the 3rd Qtr | 0 | CORPS & CFO
46 | Improved Governance and Organisational Excellence | Furniture & Equipment | To purchase office signs and posters by 30 September 2014 | Four (4)signs and posters | 2000 | 01/07/2014 | 30/09/2014 | Develop specification, submit to SCM, purchase office signs and posters | Target not achieved. Specification submitted. OHS Posters not purchased | Non adherence to procurement plan | To purchase in the 3rd Qtr | 0 | CORPS & CFO
46 | Improved Governance and Organisational Excellence | OHS | To purchase First aid kit by 30 September 2014 | First Aid content | 5000 | 01/07/2014 | 30/09/2014 | Develop specification, submit to SCM, purchase first aid kit | Target not achieved. First aid kit not purchased. | First aid kit no longer required. | To be removed during budget adjustment | 0 | CORPS & CFO
46 | Improved Governance and Organisational Excellence | Human Resources | To organise EWP day by 12 December 2014 | Employee wellness programme | 40000 | 01/10/2014 | 12/12/2014 | Employee wellness day | Target achieved. EWP day held. | n/a | n/a | 12000 | CORPS
54 | Improved Governance and Organisational Excellence | Property Services | Purchasing of a scanner by 30 September 2014 | Scanner | 5000 | 01/07/2014 | 30/09/2014 | Develop specification, submit to SCM, purchase scanner | Target not achieved. Specifications developed and submitted to SCM. Scanner not purchased | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | CORPS
46 | Improved Governance and Organisational Excellence | Property Services | To develop and implement skills Developemnt programmes by 30 June 2015 | Skills development levy | 300000 | 01/07/2014 | 30/06/2015 | Advertisement of tender and appointment of service provider | Target achieved. Paymenst of skills development levy made | n/a | n/a | 284706000 | CORPS
46 | Improved Governance and Organisational Excellence | Human Resources | To award long service award to eligible employees timeously according to policy | Long service award | 169920 | 01/07/2014 | 30/06/2015 | 100% of the qualifying employees | Target achieved. 100% of the qualifying employees awarded long service award. | n/a | n/a | 93218 | CORPS
46 | Improved Governance and Organisational Excellence | IT | To rent network printer by 12 December 2014 | Rental of the network printer | 1101597 | 01/07/2014 | 12/12/2014 | .Appointment of service provider | Target achieved. Network printer rented (existing project) | n/a | n/a | 0 | CORPS
46 | Improved Governance and Organisational Excellence | IT | To network all GLM sub offices by 31 March 2015 | Networking of the sub-offices | 264000 | 01/07/2014 | 31/03/2015 | Appointment of service provider and implement 50% of the project. | Target not achieved. Service provider not appointed and implementation at 0%. | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | CORPS
39 | Improved Governance and Organisational Excellence | IT | Develop maintenance Plan for all IT Systems by 30 September 2014 | Maintenance Plan for all IT Systems | 10560 | 01/07/2014 | 30/09/2014 | Appointment of service provider and 100% plan completed. | Target not achieved. Service provider not appointed and implementation at 0%. | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | CORPS
46 | Improved Governance and Organisational Excellence | IT | To purchase 4 Printers: Senwamokgope, Mokwakwaila, Kgapane and main office by 30 September 2014 | 4 Printers: Senwamokgope, Mokwakwaila, Kgapane and main office | 100000 | 01/07/2014 | 30/09/2014 | Develop specification, submit to SCM and purchase printers | Target not achieved. 4 x printers not procured. | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | CORPS & CFO
46 | Improved Governance and Organisational Excellence | Human Resources | Procument of 6 steel cabinets: Finance by 30 September 2014 | 6 x Steel Filling Cabinet: Finance | 30000 | 01/07/2014 | 30/09/2014 | Develop specification, submit to SCM and purchase steel filling cabinets | Target achieved. 6 x steel cabinets purchased. | n/a | n/a | 8205 | CORPS
46 | Improved Governance and Organisational Excellence | Human Resources | To purchase Office furniture by 12 December 2014 | Office furniture | 175000 | 01/07/2014 | 12/12/2014 | Develop specification, submit to SCM, advertise and purchase office furniture | Target not achieved. Office furniture not purchased. | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | CORPS & CFO
46 | Improved Governance and Organisational Excellence | IT | To purchase Servers by 12 December 2014 | Servers | 100000 | 01/07/2014 | 12/12/2014 | Request quotations for procurement, appoint service provider, supply and installation of servers at 100% | Target not achieved. Server procured. Installation at 0% | Non adherence to procurement plan | To followup with the service provider for installation | 0 | CORPS & CFO
46 | Improved Governance and Organisational Excellence | IT | To purchase Server room door by 12 December 2014 | Server room door | 50000 | 01/07/2014 | 12/12/2015 | Request quotations for procurement, appoint service provider, supply and installation of server room door at 100% | Target not achieved. Server room door not procured. Installation at 0%. | Non adherence to procurement plan | To followup with the service provider for installation | 0 | CORPS & CFO
46 | Improved Governance and Organisational Excellence | IT | To purchase 10 laptops by 30 September 2014 | 10 Laptops | 100000 | 01/07/2014 | 30/09/2014 | Develop specifications,submit to SCM and purchase laptops. | Target not achieved. 10 laptops not purchased | Non adherence to procurement plan | Reprioritise and review procurement plan | 0 | CORPS & CFO
46 | Improved Governance and Organisational Excellence | IT | To develop and implement disaster recovery plan by 31 March 2015 | Disaster Recovery Plan and UPS | 300000 | 01/10/2014 | 31/03/2015 | Develop specification, submit to SCM, advertise, appoint a service provider and 50% implementation | Target not achieved. Service provider not appointed and implementation at 0%. | Delay in the identification of DRP/UPS location | Identification of a new location | 0 | CORPS & CFO
54 | Improved Governance and Organisational Excellence | Property Services | To purchase shelves for filling by 30 September 2014 | Shelves for filling | 30000 | 01/07/2014 | 30/09/2014 | Develop specification, submit to SCM and purchase | Target not achieved. Shelves not purchased. | Delay in identification of location for the shelves. | Purchase shelves for filling | 0 | CORPS
54 | Improved Governance and Organisational Excellence | Property Services | Construction of parking area for 36 vehicles at main office by 31 March 2015 | Parking at Municipal Offices | 1000000 | 01/07/2014 | 31/03/2015 | Develop specification, submit to SCM, advertise, appoint a service provider and construction at 50% implementation | Target not achieved. Service provider not appointed. Construction of municipal parking offices at 0%. | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T

## BSD PROJECTS
KPA 2 BASIC SERVICE DELIVERY AND INFRASTRUCTURE KEY PERFORMANCE PROJECTS OUTCOME NINE (OUTPUT 2: IMPROVING ACCESS TO BASIC SERVICES, OUTPUT 3: IMPLEMENTATION OF THE COMMUNITY WORK PROGRAMME)
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project / Initiative | Budget 2014/2015 | Start Date | Completion Date | Milestones (Mid year) Qtr Ending Dec 14 | Achievements / Progress Midyear Ending Dec 2014 | Challenges | Intervention | Expenditure | Project Owner
62 | Access to Sustainable Basic Services | Stormwater | Construction of pedestrian bridge at Ga-Kgapane (William Kgatla) by 31 March 2015 | Pedestrian William Kgatle Bridge | 150000 | 01/07/2014 | 31/03/2015 | Appoint contractors. Project management and construction monitoring to achieve 25% progress | Target not achieved. Contractors not appointed and construction at 0% | Non-acceptance of the contract in the previous FY | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
62 | Access to Sustainable Basic Services | Stormwater | Design and construction of low level bridges by 31 March 2015 | Low Level Bridges | 1500000 | 01/07/2014 | 31/03/2015 | Appoint contractors. Project management and construction monitoring to achieve 25% progress | Target not achieved. Contractors not appointed and construction at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
62 | Access to Sustainable Basic Services | Stormwater | Design and construction of stormwater management channels in Modjadjiskloof by 31 March 2015 | Modjadjiskloof- Channels | 2000000 | 01/07/2014 | 31/03/2015 | Appoint consultants for professional services and resume with construction to 15% | Target not achieved. Consultants not appointed. Construction at 0% | Non adherence to procurement plan | Design to be finalised in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Purchasing of two TLB (Backhoe Loader) by 12 December 2014 | TLB (Backhoe Loader) | 1500000 | 01/07/2014 | 12/12/2014 | Purchasing and delivery | Target not achieved. TLB (Backhoe loader) not purchased. | Non adherence to procurement plan | Machine to be procured in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Purchasing of a 2 tonner truck with quarter canopy for roads maintenance team by 12 December 2014 | 2 Tonner Truck with Quarter Canopy | 300000 | 01/07/2014 | 12/12/2014 | Purchasing and delivery | Target not achieved. 2 tonner trucks with quarter canopy not purchased | Non adherence to procurement plan | Truck to be procured in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Purchasing of a plate compactor by 30 September 2014 | Plate compactor | 35000 | 01/07/2014 | 30/09/2014 | Develop, submit specifications to SCM and purchase | Target not achieved. Pllate compactor not purchased. | Non adherence to procurement plan | Machine to be procured in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Supply and installation of gabions for Sekgopo by 31 March 2015 | Gabions - Sekgopo | 1200000 | 01/07/2014 | 31/03/2015 | Appoint service provider for installation of gabions, progress at 50% | Target not achieved. Service provider not appointed, installation of gabions at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Upgrading of gravel to concrete paving blocks for 1.8 km at Mothobeki village by 31 March 2015 | Mothobeki Paving | 6500000 | 01/07/2014 | 31/03/2015 | Appoint contractors and construction progress a 10% | Target not achieved. Contractors not appointed and construction at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | R135 229.00 (Professional fees) | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Upgrading of gravel to concrete paving blocks for 1.8 km at Mamaila Phaphadi village by 31 March 2015 | Mamaila Phaphadi Paving | 6500000 | 01/07/2014 | 31/03/2015 | Appoint contractors and construction progress a 10% | Target not achieved. Contractors not appointed and construction at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Upgrading of gravel to concrete paving blocks for 1.8 km at Phooko village by 31 March 2015 | Phooko Head Kraal Paving | 3200000 | 01/07/2014 | 31/03/2015 | Appoint contractors and construction progress a 10% | Target not achieved. Contractors not appointed and construction at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | R139 693.00 (Professional fees) | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Upgrading of gravel to concrete paving blocks for 1.8 km at Raphahlelo village by 31 March 2015 | Raphahlelo Head Kraal Paving | 6550000 | 01/07/2014 | 31/03/2015 | Appoint contractors and construction progress a 10% | Target not achieved. Contractors not appointed and construction at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | R179 660.00 (Professional fees) | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Purchasing of 2 tipper trucks by 12 December 2014 | Tipper truck | 1380000 | 01/07/2014 | 12/12/2014 | Purchasing and delivery | Target not achieved. Tipper truch not purchased. | Non adherence to procurement plan | Truck to be procured in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Rehabilitation of 3 km of streets in Modjadjiskloof by 31 March 2015 | Rehabilitation of Modjadjiskloof Streets | 5500000 | 01/07/2014 | 31/03/2015 | Appoint contractors and construction progress a 10% | Target not achieved. Contractors not appointed and construction at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | R88 405.00 (Professional fees) | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Rehabilitation of 3 km of streets in Ga-Kgapane by 31 March 2015 | Rehabilitation of Ga-Kgapane Streets | 5500000 | 01/07/2014 | 31/03/2015 | Appoint contractors and construction progress a 10% | Target not achieved. Contractors not appointed and construction at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Purchasing of quick cut machine by 30 September 2014 | Quick cut machine | 28000 | 01/07/2014 | 30/09/2014 | Develop, submit specifications to SCM and purchase | n/a | n/a | n/a | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Construction of 3.5 km of sidewalks in Modjadjiskloof by 31 March 2015 | Modjadjiskloof Sidewalks | 3000000 | 01/07/2014 | 31/03/2015 | Appoint contractors and Construction progress a 50% | Target not achieved. Contractors not appointed and construction at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Construction of access road to Mokwakwaila Taxi Rank for 600m by 31 March 2015 | Access Road to Mokwakwaila Taxi Rank- Roll over | 3100000 | 01/07/2014 | 31/03/2015 | Appoint contractors and construction progress a 10% | Target not achieved. Contractors not appointed and construction at 0% | Non adherence to procurement plan | Design to be finalised in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Planning and designing of street paving at Itieleng (Sekgosese) by 30 June 2015 | Itieleng- Sekgosese Street Paving | 450000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Tender to be awarded and design be finalised in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Planning and designing of street paving at Lemondokop by 30 June 2015 | Lemondokop Street Paving | 450000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Tender to be awarded and design be finalised in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Planning and designing of street paving at Refilwe village by 30 June 2015 | Refilwe Street Paving | 450000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Tender to be awarded and design be finalised in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Planning and designing of street paving at Mamakata-Raselaka by 30 June 2015 | Mmamakata Raselaka Street Paving | 450000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Tender to be awarded and design be finalised in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Planning and designing of Ivory-route street paving at Modjadji by 30 June 2015 | Modjadji Ivory -route Street Paving | 7000000 | 01/07/2014 | 30/06/2015 | Appoint service provider and resume and complete designs | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Tender to be awarded and design be finalised in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Planning and designing of taxi rank at Khosotupa by 30 June 2015 | Khosutupa Taxi Rank | 220000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Design to be finalised in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Planning and designing of taxi rank at Wholesale by 30 June 2015 | Wholesale Taxi Rank | 220000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Design to be finalised in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Planning and designing of taxi rank at Mamphakati by 30 June 2015 | Mamphakati Taxi Rank | 220000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Design to be finalised in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of gravel to concrete paving blocks for 3 km at Ga-Kgapane by 31 March 2015 | Ga-Kgapane Street Upgrading | 8965000 | 01/07/2014 | 31/03/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | R241 633.00 (Professional fees) | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of gravel to concrete paving blocks for 1.8 km at Senwamokgope by 31 March 2015 | Senwamokgope Street Upgrading | 5400000 | 01/07/2014 | 30/03/2015 | Appoint contractors and construction progress at 10% | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of gravel to concrete paving blocks at Thakgalane by 30 September 2014 | Upgrading of streets - Thakgalane | 1500000 | 01/07/2014 | 30/09/2014 | Complete construction | Target not achieved. Construction incomplete | Non adherence to procurement plan | To be completed in the 3rd Qtr | R164 4213.00 (Professional fees) | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of gravel to concrete paving blocks for 1.2 km at Kuranta by 31 March 2015 | Upgrading of streets -Kuranta | 3600000 | 01/07/2014 | 31/03/2015 | Construction up to 50% | Target not achieved. Construction at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of gravel to concrete paving blocks for 2 km at Mokgoba by 31 March 2015 | Upgrading of streets -Mokgoba | 5950000 | 01/07/2014 | 31/03/2015 | Construction up to 50% | Target not achieved. Construction at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of gravel to concrete paving blocks for 2 km at Modjadji Valley by 31 March 2015 | Upgrading of streets -Modjadji Valley | 5950000 | 01/07/2014 | 31/03/2015 | Construction up to 50% | Target not achieved. Construction at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of gravel to concrete paving blocks for 2 km at Mandela park by 30 September 2014 | Mandela Park road | 2000000 | 01/07/2014 | 30/09/2014 | Complete construction | Target not achieved. Construction incomplete | Non adherence to procurement plan | To be completed in the 3rd Qtr | 1839596 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of gravel to concrete paving blocks for 2 km at Modjadji Head Kraal by 30 September 2014 | Modjadji Head Kraal road | 1000000 | 01/07/2014 | 30/09/2014 | Complete construction | Target not achieved. Construction incomplete | Non adherence to procurement plan | Apply penalties | 2616777 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of gravel to concrete paving blocks for 1.8 km at Ratjeke by 31 March 2015 | Ratjeke Street Paving | 5600000 | 01/07/2014 | 31/03/2015 | Construction up to 50% | Target not achieved. Construction at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of street paving at Seatlaleng village by 30 June 2015 | Seatlaleng Street Paving | 400000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed and designs progress at 0%. | Non adherence to procurement plan | Tender to be awarded and design be finalised in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of street paving at Mohlakong village by 30 June 2015 | Mohlakong Street paving | 400000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed and designs progress at 0%. | Non adherence to procurement plan | Tender to be awarded and design be finalised in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of street paving at Sephukubje village by 30 June 2015 | Sephukhubje Street Paving | 400000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed and designs progress at 0%. | Non adherence to procurement plan | Tender to be awarded and design be finalised in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of street paving at Matshelapata village by 30 June 2015 | Matshelapata Street Paving | 400000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed and designs progress at 0%. | Non adherence to procurement plan | Tender to be awarded and design be finalised in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of street paving at Shawela village by 30 June 2015 | Shawela Street Paving | 400000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed and designs progress at 0%. | Non adherence to procurement plan | Tender to be awarded and design be finalised in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of street paving at Sekgop (Maboying) village by 30 June 2015 | Sekgopo Maboying Street Paving | 400000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointedand designs progress at 0%. | Non adherence to procurement plan | Tender to be awarded and design be finalised in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of street paving at Tlhotlhokwe village by 30 June 2015 | Tlhotlhokwe Street Paving | 400000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointedand designs progress at 0%. | Non adherence to procurement plan | Tender to be awarded and design be finalised in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of street paving at Shamfana village by 30 June 2015 | Shamfana Street Paving | 400000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed and designs progress at 0%. | Non adherence to procurement plan | Tender to be awarded and design be finalised in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of street paving at Kherobene village by 30 June 2015 | Kherobeng Street Paving | 400000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointedand designs progress at 0%. | Non adherence to procurement plan | Tender to be awarded and design be finalised in the 3rd quarter | 0 | INDEP / B & T
34 | Access to Sustainable Basic Services | Contribution from MIG | Construction of Sport complex at Shaamiriri Village by 12 December 2014. | Shaamiriri Sport Complex | 1700000 | 01/07/2014 | 12/12/2014 | 100% Complete | Target not achieved. Construction stage: 95% | Non adherence to procurement plan | Apply penalties | 2208757 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Construction of library at Senwamokgope township by 31 March 2015 | Senwamokgope library | 2100000 | 01/07/2014 | 31/03/2015 | Appoint contractors and resume with construction up to 10% | Target not achieved. Construction at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | R132 600.00 (Professional fees) | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Construction of library at Sekgopo by 31 March 2015 | Sekgopo library | 2100000 | 01/07/2014 | 31/03/2015 | Appoint contractors and resume with construction up to 10% | Target not achieved. Contractors not appointed and. Construction at 0%. | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | R142 363.00 (Professional fees) | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of library at Mokwakwaila by 30 June 2015 | Mokwakwaila library | 375000 | 01/07/2014 | 30/06/2015 | Appoint service provider and resume with designs at 30% progress | Target not achieved. Service provider not appointed and designs progress at 0%. | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of Ga-Kgapane stadium by 31 March 2015 | Kgapane stadium | 3600000 | 01/07/2014 | 31/03/2015 | Appoint contractors and resume with construction up to 10% | Target not achieved. Service provider not appointed. Construction at 0%. | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | R1 726 644.00 (Professional fees) | INDEP / B & T
54 | Access to Sustainable Basic Services | Property Services | Refurbish municipal workshop and stores by 12 December 2014 | Refurbishment of Municipal Workshop and stores | 500000 | 01/07/2014 | 12/12/2014 | Project management and construction monitoring to achieve progress of 100% | Target not achieved. Construction at 0% | Tender was re-advertised for compliance with SCM regulations | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
54 | Access to Sustainable Basic Services | Property Services | Renovate 6 Rottaba Cottages in Modjadjiskloof by 31 March 2015 | Rehabilitation of Rotaba Cottages | 500000 | 01/10/2014 | 31/03/2015 | Appointment of service provider. Project management and construction monitoring to achieve progress of 10% | Target not achieved. Service provider not appointed. Construction at 0%. | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
52 | Access to Sustainable Basic Services | Electricity Distribution | Upgrading of electricity infrastructure at Modjadjiskloof for compliance with NER by 31 March 2015 | Upgrade of Electricity to NER Standards | 5326472 | 01/07/2014 | 31/03/2015 | Appoint contractors and resume with construction up to 25% | Target not achieved. Contractors not appointed. Construction at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | R790 075.00 (Professional fee) | INDEP / B & T
25 | Access to Sustainable Basic Services | Street Lighting | Erection of two (2) highmast lights at Moroatshehla village by 30 September 2014. | Moroatshehla Highmast Lights | 105000 | 01/07/2014 | 30/09/2014 | Erection of highmast lights | Target not achieved. Erection of highmast lights incomplete. | Backlog in delivery of lights cause by strike in the metal industry | Construct self-built electricity supply | 68639 | INDEP / B & T
25 | Access to Sustainable Basic Services | Street Lighting | Erection of two (2) highmast lights at Thakgalang village by 30 September 2014 | Thakgalang Highmast Lights | 105000 | 01/07/2014 | 30/09/2014 | Erection of highmast lights | Target not achieved. Erection of highmast lights incomplete. | Backlog in delivery of lights cause by strike in the metal industry | Construct self-built electricity supply | 69810 | INDEP / B & T
25 | Access to Sustainable Basic Services | Street Lighting | Erection of two (2) highmast lights at Mapaana village by 30 September 2014 | Mapaana Highmast Lights | 105000 | 01/07/2014 | 30/09/2014 | Erection of highmast lights | Target not achieved. Erection of highmast lights incomplete. | Backlog in delivery of lights cause by strike in the metal industry | Construct self-built electricity supply | 69810 | INDEP / B & T
25 | Access to Sustainable Basic Services | Street Lighting | Erection of two (2) highmast lights at Shamfana village by 30 September 2014 | Shamfana Highmast Lights | 105000 | 01/07/2014 | 30/09/2014 | Erection of highmast lights | Target not achieved. Erection of highmast lights incomplete. | Backlog in delivery of lights cause by strike in the metal industry | Construct self-built electricity supply | 68639 | INDEP / B & T
25 | Access to Sustainable Basic Services | Street Lighting | Erection of two (2) highmast lights at Mamokgadi village by 30 September 2014 | Mamokgadi Highmast Lights | 105000 | 01/07/2014 | 30/09/2014 | Erection of highmast lights | Target not achieved. Erection of highmast lights incomplete. | Backlog in delivery of lights cause by strike in the metal industry | Construct self-built electricity supply | 68639 | INDEP / B & T
25 | Access to Sustainable Basic Services | Street Lighting | Erection of two (2) highmast lights at Malematja village by 30 September 2014 | Malematja Highmast Lights | 105000 | 01/07/2014 | 30/09/2014 | Erection of highmast lights | Target not achieved. Erection of highmast lights incomplete. | Backlog in delivery of lights cause by strike in the metal industry | Construct self-built electricity supply | 69810 | INDEP / B & T
25 | Access to Sustainable Basic Services | Street Lighting | Erection of two (2) highmast lights at Mamphakathi village by 30 September 2014 | Mamphakati Highmast Lights | 105000 | 01/07/2014 | 30/09/2014 | Erection of highmast lights | Target not achieved. Erection of highmast lights incomplete. | Backlog in delivery of lights cause by strike in the metal industry | Construct self-built electricity supply | 69810 | INDEP / B & T
25 | Access to Sustainable Basic Services | Street Lighting | Erection of ten(10) highmast lights in various villages by 30 September 2014 | Highmast Lights in 10 villages | 6000000 | 01/07/2014 | 30/09/2014 | Erection of highmast lights | Target not achieved. Highmast lights not erected. | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
25 | Access to Sustainable Basic Services | Street Lighting | Erection of two (2) highmast lights at Abel village by 30 September 2014 | Abel Highmast Lights | 105000 | 01/07/2014 | 30/09/2014 | Erection of highmast lights | Target not achieved. Erection of highmast lights incomplete. | Backlog in delivery of lights cause by strike in the metal industry | Construct self-built electricity supply | 68639 | INDEP / B & T
34 | Access to Sustainable Basic Services | Waste Management / Refuse removal | Construction of landfill site at Maphalle village by 31 March 2015 | Landfill Site | 5000000 | 01/07/2014 | 31/03/2015 | Appoint contractors for construction and progress at 20% | Target not achieved. Contractors not appointed. Construction at 0% | Non adherence to procurement plan | Tender was advertised for reviewing designs | R960 000.00 (Professional fees) | INDEP / B & T
22 | Improved Local Economy | Community & Social | To organize and conduct environmental programme within the municipality quarterly | Environmental Programmes | 100000 | 01/07/2014 | 30/06/2015 | Coordinate and conduct enviromental related events and campaigns (1 per quarter) | Target achieved. 1 x environmental campaign held. | n/a | n/a | R48 056.89 | COMM
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Construction of paving and fence at Senwamokgope community hall by 31 March 2015 | Senwamokgope Comm Hall Paving and Fencing | 1500000 | 01/07/2014 | 31/03/2015 | Appoint service provider and construction at 25% progress | Target not achieved. Contractors not appointed. Construction at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Planning and designing of community hall for Ward 2 by 31 March 2015 | Ward 2 Community Hall | 280000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Planning and designing of community hall for Ward 5 by 31 March 2015 | Ward 5 Community Hall | 280000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Planning and designing of community hall for Matswi village by 31 March 2015 | Matswi Community Hall | 280000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Planning and designing of community hall for Mohlele village by 31 March 2015 | Mohlele Community Hall | 280000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Planning and designing of community hall for Mamaila (Kolobetona) village by 31 March 2015 | Mamaila - Kolobetona Community Hall | 280000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Planning and designing of community hall for Shamfana village by 31 March 2015 | Shamfana Community Hall | 280000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Planning and designing of new community hall for Rotterdam by 31 March 2015 | Rotterdam (new Community hall) | 2400000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed. Designs progress at 0% | Delays caused by land dispute | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Construction of Ga-Kgapane Parks (Below Civic Centre and Mesopotamia) by 31 March 2015 | Ga-Kgapane Parks | 500000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Speed up the process of evaluation and adjudication | 0 | COMM
34 | Access to Sustainable Basic Services | Sports & Recreation | Enhancement & Beautification of Modjadjiskloof Town Entrances by 30 June 2015 | Enhancement & Beautification of Town Entrances | 700000 | 01/07/2014 | 30/06/2015 | Appoint service provider and construction progress at 30% | Target not achieved. Service provider not appointed. Construction at 0%. | Service provider for designs has not yet started due to SLA which is not yet signed | SCM provide Legal with documents for development of SLA | 0 | COMM
34 | Access to Sustainable Basic Services | Sports & Recreation | Installation of 3 outdoor gyms at GaKgapane, Modjadjiskloof and Senwamokgope by 31 March 2015 | Outdoor Gyms x3 (Kgapane, Senwamokgope &Modjadjiskloof) | 1600000 | 01/07/2014 | 31/03/2015 | Appoint service provider and installation progress at 30% | Target not achieved. Service provider not appointed. Installation progress at 0% | Non adherence to procurement plan | Speed up the process of appointment | 0 | COMM
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of sport complex for Mamanyoha village by 30 June 2015 | Mamanyoha Sports Complex | 500000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of sport complex for Rotterdam village by 30 June 2015 | Rotterdam Sports Complex | 500000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of youth centre for Sekgopo village by 30 June 2015 | Sekgopo Youth Centre | 320000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of youth centre for Ga-Kgapane township by 30 June 2015 | Kgapane Youth Centre | 320000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of youth centre for Mokwakwaila village by 30 June 2015 | Mokwakwaila Youth Centre | 320000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of youth centre for Roerfontein village by 30 June 2015 | Roerfontein Youth Centre | 320000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
31 | Access to Sustainable Basic Services | Sports & Recreation | Construction of outdoor gym at Maphalle by 31 March 2015 | Maphalle Outdoor gym | 550000 | 01/07/2014 | 31/03/2015 | Appoint service providers and construction progress at 25% | Target not achieved. Service provider not appointed. Construction progress at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
31 | Access to Sustainable Basic Services | Sports & Recreation | Construction of outdoor gym at Sekgopo village by 31 March 2015 | Sekgopo Outdoor gym | 550000 | 01/07/2014 | 31/03/2015 | Appoint service providers and construction progress at 25% | Target not achieved. Service provider not appointed. Construction progress at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
31 | Access to Sustainable Basic Services | Sports & Recreation | Construction of outdoor gym at Abel village by 31 March 2015 | Abel Outdoor gym | 550000 | 01/07/2014 | 31/03/2015 | Appoint service providers and construction progress at 25% | Target not achieved. Service provider not appointed. Construction progress at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
31 | Access to Sustainable Basic Services | Sports & Recreation | Construction of outdoor gym at Ga-Kuranta village by 31 March 2015 | Kuranta Outdoor gym | 550000 | 01/07/2014 | 31/03/2015 | Appoint service providers and construction progress at 25% | Target not achieved. Service provider not appointed. Construction progress at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Design and construction of sports ground at Ga-Kgapane by 30 June 2015 | Kgapane Sports ground | 5000000 | 01/07/2014 | 30/06/2015 | Appoint consultants for professional services. | Target not achieved. Consultants not appointed for professional services | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Libraries and Archives | Procuring and installation of modular issue counters at Soetfontein library 31 March 2015 | Modular issue Counters (2) | 80000 | 01/07/2014 | 31/03/2015 | Advertise and appoint service provider for installation | Taget not achieved. Service provider not appointed for installation. | Non adherence to procurement plan | Speed up the appointment process | 0 | COMM

## LED PROJECTS
KPA 3 LOCAL ECONOMIC DEVELOPMENT PROJECTS OUTPUT 3: IMPLEMENTATION OF THE COMMUNITY WORK PROGRAMME
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project / Initiative | Budget 2014/2015 | Start Date | Completion Date | Midyear target end Dec 2014 | Achievements / Progress Midyear Ending Dec 2014 | Challenges | Intervention | Expenditure | Project Owner
22 | Access to Sustainable Basic Services | Planning and Development | Design and construction of fence and admin block at the new show ground by 30 June 2015 | GLM Show Ground | 6000000 | 01/07/2014 | 30/06/2015 | Appoint Architectures for professional services. | Target not achieved. Architectures not appointed. | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Design and construction of market stalls at Sekgopo by 30 June 2015 | Sekgopo Market stalls | 800000 | 01/07/2014 | 30/06/2015 | Appoint consultants for professional services. | Target not achieved. Consultants not appointed. | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Design and construction of market stalls at Sekgosese by 30 June 2015 | Sekgosese Market stalls | 800000 | 01/07/2014 | 30/06/2015 | Appoint consultants for professional services. | Target not achieved. Consultants not appointed. | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Design and construction of market stalls at Maphalle by 30 June 2015 | Maphalle Market stalls | 800000 | 01/07/2014 | 30/06/2015 | Appoint consultants for professional services. | Target not achieved. Consultants not appointed. | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Design and construction of market stalls at Ga-Kgapane by 30 June 2015 | Kgapane Market stalls | 800000 | 01/07/2014 | 30/06/2015 | Appoint consultants for professional services. | Target not achieved. Consultants not appointed. | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Design and construction of market stalls at Mamaila (Phaphadi) by 30 June 2015 | Mamaila-Phaphadi Market stalls | 800000 | 01/07/2014 | 30/06/2015 | Appoint consultants for professional services. | Target not achieved. Consultants not appointed. | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Design and construction of market stalls at Madumeleng by 30 June 2015 | Madumeleng Market stalls | 800000 | 01/07/2014 | 30/06/2015 | Appoint consultants for professional services. | Target not achieved. Consultants not appointed. | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Design and construction of market stalls at Khosuthopa by 30 June 2015 | Khosuthopa Market stalls | 800000 | 01/07/2014 | 30/06/2015 | Appoint consultants for professional services. | Target not achieved. Consultants not appointed. | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
22 | Improved Local Economy | Local Economic Development | Identify and implement SMME support initiatives by 30 June 2015 | Support of SMMEs' | 200000 | 01/07/2014 | 30/06/2015 | Approval of support initiatives and implementation thereof | Target achieved. Support initiatives have been identified | None | None | 14792 | INDEP
22 | Improved Local Economy | Local Economic Development | Participate in the annual Tourism Indaba by 30 June 2015 | Tourism Indaba | 150000 | 01/07/2014 | 30/06/2015 | Implementation of resolutions of the Tourism Indaba report | Target achieved. Resolutions of the Tourism Indaba report implemented. The next indaba to be attended in May 2015 | None | None | 0 | INDEP
22 | Improved Local Economy | Local Economic Development | Promote tourism activities within GLM by 30 June 2015 | Tourism Development | 400000 | 01/07/2014 | 30/06/2015 | Approval of tourism development initiatives and implementation thereof | Target not achieved. Tourism development initiatives not yet implemented. | Delay in identification of initiatives | Identification of initiatives for implementation | 0 | INDEP
22 | Improved Local Economy | Planning & Development | Implement agricultural development initiatives by 30 June 2015 | Agricultural development | 60000 | 01/07/2014 | 30/06/2015 | Advertise for appointment of professional service provider | Target not achieved. Service provider not appointed | Non adherence to procurement plan | Identify beneficiaries for distribution of seedlings. | 6000 | INDEP / B & T
22 | Improved Local Economy | Planning & Development | Identify business support initiatives by 30 June 2015 | Business Support | 60000 | 01/07/2014 | 30/06/2015 | Approval of business support initiatives and implementation thereof | Target not achieved. Businnes support initiatives not implemented. | Delay in identification of initiatives | Identification of initiatives for implementation | 0 | INDEP
22 | Improved Local Economy | Planning & Development | Develop entrance and fencing for Manokwe cave by 30 June 2015 | Development of Manokwe cave | 400000 | 01/07/2014 | 30/06/2015 | Advertise for appointment of professional service provider | Target achieved. Tender advertised | n/a | n/a | 0 | INDEP / B & T
22 | Improved Local Economy | Planning & Development | Support emerging piggery farmers within GLM by 30 June 2015 | GLM Piggery Project | 400000 | 01/07/2014 | 30/06/2015 | Approval and implementation of support initiatives | Target not achieved. Support initiatives have been identified but not yet implemented | None | Implementation of the support initiatives | 0 | INDEP
22 | Improved Local Economy | Planning & Development | Award performance in agricultural sector by 12 December 2014 | Agricultural Awards | 120000 | 01/07/2014 | 12/12/2014 | Conduct award ceremony | Target achieved. Agriculture Awards ceremony was held | n/a | n/a | 192051 | INDEP
22 | Improved Local Economy | Planning & Development | Compile feasibility study for picnic sites in GLM by 30 June 2015 | Feasibility Study for Picnic Sites | 400000 | 01/07/2014 | 12/12/2014 | Advertise for appointment of professional service provider | Target achieved. Tender advertised | n/a | n/a | 0 | INDEP / B & T
34 | Improved Local Economy | Sports and Recreation | To organise the rainmaking ceremony by 12 December 2014 | Rain making ceremony | 100000 | 01/07/2014 | 12/12/2014 | Participate in the celebratory activities | Target not achieved. Did not participate in the ceremonies. | Closed ceremonies were held and municipality was not engaged / invited | Engage the ceremony organisers. | 0 | COMM
34 | Improved Local Economy | Sports and Recreation | To organise the Wolkberg sports day by 31 March 2015 | Wolkberg Sports day | 120000 | 01/07/2014 | 31/03/2015 | Games held for various sporting codes | Target achieved. Games for various sporting codes held. | n/a | n/a | 0 | COMM
34 | Improved Local Economy | Sports and Recreation | To organise and host various sport codes by 30 June 2015 | Sports Activities | 200000 | 01/07/2014 | 30/06/2015 | Sporting activities held | Target achieved. Implementation plan is in place and sporting codes are being held | n/a | n/a | R8 771.60 | COMM
34 | Improved Local Economy | Sports and Recreation | To organise event for cultural activities by 31 March 2015 | Cultural Activities | 150000 | 01/07/2014 | 31/03/2015 | Event held for various cultural activities | Target achieved. Plan in place and activities are being held | n/a | n/a | R75 000.00 | COMM
34 | Improved Local Economy | Sports and Recreation | To organise Choral Music Competition by 31 March 2015 | Choral Music Competition | 100000 | 01/07/2014 | 31/03/2015 | Group stages competition | Target not achieved. Plan is in place and group stages not yet started | Choirs still registering | speed up registration | NONE | COMM
22 | Improved Local Economy | Planning and Development | To demarcate and peg sites at Goudplaas by 31 March 2015 | Dermacation of sites (Goudplaas) | 700000 | 01/07/2014 | 31/03/2015 | Appointment of professional service provider and progress of dermacation at 20% | Target not achieved. Professional service provider not appointed. Demarcation Progress at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 178100 | INDEP / B & T
22 | Improved Local Economy | Planning and Development | To demarcate and peg sites at Nooitedaght by 31 March 2015 | Dermacation of sites (Nooitedaght Farm) | 600000 | 01/07/2015 | 31/03/2015 | Appointment of professional service provider and progress of dermacation at 20% | Target not achieved. Professional service provider not appointed. Demarcation Progress at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
22 | Improved Local Economy | Planning & Development | Conveyance of unregistered municipal properties by 31 March 2015 | Conveyance of Unregistered GLM properties | 60000 | 01/07/2014 | 31/03/2015 | Appoint service provider for conveyancing and progress at 20% | Target not achieved. Professional service provider not appointed. Demarcation Progress at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
22 | Improved Local Economy | Planning & Development | Implement Land-use Management Scheme by 30 June 2015 | Land-use Management | 500000 | 01/07/2014 | 30/06/2015 | 100% (# of complaints received / # of complaints resolved) | Target not achieved. 33% (9 received / 3 resolved) | Boundary disputes | Site pegging | 0 | INDEP
22 | Improved Local Economy | Planning & Development | Planning for renewal of Modjadjiskloof CBD by 30 June 2015 | Modjadjiskloof Urban Renewal Plan | 400000 | 01/07/2014 | 30/06/2015 | Appointment of professional service provider | Target not achieved. Professional service provider not appointed. | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
22 | Improved Local Economy | Planning & Development | Scan building plans for uploading in the GIS by 31 March 2015 | Scanning of building plans into GIS | 100000 | 01/10/2014 | 31/03/2015 | Scanning of building plans, uploading in the GIS and progress at 50% | Target not achieved. Scanning of building plan, uploading of plans in GIS progress at 0% | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 0 | INDEP / B & T
Note on F15: Nomsa Makhubela:
Note on E16: Nomsa Makhubela: individuals

## MFMV KPI
KPA 4 MUNICIPAL FINANCIAL VIABILITY KEY PERFORMANCE INDICATORS OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY
Vote Nr | Strategic Objective | Progranmes | Measurable Objectives | Performance measures | Baseline / Status | Budget 2014/2015 | Mid year target end Dec 2014 | Achievements / Progress mid year end Dec 2014 | Challenges | Interventions | Expenditure | Responsible Person
50 | Sustainable Financial Institution | Budget and Reporting | To ensure that financial information is supplied to relevant authorities by 30 June 2015. | Financial information supplied to relevant authorities by 30 June 2015 | Information was submitted by 10 June 2015 | Operational | n/a | n/a | n/a | n/a | 0 | CFO
50 | Sustainable Financial Institution | Budget and Reporting | To ensure that quartely financial statements are prepared within 14 days after the end of each quarter. | # of quarterly financial statements and submitted to the relevant authorities | 25% | Operational | 2 financial statements (100%) | Target not achieved. 1x financial statements prepared and submitted to relevant authorities (50%) | Opening balances can only be moved after audit | 2nd financial statements to be prepared and submitted end January | 0 | CFO
50 | Sustainable Financial Institution | Supply Chain Management | To ensure payment of service providers within 30 days of the submission of invoices. | % of payments of service providers made within 30 days (# of invoices received / # of invoices paid. | 100% | Operational | 100% | Target achieved. 100% payment within 30 days | n/a | n/a | 0 | CFO
50 | Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality within the financial year | % capital budget spent as approved by Council | 70% | Operational | 50% | Target not achieved. 34% spent. | Non adherence to procurement plan | Award tenders in the 3rd quarter | 34% | CFO/INDEP/MM
50 | Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality within the financial year | % MIG expenditure | 70% | 46950000 | 50% | Target not achieved. 21.4% spent. | Non adherence to procurement plan | Award tenders in the 3rd quarter | 16.21% | CFO/INDEP/MM
50 | Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality within the financial year | % FMG expenditure | 90% | 1550000 | 50% | Target not achieved. 10% spent. | Internship posts not filled. | To fill the posts by 01 February 2015 | 9.72% | CFO/INDEP/MM
50 | Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality within the financial year | % MSIG expenditure | 100% | 890000 | 50% | Target not achieved. 27% spent. | Non adherence to procurement plan | Tender to be awarded in the 3rd quarter | 27.04% | CFO/INDEP/MM

## MFMV PROJECTS
KPA 4 MUNICIPAL FINANCIAL VIABILITY PROJECTS OUTCOME NINE (OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY)
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project / Initiative | Budget 2014/2015 | Start Date | Completion Date | Midyear milestones Qtr Ending Dec 2014 | Achievements / Progress mid year end Dec 2014 | Challenges | Intervention | Expenditure | Project Owner
50 | Sustainable Financial Institution | Budget and Treasury | Installation of GPS system and training of end users by 31 March 2015 | GPS system and training | 80000 | 01/07/2014 | 31/03/2015 | Appointment of service provider to supply, instal and conduct training | Target not achieved. Service provider not appointed. No installation. Training not conducted. | Non adherence to procurement plan | Tender to be awarded in the 3rd Qtr | 0 | CFO
50 | Sustainable Financial Institution | Budget and Treasury | Installation of security glass at Senwamokgope sub-office by 30 September 2014 | Security glass at Senwamokgope sub office | 8000 | 01/07/2014 | 30/09/2014 | Request quotations for procurement, appoint service provider, supply and installation of security glass | Target not achieved. Quotations not requested. Service provider not appointed. Security glass not installed. | Non adherence to procurement plan | Tender to be awarded in the 3rd Qtr | 0 | CFO
50 | Sustainable Financial Institution | Budget and Treasury | To conduct environmental impact assessment, purchase new tanks, pumps and shades by 31 March 2015 | New tanks, pumps and shades | 550000 | 01/07/2014 | 31/03/2015 | Conduct environmental impact assessment | Target not achieved. Environmental Impact Assessment not conducted | Non adherence to procurement plan | Tender to be awarded in the 3rd Qtr | 0 | CFO
54 | Access to Sustainable Basic Services | Property Services | To purchase 1 concrete mixer by 30 September 2014 | Concrete Mixer | 20000 | 01/07/2014 | 30/09/2014 | Develop, submit specifications to SCM and purchase | Target not achieved. Concrete mixer not purchased. | Non adherence to procurement plan | Tender to be awarded in the 3rd Qtr | 0 | INDEP / B & T
52 | Access to Sustainable Basic Services | Electricity Distribution | Purchasing of electrical tools and equipment by 30 September 2014 | Tools and equipment | 200000 | 01/07/2014 | 30/09/2014 | Develop, submit specifications to SCM and purchase | Target not achieved. Tools and equipment not purchased. | Non adherence to procurement plan | Tender to be awarded in the 3rd Qtr | 0 | INDEP / B & T
50 | Sustainable Financial Institution | Indigent Management | To register qualifying indigents 30 June 2014 | Updating of Indigent Register | Operational | 01/07/2014 | 30/06/2015 | Collection of information on indigent households and update the register | Target achieved. Information collected and indigent register updated | n/a | n/a | Operational | CFO
50 | Sustainable Financial Institution | Revenue Management | Review, adopt and implement Revenue Enhancement Strategy 30 June 2015 | Revenue Enhancement Strategy | Operational | 01/07/2014 | 30/06/2015 | Implementation of the adopted Revenue Enhancement Strategy | Target achieved. Revenue Enhancement Strategy implemented | n/a | n/a | Operational | CFO
50 | Sustainable Financial Institution | Revenue Management | To update household billing system information 30 Sept 2014 and implement | Data cleansing | Operational | 01/07/2014 | 30/06/2015 | Approval by Council | Target not achieved. Billing system not yet approved by Council | Service provider charging high prices | Price negotiation | Operational | CFO
50 | Sustainable Financial Institution | Asset Management | To monitor the process of unbundling and make progress report by 30 June 2015 | Unbundling of Infrastructure Assets to update the asset register | Operational | 01/07/2014 | 30/06/2015 | Appointment of professional service provider for unbundling of municipal assets and updating of GRAP compialnt asset register. | Target chieved. Service provider appointed. Asset register updated | n/a | n/a | Operational | CFO
50 | Sustainable Financial Institution | Asset Management | Updating of valuation roll by 30 June 2015 | Valuation Roll | Operational | 01/07/2014 | 30/06/2015 | Conduct assessment of supplementary valuation roll. | Target achieved. Supplementary valuation roll conducted | n/a | n/a | 240 | CFO

## GGPP PROJECTS
KPA 5 GOOD GOVERNANCE AND PUBLIC PARTICIPATION PROJECTS OUTPUT 5: DEEPEN DEMOCRACY THROUGH A REFINED WARD COMMITTEE MODEL, OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY)
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project / Initiative | Budget 2014/2015 | Start Date | Completion Date | Midyear milestones Ending Dec 2014 | Achievements/Progress made end Dec 2014 | Challeges | Intervention | Expenditure | Project Owner
34 | Improved Governance and Organisational Excellence | Good Governance | Manage events effectively by 30 June 2015 | Communication and event management | 100000 | 01/07/2014 | 30/06/2015 | Manage events and 50% of the budget spent | Target not achieved. No communication programme / event was done. | Lack of capacity | Appoint Admin Officer: Comm & Events | 0 | MM
40 | Improved Governance and Organisational Excellence | Good Governance | To award academic excellent performers by 30 June 2015 | Municipal Mayor’s excellent award | 200000 | 01/01/2015 | 31/03/2015 | n/a | n/a | n/a | n/a | 0 | MM
34 | Improved Governance and Organisational Excellence | Good Governance | Attending of conference and congresses | Conference and congresses | 100000 | 01/07/2014 | 30/06/2015 | Adrehence to procedures and attend conference and congresses | Target achieved. Employees who attend congresses and conferences adhere to procedures. | n/a | n/a | 59335 | CORPS
46 | Improved Governance and Organisational Excellence | Skills Development/Training | To improve capacity of councillors by 30 June 2015 | Capacity building: councillors | 318600 | 01/10/2014 | 30/06/2015 | Conduct need analysis and submit specification to SCM | Target achieved. Need analysis of Councillors conducted. Specifications submitted to SCM | n/a | n/a |  | CORPS
40 | Improved Governance and Organisational Excellence | Batho Pele | To implement Batho Pele principles by 31 March 2015 | Batho Pele strategies | 30798 | 01/10/2014 | 12/12/2014 | n/a | n/a | n/a | n/a | 18200 | MM
40 | Improved Governance and Organisational Excellence | Bursary Scheme | To fund good performing student from the needy families | Bursary scheme council | R2 000 000 | 01/07/2014 | 30/06/2015 | Advertise for applications and pay costs- Payment of costs | Target achieved. Bursary scheme was advertised. Payments are made for the existing bursary holders. | n/a | n/a | 158321 | MM
54 | Improved Governance and Organisational Excellence | Humanitarian | To enhance humanitarian by 30 June 2014 | Humanitarian Aid | 100000 | 01/07/2014 | 30/06/2015 | 50% | Target achieved. 51.3% | n/a | n/a | 51321 | MM
40 | Improved Governance and Organisational Excellence | Communication | To issue 4 newsletters by 30/06/2015 | News letter | 350000 | 01/07/2014 | 30/06/2015 | 2 | Target not achieved. No news letter was issued. | Delay in compiling the newsletter | To issue before the end March 2015 | 0 | MM
40 | Improved Governance and Organisational Excellence | Communication | To purchase calenders and diaries by 30/09/2014 | Calendar and diaries | 20000 | 01/07/2014 | 30/09/2014 | 100% | Target not achieved. Calenders and diaries not purchased. | Non adherence to procurement plan | To purchase by end March 2015 | 0 | MM
40 | Improved Governance and Organisational Excellence | MM | Purchasing of Council vehicle for the Speaker by 31 March 2015 | Council Vehicle for the speaker | 700000 | 01/09/2014 | 31/09/2014 | Purchase and delivery of Council Vehicle for the speaker | Target not achieved. Council vehicle for the speaker not purchased. | Delay in the process of obtaining concurrence from the MEC s office | Purchase during 4th Qtr. | 0 | MM
40 | Improved Governance and Organisational Excellence | MM | Purchasing of two (2) gazebos by 30 September 2014 | 2 x Gazebos | 40000 | 01/07/2014 | 30/09/2014 | Sourcing of quatations and appointment of service provider for supply | Target not achieved. 2 x Gazebos not purchased. | Non adherence to procurement plan | To pruchase during the 3rd Qtr | 0 | MM
40 | Improved Governance and Organisational Excellence | MM | Purchasing of a scanner by 30 September 2014 | Scanner | 5000 | 01/07/2014 | 30/09/2014 | Sourcing of quatations and appointment of service provider for supply | Target not achieved. Scanner not purchased. | Scanner no longer required. | To be removed during budget adjustment | 0 | MM
40 | Improved Governance and Organisational Excellence | MM | Purchasing of a Cooler box by 30 September 2014 | Cooler box | 5000 | 01/07/2014 | 30/09/2014 | Sourcing of quatations and appointment of service provider for supply | Target not achieved. Cooler box not purchased. | Non adherence to procurement plan | To be purchased in the 3rd quarter | 0 | MM
54 | Improved Governance and Organisational Excellence | Property Services | Purchasing of 5 Aqua Coolers by 30 September 2014 | 5x Aqua coolers | 15000 | 01/07/2014 | 30/09/2014 | Sourcing of quatations and appointment of service provider for supply | Target not achieved. Scanner not purchased. | 5 x Aqua Coolers no longer required. | To be removed during budget adjustment | 0 | CORPS
54 | Improved Governance and Organisational Excellence | Property Services | Purchasing of shredding machine for registry by 30 September 2014 | Shredding machine for registry | 8000 | 01/07/2014 | 30/09/2014 | Sourcing of quatations and appointment of service provider for supply | Target not achieved. Shredding machine not purchased. | Non adherence to procurement plan | To be purchased in the 3rd quarter | 0 | MM
40 | Improved Governance and Organisational Excellence | Special Programmes | To facilitate youth development activities by 30 June 2015 | Youth desk activities | 280000 | 01/07/2014 | 30/06/2015 | Youth desk activities implementation | Target achieved. Youth desk activity program developed and implemented | n/a | n/a | 3900 | MM
40 | Improved Governance and Organisational Excellence | Special Programmes | To facilitate gender desk activities by 30 June 2016 | Gender desk activities | 200000 | 01/07/2014 | 30/06/2015 | Gender desk activities implementation | Target achieved. Gender desk activity program developed and implemented. | n/a | n/a | 105880 | MM
54 | Improved Governance and Organisational Excellence | Special Programmes | To facilitate Disability desk activities by 30 June 2017 | Disability desk activities | 100000 | 01/07/2014 | 30/06/2015 | Disability desk activities implementation | Target achieved. Disability desk activity program developed and implemented | n/a | n/a | 104100 | MM
40 | Improved Governance and Organisational Excellence | Special Programmes | To facilitate HIV/AIDS Council activities by 30 June 2018 | HIV & AIDS Council activities | 95000 | 01/07/2014 | 30/06/2015 | HIV/AIDS Council activity program implementation | Target achieved. HIV/AIDS Council activity program developed and implemented. | n/a | n/a | 0 | MM
40 | Improved Governance and Organisational Excellence | Special Programmes | Supporting initiatives for youth empowerment | Youth empowerment projects | 200000 | 01/07/2014 | 30/06/2015 | Youth empowerment initiatives implementation | Target achieved. Memorandum submitted. Requisitions for tools and equipments have been made | Project on hold | Resuscitation of the project | 0 | MM
14 | Access to Sustainable Basic Services | Libraries and Archives | Planning and designing of library for Shotong village by 30 June 2015 | Shotong Library | 300000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Appoint Service provider in the 3rd Qtr | 0 | INDEP / B & T
14 | Access to Sustainable Basic Services | Libraries and Archives | Planning and designing of library for Rotterdam village by 30 June 2015 | Rotterdam Library | 300000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Appoint Service provider in the 3rd Qtr | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Facilities | To do cemetry layout and fencing at Ga-Kgapane cemetry by 30 June 2015 | Kgapane Cemetry layout and fencing | 1500000 | 01/07/2014 | 30/06/2015 | Appoint service provider and progress 20% | Target not achieved. Service provider not appointed. Progress at 0% | Non adherence to procurement plan | Appoint Service provider in the 3rd Qtr | 0 | COMM
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of old age facility for Madumeleng village by 30 June 2015 | Madumeleng Old Age Facility | 220000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Appoint Service provider in the 3rd Qtr | 0 | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of old age facility for Ga-Kgapane township by 30 June 2015 | Kgapane Old Age Facility | 220000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Appoint Service provider in the 3rd Qtr | 0 | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of old age facility for Roerfontein village by 30 June 2015 | Roerfontein Old Age Facility | 220000 | 01/07/2014 | 30/06/2015 | Appoint service provider and designs progress at 30% | Target not achieved. Service provider not appointed. Designs progress at 0% | Non adherence to procurement plan | Appoint Service provider in the 3rd Qtr | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Supply and erection of bus shelter at Mokwakwaila - Ga-Kgapane road by 31 March 2015 | Mokwakwaila to Kgapane Bus shelter | 75000 | 01/07/2014 | 31/03/2015 | Appoint service provider and erection of bus shelter at 50% progress. | Target not achieved. Service provider not appointed and erection of bus shelter at 0% | Non adherence to procurement plan | Appoint Service provider in the 3rd Qtr | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Supply and erection of bus shelter at Malematsa - Rapitsi road by 31 March 2015 | Rapitsi to Malematsa Bus Shelter | 75000 | 01/07/2014 | 31/03/2015 | Appoint service provider and erection of bus shelter at 50% progress. | Target not achieved. Service provider not appointed and erection of bus shelter at 0% | Non adherence to procurement plan | Appoint Service provider in the 3rd Qtr | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Supply and erection of bus shelter at Lemondokop - Mamaila road by 31 March 2015 | Lemondokop to Mamaila via Phooko Bus Shelter | 75000 | 01/07/2014 | 31/03/2015 | Appoint service provider and erection of bus shelter at 50% progress. | Target not achieved. Service provider not appointed and erection of bus shelter at 0% | Non adherence to procurement plan | Appoint Service provider in the 3rd Qtr | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Supply and erection of bus shelter at Modjadji Head Kraal by 31 March 2015 | Modjadji Headkraal Bus Shelter | 75000 | 01/07/2014 | 31/03/2015 | Appoint service provider and erection of bus shelter at 50% progress. | Target not achieved. Service provider not appointed and erection of bus shelter at 0% | Non adherence to procurement plan | Appoint Service provider in the 3rd Qtr | 0 | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Supply and erection of bus shelter at Goudplaats village by 31 March 2015 | Goudplaas Bus Shelter | 75000 | 01/07/2014 | 31/03/2015 | Appoint service provider and erection of bus shelter at 50% progress. | Target not achieved. Service provider not appointed and erection of bus shelter at 0% | Non adherence to procurement plan | Appoint Service provider in the 3rd Qtr | 0 | INDEP / B & T
28 | Roads & Transport | Vehicle Licencing and Test | Purchasing of twotraffic Blue lights by 30 September 2014 | Traffic Blue lights (2) | 20000 | 1/07/2014 | 30/09/2015 | Appointment of service provider and procurement of goods | Target achieved. Traffic blue lights procured | n/a | n/a | R10 300.00 | COMM
28 | Roads & Transport | Vehicle Licencing and Test | Construction Of Testing room for learners Licences by 31 March 2015 | Testing room for learners Licence | 300000 | 01/07/2014 | 31/03/2015 | Appoint service providers and construction at 50% | Target not achieved. Progress at 0%. | The initial service provider has just finished and specification could not be made | Start with Specification | 0 | COMM
28 | Roads & Transport | Vehicle Licencing and Test | Purchasing of Traffic Sedan by 12 December 2014 | Traffic Sedan | 350000 | 01/07/2014 | 12/12/2014 | Appoint service provider and purchase traffic sedan | Target not achived, Service provider not appointed. | Non adherence to procurement plan | Appoint Service provider in the 3rd Qtr | 0 | COMM

## GGPP KPI's
KPA 5 GOOD GOVERNANCE AND PUBLIC PARTICIPATION KEY PERFORMANCE INDICATORS OUTCOME 9 (OUTPUT 5: DEEPEN DEMOCRACY THROUGH A REFINED WARD COMMITTEE MODEL, OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY)
Vote Nr | Strategic Objective | Programmes | Measurable Objectives | Performance measures | Baseline / Status | Budget 2014/2015 | Mid Year target end Dec 2014 | Achievements/ Progress made end Dec 2014 | Challenges | Interventions | Expenditure | Responsible Person
54 | Improved Governance and Organisational Excellence | Ward Committee | To ensure full participation of ward committees in annual ward programmes within the financial year. | # of ward committee programmes evaluated per month. | 29 | Operational | 29 | Target achieved. 29 | n/a | n/a | Operational | MM/CORPS
54 | Improved Governance and Organisational Excellence | Ward Committee | To ensure that community complaints are resolved within time frames. | % of complaints attended per month (# of community complaints received/ # of complaints atteneded to). | 100% | Operational | 100% | Target achieved. 100% complaints received and resolved.(7/7) | n/a | n/a | Operational | MM
54 | Improved Governance and Organisational Excellence | Local Imbizos | To implement Mayoral outreach programme by 30 June 2015 | # of local imbizos held by the Mayor by 30 June 2015. | 4 | 1000000 | 2 | Target achieved. 2 x Imbizo held. | n/a | n/a | 450629 | MM
54 | Improved Governance and Organisational Excellence | Local Imbizos | To ensure community participation in the affairs of the municipality within the financial year. | # of people who attend events | 100% | Operational | 100% | Target achieved. 100% | n/a | n/a | Operational | MM
54 | Improved Governance and Organisational Excellence | Traditional Leaders | To establish a good relationship with traditional leaders within the financial year. | # traditional leaders invited to take part in council meetings and activities. | 10 | Operational | 10 | Target achieved. 10 x Traditional leaders participate in Council activities | n/a | n/a | Operational | MM
54 | Improved Governance and Organisational Excellence | IT | To publicise official documents in the website within legislated time frames (Budget, IDP, SDBIP) | # of official documents published. | 3 | Operational | 6 | Target achieved. 6 documents are published on the website. | n/a | n/a | Operational | IT
54 | Improved Governance and Organisational Excellence | Communication | To promote effective and efficient communication within the financial year. | # of articles issued to the media quartely. | 1 | Operational | 2 | Target achieved. 10 articles published | n/a | n/a | Operational | Ass-Director (Mayor's office)/MM
54 | Improved Governance and Organisational Excellence | Communication | To promote effective and efficient communication within the financial year. | # of newslatters issued quarterly. | 4 | Operational | 2 | Target not achieved. Newsletter not issued. | Lack of capacity | Appointment of Adim Officer: Communication & events | Operational | Ass-Director (Mayor's office)/MM
54 | Improved Governance and Organisational Excellence | Legal | To ensure proper contract management within the financial year. | % appointed service providers with Service Level Agreement (# of service providers appointed/# of service providers with service level agreement) | 100% | Operational | 100% | Target achieved. 100%. All service providers appointed have service providers | n/a | n/a | Operational | CORPS/MM
46 | Improved Human Resource | Skills Development | To ensure effective implementation of the WSP within the financial year. | % employees trained as per the WSP | 100% | Operational | 50% | Target achieved. Employeed are trained as per WSP | n/a | n/a | Operational | CORPS
46 | Improved Human Resource | OHS | To ensure a health and safe working environment | # of wellness and OHS campaigns conducted per quarter | 4 | Operational | 2 | Target achieved. 1 x OHS campaign held | n/a | n/a | Operational | CORPS

## ROLL OVER PROJECTS
ROLL OVER PROJECTS COMMITTMENT REGISTER (OWN FUNDING)
No | Project / Initiative | Budget Adjustment / Contract Amount | Expenditure | Balance Rollover / Commitment | Progress
1 | Renovation of Municipal Workshop | 300000 | 0 | 300000 | Tender advertised
2 | Highmast lights in villages | 2847974 | 0 | 2847974 | Tender awarded
3 | Ga-Kgapane Stadium Bridge | 4450890.4 | 0 | 4450890.4 | Construction is at 11%
4 | Shawela Bridge | 4190924.84 | 0 | 4190924.84 | Construction is at 15%
5 | Graders | 4578947.36 | 0 | 4578947.36 | Procured
6 | Mothobeki Street Paving | 263675 | 0 | 263675 | 100% complete (planning)
7 | Mamaila Phaphadi Street Paving | 223222.22 | 0 | 223222.22 | Tender awarded
8 | Phooko Headkraal Street Paving | 239981.44 | 0 | 239981.44 | 100% complete (planning)
9 | Raphahlelo Street Paving | 223222.22 | 0 | 223222.22 | 100% complete (planning)
10 | Jamela Street Paving | 5300000 | 615553.9 | 4684446.1 | Construction is at 81%
11 | Sedibeng Street Paving | 4733836 | 852050 | 3881786 | Construction is at 94%
12 | Sefofotse Street Paving | 2080000 | 0 | 2080000 | Contract terminated. Tender to be readvertised
13 | Rotterdam (Duvula) Street Paving | 2916000 | 2055166 | 860834 | 100% complete
14 | Rotterdam (Mahunsi) Street Paving | 3337200 | 0 | 3337200 | Construction is at 8%
15 | Medingen Street Paving | 5953631.68 | 430087.8 | 5523543.88 | Project at halt. Construction was at 25%
16 | Matswi Street Paving | 7623720 | 2159446 | 5464274 | Construction at 75%
17 | Makaba Street Paving | 5126336.25 | 3496580 | 1629756.25 | Construction at 95%
18 | Access road to Mokwakwaila Taxi Rank | 159819.14 | 0 | 159819.14 | Tender awarded
19 | Modjadjiskloof Gabions | 840730 | 0 | 840730 | Construction at 5%
20 | Upgrading of Hill and Kerk Streets | 4320000 | 0 | 4320000 | The appointed service provider did not accept the contract
21 | Ga-Kgapane Sidewalks | 2000000 | 0 | 2000000 | To be re-advertised
22 | Upgrading electricty network to NER standard | 1000000 | 196416.27 | 803583.73 | 100% complete
23 | Intergrated Roads & Transport Plan | 650000 | 0 | 650000 | Tender awarded and under implementation
24 | Supply of Water Cart | 610014 | 0 | 610014 | Procured
25 | Supply of Bulldozer | 2600000 | 0 | 2600000 | Procured
26 | Supply of Tipper Truck | 566834 | 0 | 566834 | Procured
COMMITTMENT REGISTER (MIG FUNDING)
No | Project / Initiative | Budget Adjustment 2013/2014 | Expenditure | Balance Rollover / Commitment | Progress
27 | Thakgalang Street Paving | 4952938 | 1914168.73 | 3038769.27 | Project at halt. Construction was at 65%
28 | Rapitsi Street Paving | 1625921 | 1612178.46 | 13742.54 | 100% complete
29 | Modjadji Headkraal Street Paving | 3476490 | 2720948.28 | 755541.72 | Construction at 88%
30 | Ga-Kgapane Streets Upgrading | 478582.5 | 0 | 478582.5 | 100% complete (planning)
31 | Senwamokgope Streets Upgrading | 207821.91 | 0 | 207821.91 | 100% complete (planning)
32 | Modjadji Valley Streets Upgrading | 248111.11 | 0 | 248111.11 | 100% complete (planning)
33 | Kuranta Street Paving | 192111.11 | 0 | 192111.11 | 100% complete (planning)
34 | Mokgoba Street Paving | 229976.25 | 0 | 229976.25 | 100% complete (planning)
35 | Ratjeke Street Paving | 292846.15 | 0 | 292846.15 | 100% complete (planning)
36 | Senwamokgope Library | 221000 | 0 | 221000 | 100% complete (planning)
37 | Sekgopo Library | 237271.93 | 0 | 237271.93 | 100% complete (planning)
38 | Ga-Kgapane Stadium | 1000000 | 75190 | 924810 | Tender advertised

## SDBIP summary
SERVICE DELIVERY PERFORMANCE SUMMARY
The table and graph below illustrates service delivery performance of Greater Letaba Municipality against the National Key Performance Areas (NKPAs)
KPA | % Target achieved | No. of Applicable Indicators (Including projects) | No. of targets achieved | % Target achieved
Municipal Transformation and Organisational Development | 44.76% | 38 | 17 | 44.76%
Basic ServiceDelivery | 1.15% | 84 | 1 | 1.15%
Local Economic Development | 28.57% | 28 | 8 | 28.57%
Municipal Finance Management Viability | 31.25% | 16 | 5 | 31.25%
Good Governance and Public Participation | 46.51% | 43 | 20 | 46.51%
Overall % = 30.45%
The root cause of 30.45% performance of the municipality is mainly due to non-adherence to procurement plan. It is worth noting that in some instances of under-performance and delays in decision making has resulted in targets not being met. It can also be indicated that poor project management resulted in the underperformance of the capital programs. The Project Management Unit (PMU) needs to be capacitated with human resources and expertise to ensure that the municipality is not penalized for underperformance on allocations such as MIG. Poor record keeping by directorates is impacting on delays and integrity of performance information.

## Finance Report
GREATER LETABA LOCAL MUNICIPALITY
MID-YEAR FINANCIAL PERFORMANCE REPORT ENDING 31 DECEMBER 2014

## Capital Projects
Capital Projects
Budget Implementation
SUPPLY CHAIN MANAGEMENT IMPLEMENTATION (Report on the implementation of SDBIP)
Projects/Equipment to be implemented
| BUDGET | ROLL OVER | ACTUAL
750000
Council vehicles(Speaker) | 700000 |  |  | Specification not Submitted
Gazebo(2) | 40000 |  |  | Service
Scanner | 5000 |  |  | Specification not Submitted
Cooler box | 5000 |  |  | Specification not Submitted
Recording System / Video Camera | 0 | 0 | 0 | Specification Stage
Budget & Treasury Office | 638000
GPS System and Training | 80000 |  |  | Specification not Submitted
Security glass-senwamokgope cash office | 8000 |  |  | Awaiting submission of quotations
New tanks,pumps and shades | 550000 |  |  | Specification not Submitted
Printers (2) Salaries & Revenue Section |  | 34593 | 1560 | Service provider did not accept
Human Resource | 305000
Steel Filling Cabinets (2) | 30000 |  | 8205 | Procured
Office Furniture | 175000 |  |  | Advertised
Printers(4)Senwamokgope,Mokwakwaila,Kgapane and Main office | 100000 |  |  | Advertised
Information Technology | 550000
Server | 100000 |  |  | Specification Stage
Server Room Door | 50000 |  |  | Advertised
Laptop and Computer | 100000 |  |  | Advertised
Disaster Recovery Plan & Implementation | 300000 |  |  | Advertised
Property Services | 2078000
0
Decoration of Council Chamber (including foyer) (Budget adjustment) | . | 0 |  | Advertised
Fencing and Paving of Kgapane Old Sub-Office | . | 166200.07 |  | Work in progress
Aqua cooler(5) | 15000 |  |  | Quotation stage
Shedding Machine Registry | 8000 |  |  | Quotation stage
Concrete Mixer | 20000 |  |  | Advertised
Refurbishment of Municipal workshop and stores | 500000 |  |  | Advertised
Shelves for falling | 30000 |  |  | Specification not submitted
scanner | 5000 |  |  | Specification not submitted
Rehibilitation of rotaba Cottages | 500000 |  |  | Specification not submitted
Parking at Municipal office | 1000000 |  |  | On Advertsement
Finance & Admin/Others
Planning & Development
Economic Development/ Planning
6000000
GLM Show Ground | 6000000 |  |  | Advertised
Purchasing of land |  | 11000000 | 10580000 | Procured
Community Halls & Facilities | 11555000
Senwamokgope Comm Hall Paving and Fencing | 1500000 |  |  | On Advertsement
New Community Hall - Rotterdam | 2400000 |  |  | On Advertsement
Ward 2 Communnity Hall | 280000 |  |  | On Advertsement
Ward 5 Communnity Hall | 280000 |  |  | On Advertsement
Matshwi Community Hall | 280000 |  |  | On Advertsement
Mohlele Community Hall | 280000 |  |  | On Advertsement
Mamaila Kolobetona Community Hall | 280000 |  |  | On Advertsement
Shamfana Community Hall | 280000 |  |  | On Advertsement
Mokwakwaila to Kgapane Bus shelter | 75000 |  |  | Advertised
Rapitsi to Malematsa Bus Shelter | 75000 |  |  | Advertised
Lemondokop to Mamaila via Phooko Bus Shelter | 75000 |  |  | Advertised
Modjadji Headkraal Bus Shelter | 75000 |  |  | Advertised
Goedplaas Bus Shelter | 75000 |  |  | Advertised
Maphalle Market stalls | 800000 |  |  | Advertised
Sekgopo Market stalls | 800000 |  |  | Advertised
Sekgosese Market stalls | 800000 |  |  | Advertised
Kgapane Market stalls | 800000 |  |  | Advertised
Mamaila-Phaphadi Market stalls | 800000 |  |  | Advertised
Madumeleng Market stalls | 800000 |  |  | Advertised
Khosuthopa Market stalls | 800000 |  |  | Advertised
Libraries & Archives
680000
Modular Issue Counter | 80000 |  |  | Advertised
Shotong Library | 300000 |  |  | Advertised
Rotterdam Library | 300000 |  |  | Advertised
Versa Trollies |  | 50000 |  | Delayed delivery
Community & Social Services/Cemeteries | 1500000
Layout and Fencing of 3 cemetries in Kgapane | 1500000 | 0 | 61880 | Work in progress
Ga-Kgapane new cemetry earthworks |  |  | 401142
Street Lighting
6840000
Abel Highmast | 105000 | 420000 | 68639 | Work in Progress
Moroatshehla Highmast | 105000 | 420000 | 68639 | Awarded
Thakgalane Highmast | 105000 | 420000 | 69810 | Awarded
Maapana Highmast | 105000 | 420000 | 69810 | Awarded
Shamfana Highmast | 105000 | 420000 | 68639 | Awarded
Mmamokgadi Highmast | 105000 | 420000 | 68639 | Awarded
Malematja Highmast | 105000 | 420000 | 69810 | Awarded
Highmast in 10 Village | 6000000 |  |  | Advertised
Mamphakhathi Highmast | 105000 | 420000 | 69810 | Work in Progress
Motlhele,Rajeke & Mamanyoha Highmast - Roll Over |  |  |  | Work in Progress
Las Vegas,Rapitsi & Makaba Highmast - Roll Over | . |  |  | Work in Progress
Bellevue & Mpepule Highmast - Roll Over | . |  |  | Work in Progress
Madumeleng,Mokohokong,ramaroka,Setlaleng Highmast - Roll Over |  |  |  | Work in Progress
Raphahlelo,Phooko,Lomondokop Highmast - Roll Over | . |  |  | Work in Progress
Mokgoba Streetlights |  |  | 200000 | Work in Progress
Sports & Recreation
12940000
Ga- Kgapane Park | 500000 | 2889080 |  | Advertised
Enhancement & Beautifications of Town entrance | 700000 | 300000 |  | Awarded
Sekgopo Sport Complex |  | 5150000 |  | Completed
Outdoor gyms x 3 (Ga-Kgapane,Modjadjiskloof and Senwamokgope) | 1600000 |  |  | On Advertsement
Mamanyoha Sports Complex | 500000 |  |  | Advertised
Rotterdam Sports Complex | 500000 |  |  | Advertised
Sekgopo Youth Centre | 320000 |  |  | Advertised
Kgapane Youth Centre | 320000 |  |  | Advertised
Roerfontein Youth Centre | 320000 |  |  | Advertised
Mokwakwaila Youth Centre | 320000 |  |  | Advertised
Maphalle Outdoor gymnasium | 550000 |  |  | Advertised
Sekgopo Outdoor gymnasium | 550000 |  |  | Advertised
Abel Outdoor gymnasium | 550000 |  |  | Advertised
Kuranta Outdoor gymnasium | 550000 |  |  | Advertised
Madumeleng Old Age Facility | 220000 |  |  | Advertised
Kgapane Old Age Facility | 220000 |  |  | Advertised
Roerfontein Old Age Facility | 220000 |  |  | Advertised
Kgapane Sports ground | 5000000 |  |  | Advertised
WASTE WATER MANAGEMENT | 5000000
Transfer Stations |  | 1700000 | 95413 | Work in Progress
Skip Bins (14) |  | 350000 | 258312 | procured
Skip Truck |  | 900000 | 779531 | procured
Waste Bakkie |  | 250000 | 206162 | procured
Landfill Site | 5000000 | 1050000 | 960000 | Work in Progress
Storm Water | 3650000
Pedestrian William Kgatle Bridge | 150000 |  |  | Advertised
Low level Bridges | 1500000 | 200000 |  | Advertised
Modjadjiskloof Channels | 2000000 | 400000 |  | On Advertsement
Shawela Graveyard Bridge |  | 5800000 | 2012690 | Work in progress
Roads
53853000
Graders (2) |  | 5000000 | 4578948 | procured
TLB(Backhoe Loader) | 1500000 |  |  | procured
2 Toner Truck with Quarter Conopy | 300000 |  |  | Advertised
Plate Compator | 35000 |  |  | Advertised
Mothobekgi Paving | 6550000 | 450000 | 135229 | Advertised
Mamaila Phaphadi Paving | 6550000 | 450000 |  | Design stage
Phooko Head Kraal Paving | 3200000 | 320000 | 139693 | Advertised
Raphahlelo Head Kraal paving | 6550000 | 450000 | 179660 | Advertised
Jamela Street Paving -Consultants and Contractor | 0 | 5300000 | 3873166 | Work in Progress
Sedibeng Street Upgrading |  | 6000000 | 3057245 | Work in Progress
Water cart |  | 700000 | 611058 | procured
Tipper Truck | 1380000 |  |  | Awaiting appointment
Rehabilitation of Modjadjiskloof Streets | 5500000 |  | 88405 | Work in Progress
Rehabilitation of Ga-kgapane Streets | 5500000 |  |  | Advertised
Quick Cut machine | 28000 |  |  | Advertised
Rotterdam (Duvula) |  | 2916000 | 1405781 | Work in Progress
Mamaila (Kolobetona) |  | 2332800 |  | Completed
Rotterdam (Mahonsi) |  | 3337200 |  | Work in Progress
Modjadjiskloof Sidewalks | 3000000 |  |  | Advertised
Ga-Kgapane Sidewalks | 0 | 2000000 |  | Advertised
Hill & Kerk Streets Upgrading |  | 4320000 |  | Contractor did not accept due to underpricing
Medigen Street paving |  | 6156000 | 128260 | Work in Progress
Matshwi Street paving |  | 7623720 | 4275849 | Work in Progress
Bulldozer |  | 2600000 | 2600000 | procured
Access Road to Mokwakwaila Taxi Rank | 3100000 | 400000 |  | No appointment was made
Modjadjiskloof Gabions | 0 |  |  | awarded
Sekgopo Gabions | 1200000 |  |  | Advertised
Itieleng-Sekgosese Street Paving | 450000 |  |  | Evaluation stage
Refilwe Street paving | 450000 |  |  | Evaluation stage
Mmamakata Raselaka Street Paving | 450000 |  |  | Evaluation stage
Khosotupa Taxi Rank | 220000 |  |  | Awaiting appointment
Wholesaler Taxi Rank | 220000 |  |  | Evaluation stage
Mmaphakhati Taxi Rank | 220000 |  |  | Awaiting appointment
Lemondokop Street Paving | 450000 |  |  | Evaluation stage
Modjadji Ivory Route | 7000000 |  |  | On Advertsement
Maapana Street Paving - Roll Over | 0 | 610137.13 |  | Completed
Mandela Barlow-Thibeni Road -Roll Over |  | 365523 |  | Completed
Makaba Street Paving - Roll Over |  | 6048000 | 1085007 | Completed
Road Transport/Vehicle licensing & Testing
670000
Traffic Blue Lights(2) | 20000 |  |  | Procured
Testing Room for Leaner Licenses | 300000 |  | 68282 | work in progress
Traffic sedan | 350000 |  |  | Awaiting appointment
Electricity/Electricity Distribution
5526472
Upgrade of Electricity to NER Standards-NER Compliance | 5326472 |  | 790075 | Work in progress
Tools and Equipment | 200000 |  |  | No specification submitted
Maximum Demand Metering |  | 1000000 |  | Awarded
| 112535472 | 91979253.2 | 39135349 | 34.776
CONTRIBUTION FROM MIG
| 53440000 | 14316360.47 | 10986419 | 16.2146
Ga-Kgapane Street Upgrading | 8965000 | 478582.5 | 241633 | awarded
Senwamokgope Street Upgrading | 5400000 | 441000 |  | awarded
Upgrading of Streets-Thakgalane | 1500000 | 3535454.02 | 1644213 | work in progress
Upgrading of streets -Kuranta | 3600000 | 315789.47 |  | awarded
Upgrading of streets -Mokgoba | 5950000 | 364423.05 |  | work in progress
Upgrading of streets -Rapitsi |  | 447763.3 | 433836 | Completed
Upgrading of streets -Modjadji Valley | 5950000 | 248111.11 |  | awarded
Upgrading of streets -Sekgopo |  | 70230.46 |  | Completed
Shawela Graveyard Bridge |  | 74448.75 |  | awarded
Maphalle market stalls |  |  |  | Advertised
Mandela Park Road | 2000000 | 1415620.36 | 1839596 | work in progress
Modjadji Head Kraal Road | 1000000 | 3147156.34 | 2616777 | work in progress
Ratjeke Street Paving - Consultant | 5600000 | 400000 |  | awarded
Senwamokgope library | 2100000 | 221000 | 132600 | awarded
Sekgopo library | 2100000 | 237271.19 | 142363 | awarded
Mokwakwaila Library | 375000 |  |  | On Advertsement
Kgapane stadium | 3600000 |  | 1726644 | work in progress
Lebaka Sports complex
Sekgopo Sports complex |  | 504564.62 |  | Completed
Shaamiriri Sports complex | 1700000 | 2414945.3 | 2208757 | work in progress
Mokwakwaila stadium - Roll Over |  |  |  | Completed
Senwamokgope Stadium - Roll Over |  |  |  | Completed
Seatlaleng Street Paving | 400000 |  |  | Awaiting apointment
Mohlakong Street paving | 400000 |  |  | Awaiting apointment
Sephukhubje Street paving | 400000 |  |  | Evaluation stage
Matshelapata Street paving | 400000 |  |  | Evaluation stage
Shawela Street paving | 400000 |  |  | Evaluation stage
Sekgopo Street paving | 400000 |  |  | Evaluation stage
Tlotlokwe Street paving | 400000 |  |  | Evaluation stage
Shamfana Street Paving | 400000 |  |  | Evaluation stage
Kherobeng Street Paving | 400000 |  |  | Evaluation stage
| 165975472 | 106295613.67 | 50121768 | 50.9906
CAPITAL PROJECTS BUDGET PERFORMANCE ASSESSMENT
The municipality had fourty four (44) own funded rolled over projects and sixteen (16) MIG projects also rolled over. The fourty four projects which were rolled over amounts to R91 979 253.20. The sixteen MIG projects amounts to R14 316 360.47. The roll over projects will be included in the budget adjustment. The municipality has budgeted for one hindred and four (104) projects for the current financial year on own funding amounting to R112 535 472.00. MIG projects are twenty three (23) in number with the budget of R53 440 000.00. The total budget on projects for 2014/2015 financil year is R165 675 472.00, when added to rollover amount which is R106 295 613.67; the total budget of all the projects which will be implemented this financial year is R271 971 085.70.

## Expenditure
Expenditure
Expenditure per vote (section 71 of the MFMA)
Vote No | Description | Department | Budget | Actual | %
0014 | Library | Comm.Serv | 940699 | 557451 | 59.2592
0018 | Disaster Management | Comm.Serv | 1012209 | 291356 | 28.7842
0020 | Taxi Rank | Comm.Serv | 415125 | 157058 | 37.8339
0022 | Planning & Development | EDP | 10763261 | 3369159 | 31.3024
0028 | Vehicle Licensing & Testing | Comm.Serv | 11615940 | 4478953 | 38.5587
0029 | Roads | Tech.Serv | 13136818 | 4884590 | 37.1824
0032 | Comm Halls & Other | Comm.Serv | 418416 | 0 | 0
Non appointment of budgeted personnel.
0033 | Housing | EDP | 573596 | 252905 | 44.0911
0034 | Sports & Recreation | Comm.Serv | 8905577 | 2920600 | 32.7952
0036 | Public Toilets | Comm.Serv | 604481 | 241608 | 39.9695
0038 | Cemetries & Crematoriums | Comm.Serv | 335491 | 134653 | 40.1361
0039 | Finance & Admin IT | Corps | 3697677 | 946113 | 25.5867
0040 | Executive & Council | Corps | 34011145 | 13674639 | 40.2063
0041 | Finance & Admin Other | Corps Finance | 11365671 | 5100737 | 44.8785
0042 | Refuse Removal | Comm.Serv | 5447043 | 1820069 | 33.4139
0043 | Sewerage | Tech.Serv | 0 | 0 | 0
0046 | Finance & Admin HR | Corps | 5474789 | 2039276 | 37.2485
0048 | Municipal Manager | Exec & Coun | 7277528 | 3180593 | 43.7043
0050 | Finance & Admin Finance | Finance | 18832010 | 7700473 | 40.8903
0052 | Street Lighting | Tech.Serv | 496908 | 164826 | 33.1703
0054 | Property Services | Tech.Serv | 9548214 | 3463642 | 36.2753
0058 | Workshop | Tech.Serv | 984836 | 421317 | 42.7804
0062 | Water Storage | Tech Serv | 0 | 0 | 0
0071 | Electricity | Tech Serv | 18293314 | 6554001 | 35.8273
0073 | Water | Tech Serv | 0 | 0 | 0
| Total |  | 164150748 | 62354019 | 37.9858
Capital Expenditure
| Budget | Expenditure To Date | %
| 165975472 | 50121768 | 30.1983
Operating Expenditure
| Budget | Expenditure To Date | %
| 164150748 | 62354019 | 37.9858
Total Average for Capital & Operating Expenditure
| Budget | Expenditure To Date | %
| 330126220 | 112475787 | 34.0705
TOTAL EXPENDITURE ASSESSMENT
Capital expenditure as at 31 December 2014 was at 30.2%. Operating expenditure was at 37.99%. The budget is way below the norm of 50% and this is caused by the challenge of not adhering to the procurement plan.

## Icome
IN HOUSE REPORT DECEMBER 2014
INCOME FOR THE YEAR TO DATE
Actual as Per Revenue Source
Source | Budget | Billed to date | Received to date | %
Assessment Rates | 6355008 | 4427662 | 3550239 | 69.672
Equitable Shares | 171845000 |  | 69563000 | 40.4801
Electricity | 15906477 | 6508136 | 3999875 | 40.915
Refuse Removal | 4092948 | 1783778 | 616025 | 43.5817
Traffic Fines | 336654 |  | 47330 | 14.0589
Agencies fees | 1738494 |  | 893595 | 51.4005
Traffic Licences and Permits | 5607360 |  | 1329592 | 23.7116
Interest from Outstanding Debtors | 5607360 |  | 3639836 | 64.9118
Interest from External Investment | 3610800 |  | 1432724 | 39.6789
Debt Impairment | -6010920 |  | -158 | 0.0026285
Interest Received: FNB | 2377818 |  | 1377217 | 57.9194
Other Income | 20329220 |  | 578412 | 2.8452
TOTAL | 231796219 | 12719576 | 87027687 | 37.5449
Total Income Excluding Conditional Grants |  | 12719576 | 87027687
INCOME FROM CONDITIONAL GRANTS
MUNICIPAL INFRASTRUCTURE GRANT (MIG)
In terms of the Municipal Financial year 2014/2015
| Budget | To date Received | %
MIG - Roll Over | 14316360 | 14316360 | 100
MIG | 53440000 | 34020000 | 63.6602
MUNICIPAL SYSTEM IMPROVEMENT GRANT (MSIG)
Accumulative figures from 2005/2006 to 2014/2015
Budget | 7836000
To date Transferred | 7836000
To date Expenditure | 6443168
Percentage | 82.23%
Unspent Amount | 1392832
FINANCIAL MANAGEMENT GRANT (FMG)
Accumulative figures from 2005/2006 to 2014/2015
Budget | 9161000
To date Transferred | 9161000
Spent since Inception (see last month) | 7766557
Spent this Month | 26615
Total FMG Fund Spent | 7793172
Percentage | 85.07%
Unspent Amount | 1367828
INCOME PERFORMANCE ASSESSMENT
The municipality is not doing well in terms of revenue collection. The municipality depends more on equitable share and grants. Should National Treasury stop funding, the municipality will not be able to sustain the services.

## Salaries
Salaries
Expenditure on staff benefits (section 66 of MFMA)
Details | Budget | Actual | Monthly | %
Salaries | 43139596 | 18843682 | 3145392 | 43.6807
Housing Subsidy | 359454 | 115047 | 19389 | 32.006
Uniform | 143617 | 54900 | 9150 | 38.2267
Standby Allowance | 56599 | 31479 | 9860 | 55.6176
Group Insurance | 206588 | 97576 | 16149 | 47.2322
Industrial Council | 42343 | 7824 | 1295 | 18.4777
Medical Aid Fund | 2322064 | 1071683 | 178127 | 46.1522
Overtime | 3087934 | 1433023 | 209428 | 46.4072
Pension Fund | 8028871 | 3582490 | 593075 | 44.6201
Leave Redemption | 1484684 | 179825 | 49114 | 12.112
Leave Bonus | 3702129 | 1425442 | 205763 | 38.5033
Vehicle Allowance | 1772396 | 764471 | 128325 | 43.1321
Total Salaries &
Allowance | 64346275 | 27607442 | 4565067 | 42.9045
Expenditure on Councillors Allowances
Details | Budget | Actual | Monthly | %
Total allowance
Councillors | 16855524 | 7555351 | 1290624 | 44.8242

## Overtime
Overtime Per Department
Vote No | Description | Department | Budget | Actual | %
0014 | Library | Comm.Serv | 21358 | 8374 | 39.2078
0
0018 | Disaster Management | Comm.Serv | 4000 | 0 | 0
0
0
0020 | Taxi Rank | Comm.Serv | 24562 | 22824 | 92.924
0
0
0022 | Planning & Development | EDP | 26698 | 26055 | 97.5916
0
0
0028 | Vehicle Licensing & Testing | Comm.Serv | 300000 | 127829 | 42.6097
0
0
0029 | Roads | Tech.Serv | 380000 | 137770 | 36.2553
0
0
0032 | Community Hall | Comm.Serv | 0 | 0 | 0
0033 | Housing | EDP | 0 | 0 | 0
0034 | Sports & Recreation | Comm.Serv | 600000 | 308497 | 51.4162
0036 | Public Toilets | Comm.Serv | 91839 | 43901 | 47.8021
0038 | Cemetries & Crematoriums | Comm.Serv | 29901 | 11914 | 39.8448
0039 | Finance & Admin IT | Corps | 2500 | 0 | 0
0040 | Executive & Council | Corps | 138827 | 82057 | 59.1074
0042 | Refuse Removal | Comm.Serv | 357747 | 108736 | 30.3947
0046 | Finance & Admin HR | Corps | 96111 | 23292 | 24.2345
0048 | Municipal Manager | Exec & Coun | 58735 | 24707 | 42.0652
0050 | Finance & Admin Finance | Finance | 471595 | 192612 | 40.8427
0054 | Property Services | Tech.Serv | 209308 | 129914 | 62.0683
0058 | Workshop | Tech.Serv | 74753 | 29606 | 39.6051
0071 | Electricity | Tech Serv | 200000 | 154935 | 77.4675
| Total |  | 3087934 | 1433023 | 46.4072
Solution

## Cash Flow
CASH RECEIPTS BY SOURCE
| July | August | September | October | November | December | January | February | March | April | May | June
Property rates | 828721 | 533135 | 309903 | 391997 | 292979 | 1193504 | [6 empty] | 3550239
Service charges - electricity revenue | 668194 | 788063 | 663816 | 702321 | 310967 | 866505 | [6 empty] | 3999866
Service charges - refuse revenue | 98571 | 144774 | 113290 | 95717 | 53656 | 110017 | [6 empty] | 616025
Rental of facilities and equipment | 5947 | 8418 | 8075 | 1735 | 5961 | 3518 | [6 empty] | 33654
Interest earned - external investments | 0 | 0 | 0 | 117707 | 0 | 1315017 | [6 empty] | 1432724
Interest earned - outstanding debtors | 296885 | 574207 | 562415 | 588192 | 591780 | 483503 | [6 empty] | 3096982
Fines | 8940 | 9445 | 5350 | 1925 | 5880 | 10040 | [6 empty] | 41580
Licences and permits | 505993 | 154963 | 244130 | 220593 | 94254 | 280736 | [6 empty] | 1500669
Agency services | 150069 | 161920 | 98693 | 131260 | 214200 | 137454 | [6 empty] | 893596
Transfer receipts - operational | 67937000 | 1626000 | 0 | 0 | 0 | [7 empty] | 69563000
Other revenue | 267754 | 306075 | 512870 | 232257 | 212028 | 364131 | [6 empty] | 1895115
| 70768074 | 4307000 | 2518542 | 2483704 | 1781705 | 4764425 | [6 empty] | 86623450
OTHER CASH FLOWS/ RECEIPTS BY SOURCE
Transfer receipts - Capital | 14540000 | 0 | 0 |  |  | 19480000
| 85308074 | 4307000 | 2518542 | 2483704 | 1781705 | 24244425 | 0 | 0 | 0 | 0 | 0 | 0 | 86623450
CASH PAYMENT BY TYPE
Employee related costs | 4780470 | 4519630 | 4715208 | 4492869 | 4521294 | 4565069 | [6 empty] | 27594540
Remuneration of councillors | 1253546 | 1253546 | 1253547 | 1253547 | 1253547 | 1285683 | [6 empty] | 7553416
Interest paid | 0 | 0 | 319425 | 0 | 0 | 311067 | [6 empty] | 630492
Bulk purchases - Electricity | 1217484 | 1254282 | 842730 | 734156 | 575351 | 495612 | [6 empty] | 5119615
Contracted services | 444630 | 521058 | 604050 | 1128992 | 616374 | 560665 | [6 empty] | 3875769
General expenses | 2091372 | 3369030 | 3414237 | 2835106 | 2186799 | 5027994 | [6 empty] | 18924538
| 9787502 | 10917546 | 11149197 | 10444670 | 9153365 | 12246090 | 0 | 0 | 0 | 0 | 0 | 0 | 63698370
OTHER CASH FLOW/PAYMENTS BY TYPE
Capital Assets | 2929620 | 7448424 | 8156765 | 676457 | 11248319 | 19662184 | [6 empty] | 50121769
Payment of Borrowing | 0 | 0 | 221229 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 221229
TOTAL CASH PAYMENT BY TYPE | 12717122 | 18365970 | 19527191 | 11121127 | 20401684 | 31908274 | 0 | 0 | 0 | 0 | 0 | 0 | 114041368
NET INCREASE/DECREASE IN CASH HELD | 72590952 | -14058970 | -17008649 | -8637423 | -18619979 | -7663849 | 0 | 0 | 0 | 0 | 0 | 0 | 6602082

## Bank Balances
Bank Balances as at 31 December 2014
Main Account | 18645604.15
Traffic | 31189798.15
Housing | 0
TOTAL | 49835402.3
The balance in the main account is too low caused by delay National Treasury to deposit funds into the municipal account. There was a challenge with the Treasury systems and the money will be deposited into the municipal account in January 2015. The Traffic account has enough funds of which R20 000 000.00 may be invested in the short term investment (Call Account) which can yield more intersts/ income to the municipality.
Investments
The Municipality has got investments in the following institutions:
Momentum
Old Mutual
NedGroup
ABSA
Investec
The value of the investments as at 31 December 2014 amounts to R69 427 714
Momentum investment is held as security for the DBSA loan, to be changed from a call account
to a long term investment to yield better interest rate.
ABSA investment to be withdrawn as it is a fixed deposit and not held as security for DBSA.
Monthly Withdrawals from the Bank
Month | Amount
July | 18379584
August | 21630960
September | 23147026
October | 14609080
November | 22497709
December | 37152539.36
January
February
March
April
May
June
Total Withdrawals To Date |  | 137416898.36
Long Term Loans
An agreement for the repayment of the loan has been drawn. The municipality has to make
four(4) equal instalments of R 540 654 quarterly for 15 years. The balance as at 31 December 2014
is R7 372 868.00 for the DBSA loan.

## Debtors
Debtors Age Analysis
Total billing for the year 2014/2015 |  |  |  | 12719576
Total Payments Received for the year 2014/2015 |  |  |  | 8166139
Total Outstanding Debts for the year 2014/2015 |  |  |  | 4553437
Total Oustanding Debts owed by the Departments |  |  |  | 2059979
Detail | 0-30 | 31-60 | 61-90 | 91-120 | 121-150 | Total
| Days | Days | Days | Days | Days
Debtors Age
Analysis by
Income Source
Water
Tariffs | 0 | 0 | 0 | 0 | 0 | 0
Electricity | [5 empty] | 0
Tariffs | 960671 | 870489 | 933826 | 912354 | 14148539 | 17825879
Rates (Property
Rates ) | 894096 | 734280 | 688036 | 658193 | 22715345 | 25689950
Sewerage/
Sanitation Tariffs
Refuse Removal
Tariffs | 483435 | 488535 | 464094 | 456602 | 23522215 | 25414881
Housing (Rental
Income)
RSC Levies
Other | 55099 | 68056 | 68590 | 68846 | 15287001 | 15547592
Total By Income
Source | 2393301 | 2161360 | 2154546 | 2095995 | 75673100 | 84478302
Debtors Age
Analysis by
Customer Group
Government | 76843 | 78150 | 72829 | 61114 | 1771043 | 2059979
Business | 506943 | 301817 | 251423 | 249583 | 4706561 | 6016327
Households | 1809515 | 1781393 | 1830294 | 1785298 | 69195496 | 76401996
Other | 0 | 0 | 0 | 0 | 0 | 0
Total By
Customer Group | 2393301 | 2161360 | 2154546 | 2095995 | 75673100 | 84478302

## FBE
Free Basic Electricity
Approved Beneficiaries for Free Basic Electricity by Eskom
Wards | Configure No | Submitted Applications
1 | 0 | 0
2 | 0 | 0
3 | 6 | 10
4 | 9 | 15
5 | 19 | 38
6 | 11 | 11
7 | 0 | 0
8 | 0 | 0
9 | 3 | 6
10 | 9 | 14
11 | 18 | 69
12 | 0 | 1
13 | 10 | 25
14 | 0 | 0
15 | 0 | 284
16 |  | 0
17 | 0 | 0
18 | 0 | 0
19 | 0 | 4
20 | 0 | 0
21 | 30 | 79
22 | 45 | 67
23 | 0 | 0
24 | 0 | 0
25 | 0 | 0
26 | 91 | 135
27 | 15 | 27
28 | 0 | 0
29 | 0 | Own licenced
| Budget | Expenditure To Date | %
FBE | 796500 | 154257 | 19.3669
On average, the monthly account for FBE amounts to R70 230.17 vat exclusive.
Beneficiaries do not collect the coupons and this leads to Eskom cancelling the applications.
We do not have reliable statistics for all the individuals that receive Free Basic Water.
We rely on the indigent register (27 324 Boreholes and Water tanker truck deliveries)
We have 29 indigents in Ga-kgapane ,Senwamokgope and Modjadjiskloof receiving the following
Free Basic Sewerage (total monthly charge)
Free Basic Water (6kl)
Free Basic refuse (total monthly charge)
After the implementation of the Municipal Property Act, their properties had rebates that allowed
them not to be charged the rates at all (zero rate due to rebates)
We have 68 indigent in Mokgoba receiving Electricity only

## Grants
MUNICIPAL INFRASTRUCTURE GRANT (MIG)
In terms of the Municipal Financial year 2014/2015
| Budget | To date Received | To date Expenditure | %
MIG | 53440000 | 34020000 | 10986419 | 16.2146
Expenditure on MIG budget is at 16.21% and this will improve in the 3rd Quarter when project are awarded.
MUNICIPAL SYSTEMS IMPROVEMENT GRANT (MSIG)
In terms of the Municipal Financial year 2014/2015
| Budget | To date Received |  | %
MSIG | 1909067 | 1909067 | 516235 | 27.0412
Expenditure on MSIG is at 27.04% and will improve as and when the municipality pays PWC for unbundling of assets
FINANCE MANAGEMENT GRANT (FMG)
In terms of the Municipal Financial year 2014/2015
| Budget | To date Received |  | %
FMG | 1841512 | 1841512 | 179032 | 9.722
This budget is seriously underspending and expenditure will improve when interns are appointed in February 2015.
EXTENDED PUBLIC WORKS PROGRAMME (EPWP)
In terms of the Municipal Financial year 2014/2015
| Budget | To date Received |  | %
EPWP | 1731000 | 692000 | 1464118 | 84.5822
The EPWP Budget is overshooting due to non alignment of budget and number of employees hired.

## Audit report
Progress on resolving problems identified in the 2013/2014 Annual Report The Municipality went through a rigorous auditing process during the 2013/2014 Audit conducted by the Auditor-General (AG) of South Africa and as a result, the Municipality will use the results and comments when reviewing the 2014/2015 Service Delivery Budget Implementation Plan. In view of the fact that the 2013/2014 Annual Report has not yet been tabled during the Council meeting, and that it is still to be published, it would be premature to consider it for purposes of the assessment (Section 72(1)(a)(iii) of the MFMA).

## Conclusion
CONCLUSION
The mid-year budget and performance assessment indicates that:
An adjustments budget for 2014/2015 will be required.
The Service Delivery Budget Implementation Plan assessment displays a need for budget adjustment.
The performance Agreements of section 57 employees be amended accordingly.