## COVER
GREATER LETABA MUNICIPALITY
SERVICE DELIVERY AND BUDGET
IMPLEMENTATION PLAN
4th QUARTER PERFORMANCE REPORT
2014/2015

## INDEX
Table of Contents
Introduction | 3
Legislation | 3
Methodology and Contents | 4
Strategic Vision, Mission and Strategy Map | 5
Votes and Operational Objectives | 6
Summary of 4th Quarter Performance | 7 to 8
Municipal Transformation and Organisational Development KPI's | 9 to 10
Municipal Transformation and Organisational Development Projects | 12 to 14
Basic Service Delivery KPI's | 13
Basic Service Delivery Projects | 14 to 22
Local Economic Development Projects | 23 to 25
Municipal Financial Viability KPI's | 26
Municipal Financial Viability Projects | 27
Good Governance and Public Participation KPI's | 28 to 29
Good Governance and Public Participation Projects | 30 to 31
Approval | 32

## INTR AND LEGISLATION
Introduction | The development, implementation and monitoring of a Service Delivery and Budget Implementation Plan (SDBIP) is required by the Municipal Finance Management Act (MFMA). In terms of Circular 13 of National Treasury, “the SDBIP gives effect to the Integrated Development Plan (IDP) and budget of the municipality and will be possible if the IDP and budget are fully aligned with each other, as required by the MFMA.” As the budget gives effect to the strategic priorities of the municipality it is important to supplement the budget and the IDP with a management and implementation plan. The SDBIP serves as the commitment by the Municipality, which includes the administration, council and community, whereby the intended objectives and projected achievements are expressed in order to ensure that desired outcomes over the long term are achieved and these are implemented by the administration over the next twelve months.
The SDBIP provides the basis for measuring performance in service delivery against quarterly targets and implementing the budget based on monthly projections. Circular 13 further suggests that “the SDBIP provides the vital link between the mayor, council (executive) and the administration, and facilitates the process for holding management accountable for its performance. The SDBIP is a management, implementation and monitoring tool that will assist the mayor, councillors, municipal manager, senior managers and community.” The purpose of the SDBIP is to monitor the execution of the budget, performance of senior management and achievement of the strategic objectives set by council. It enables the municipal manager to monitor the performance of senior managers, the mayor to monitor the performance of the municipal manager, and for the community to monitor the performance of the municipality.
In the interests of good governance and better accountability, the SDBIP should therefore determine and be aligned with the performance agreements of the municipal manager and senior managers. The development, implementation and monitoring of a Service Delivery and Budget Implementation Plan (SDBIP) is required by the Municipal Finance Management Act (MFMA). In terms of Circular 13 of National Treasury, “the SDBIP gives effect to the Integrated Development Plan (IDP) and budget of the municipality and will be possible if the IDP and budget are fully aligned with each other, as required by the MFMA.”
Legislation | According to the Municipal Finance Act (MFMA) the definition of a SDBIP is: 'service delivery and budget implementation plan' means a detailed plan approved by the mayor of a municipality in terms of section 53 (1) (c) (ii) for implementing the municipality's delivery of municipal services and its annual budget, and which must indicate- (a) projections for each month; (i) revenue to be collected by source; (ii) operational and capital expenditure by vote; (b) service delivery targets and performance indicators for each quarter. Section 53 of the MFMA stipulates that the Mayor should approve the SDBIP within 28 days after the approval of the budget. The Mayor must also ensure that the revenue and expenditure projections for each month and the service delivery targets and performance indicators as set out in the SDBIP are made public within 14 days after their approval.
The following National Treasury prescriptions as minimum requirements that must form part of the SDBIP are applicable to the Municipality : (1) Monthly projections of revenue to be collected by source. (2) Monthly projections of expenditure (operating and capital) and revenue for each vote. (3) Quarterly projections of service delivery targets and performance indicators for each vote. (4) Ward information for expenditure and service delivery. (5) Detailed capital works plan broken down per ward for three years. * Section 1 of the MFMA defines a “vote” as: a) One of the main segments into which a budget of a municipality is divided for the appropriation of money for the different departments or functional areas of the municipality; and b) which specifies the total amount that is appropriated for the purposes of the department or functional area concerned.

## METHODOLOGY AND CONTENT
Methodology and Content | National Treasury directives are clear on the contents and methodology to derive at the SDBIP. As a first step, the IDP objectives need to be quantified and related into key performance indicators. The budget is aligned to the objectives, projects and activities to enable the SDBIP to serve as monitoring tool for service delivery. The SDBIP is described as a layered plan. The top layer deals with consolidated service delivery targets and time frames. Top Management is held accountable for the implementation of the consolidated projects and Key Performance Indicators. From the consolidated information, top management is expected to develop the next level of detail by breaking up outputs into smaller outputs and then linking and assigning responsibility to middle-level and junior managers.
The SDBIP of the Greater Letaba Municipality consists of strategic objectives derived from the IDP that are aligned with the strategic intent of the organisation. Strategic indicators with targets are set to measure the objectives. The Municipal Manager takes responsibility for the strategic indicators and objectives which will form part of his/her Performance Agreement and Plan. Projects and activities are aligned to the indicators with quarterly targets, time-frame and budget assigned to each. The Strategic Indicators give rise to the institutional indicators for which the Directors will take responsibility. These indicators will form part of the Performance Agreements and Plans of Senior Managers (Directors). Indicators are assigned quarterly targets and responsibilities to monitor performance. Derived from this, the next layer is developed, whereby the details with responsibilities for the next level of management is outlined and forms part of the Lower SDBIP. This lower SDBIP is a management tool for the S57 Managers and need not be made public and is a separate document for each internal department. The SDBIP serves as a management, implementation and monitoring tool that will assist the Mayor, Councilors, Municipal Manager and Directors in delivering services to the community

## STRATEGY
Vision and Mission | The strategic vision of the organisation sets the long term goal the Municipality wants to achieve. The vision of Greater Letaba Municipality is: "To be an outstanding agro-processing and eco-cultural tourism hub". The strategic mission speaks about what the purpose of Greater Letaba Municipality is: The mission of Greater Letaba Municipality is to ensure an effective, efficient and economically viable municipality through: Provision of accountable, transparent, consultative and co-operative governance. Improving the quality of life through economic development and poverty alleviation. Provision of sustainable services. Ensuring a safe and healthy environment.
Strategy map | The Strategy Map depicts the strategic objectives on how Greater Letaba Municipality will be able to become an outstanding agro-processing and eco-cultural tourism hub while providing sustainable and affordable services to all. These objectives were positioned in terms of the Balanced Scorecard Perspectives being: Learning and Growth; Institutional Processes; Financial results and Community Satisfaction. All operational outputs (projects, initiatives and process) as contained within the SDBIP are aligned to the attainment of one or more of these objectives.

## OPERATIONAL STRATEGIES
Votes and Operational objectives | Votes | Objectives and Targets
| Municipal Manager Office (Vote 040) | To lead, direct and manage a motivated and inspired administration and account to the Greater Letaba Municipal Council as Accounting Officer for long term municipal sustainability to achieve a good creditor rating within the requirements of the relevant legislation and whereas the following sections within the department, i.e. HIV/Aids, Youth, Disabled and Gender Desk, Communication and Internal Auditing is managed for integration, economic growth, marginalised poverty alleviation, efficient, economic and effective communication and service delivery.
| Finance (Vote 050) | To secure a sound and sustainable management of the financial affairs of Greater Letaba Municipality by managing the budget and treasury office and advising and if necessary assisting the Accounting Officer and the Directors in their duties and delegation contained in the MFMA. Ensuring that the Greater Letaba Municipality is 100% financially viable when it comes to cost coverage and to manage the grant revenue of the municipality so that no grant funding is foregone
| Community Services (Vote 028) | To co-ordinate Environmental Health Services, Sports Arts and Culture, Education, Libraries, Safety and Security, Environmental and Waste management, Health and Social development programmes as well as Disaster management to decrease community affected by disasters
| Infrastructure Development and Economic Planning (Votes 029 and 022) | To ensure that the service delivery requirements for roads are met and maintenance of water, sewerage and electricity are conducted for access to basic services as well as no less than an average of 100% MIG expenditure
To direct the Greater Letaba Municipality’s resources for advanced economic development and investment growth through appropriate town and infrastructure planning in order that an environment is created whereby all residents will have a sustainable income.
| Corporate Services (Vote 046 ) | To ensure efficient and effective operation of council services, human resources and management, legal services and the provision of high quality customer orientated administrative systems. Ensuring 100% compliance to the Skills Development Plan.

## SUMMARY OF THE REPORT
1. BACKGROUND OF THE REPORT
Section 52 of the Local Government: Municipal Finance Management Act, 56 of 2003, requires that the Mayor of the municipality must, within 30 days of the end of each quarter, submit a report to council on the implementation of the budget and the financial state of affairs of the municipality, the report should be submitted to Provincial Treasury and Department of Cooperative Governance and Traditional Affairs.
2. MUNICIPAL 4th QUARTER PERFORMANCE AS PER THE ASSESSMENT
The municipality used the reviewed SDBIP as approved by Council .The SDBIP is used as a performance monitoring tool for the implementation of the IDP and Budget. The performance target reflected in the SDBIP is as per the IDP objectives. The Administration component is responsible for implementation of the SDBIP and the Political component is responsible for providing oversight. This is done through regular reporting to Council.
The Municipality is complying in terms of performance reporting which is done quarterly. The Mid- year report covering the first half of the financial year (1st July to 31st December 2014) was tabled in council during January 2015 and 3rd Quarter report was tabled in council during April 2015. The municipality performed as follows as per the five Key Performance Areas:
2.1 KPA 1: Municipal Transformation and Institutional Development
The key performance area had 14 key performance indicators during the 2014/15 4th quarter. The municipality managed to record good performance on 9 key performance indicators and targets which constituted 64% of the total KPA scores. The under-performance in this key performance area was on not having the Audit Committee, since the contract has expired. Individual performance assessments were not conducted and risk reolutions were not implemented fully under review.
The overall performance for Municipal Transformation projects is 55%. The non-performance was due to non adherence to the procurement plan.
2.2 KPA2: Basic Service Delivery
The key performance area had 2 key performance indicators during the 2014/15 4th quarter. The municipality managed to record good performance on 1 key performance indicator and targets which constituted 50 %. The non performance recorded was due to number of indigent applicants not as per the target. Although all the applications received were processed, there is a less number of beneficiaries applying for Indigent relief since most of the beneficiaries have conneccted services illegally.
The overall performance targets for Basic Service Delivery projects was 65 and the municipality managed to record good performance on 29 targets that Constituted 45%. The 55% of poor performance was due to the delay Appointment of of service providers and projects not complete.
2.3 KPA 3: Local Economic Development
The overall performance targets for Local Economic Development projects was 22 in the 2014/15 4th quarter. The municipality managed to record good performance on 9 targets which constituted 41% of the total score. The 59% under performance recorded was due to the LED projects (Designs) not completed as planned.
2.4 Municipal Financial Viability
The key performance area had 12 key performance indicators during the 2014/15 4th quarter. The municipality managed to record good performance on 9 key performance indicators which constitutes 75% and recorded poor performance on 3 indicators which constituted 25% of the total KPA score. The under-performance was as a result of capital budget not fully spend and the expenditure on FMG, MSIG and MIG not fully spent.
The overall performance targets for Municipal Financial Viability projects was 5 and the municipality managed to record good performance on 4 targets that Constituted 80%. The 20% recorded was due to the Revenue Enhancement Strategy not reviewed as planned.
2.5 KPA 5: Good Governance and Public Participation
This key performance area had 11 key performance indicators during the 2014/15 4th Quarter and the municipality achieved good performance on all 9 key performance indicators which represents 82% of the total KPA score.
The overall performance targets for Good Governance and Public participation projects were 18 and the municipality managed to record good performance on 10 targets that constituted 56%. The 44% poor performance recorded was due to the Designs not completed.
2.6 Overall Performance of the municipality
For the 2014/15 4th Quarter performance report, the municipality had 5 key Performance Areas with combined key performance indicators totalling 39. The municipality recorded good performance on 28 key performance indicators constituting to 72 % and non-performance of 11 key performance indicators which constituted 28%.
The overall performance target for the municipal projects is 48%.
The overall municipal performance for the planned projects and indicators during the 4th Quarter is 60%

## MTOD KPI's
KPA 1 MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT
KEY PERFORMANCE INDICATORS
OUTCOME NINE (OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING, PLANNING AND SUPPORT, OUTPUT 4: ACTIONS SUPPORTIVE OF THE HUMAN SETTLEMENT OUTCOMES)
Vote Nr | Strategic Objective | Programmes | Measurable Objectives | Performance measures/ Indicator | Baseline / Status | Annual Target (30/06/2015) | Original Budget 2014/2015 | Adjusted Budget 2014/2015 | 4th Quarter target | 4th Quarter Actual Performance | Remarks | Challenges | Interventions | Responsible Person
22 | Integrated Sustainable Development | IDP | To ensure that draft IDP, Budget and SDBIP are adopted by 31 March 2015. | Deadlinefor adopting Draft IDP, budget and PMS adopted by Council on 31 May 2015 | IDP, budget and PMS adopted by 31 May 2014 | IDP, budget and PMS adopted by 31 May 2015 | Operational | Operational | IDP, budget and PMS adopted by 31 May 2015 | IDP, budget and PMS adopted by 31 May 2015 | Target Achieved | None | None | INDEP/CFO/MM
22 | Integrated Sustainable Development | IDP | To develop and implement IDP process plan by 30 June 2014. | Deadline for the adoption of the IDP/Budget/PMS process plan by Council on 30 June 2015 | IDP/Budget/PMS process plan by Council on 30 June 2015 | Adopted by 30 June 2014 | Operational | Operational | IDP, budget and PMS adopted by 31 May 2015 | IDP, budget and PMS adopted by 31 May 2015 | Target Achieved | None | None | INDEP/CFO/MM
22 | Integrated Sustainable Development | IDP | To review, drive and monitor implementation of the IDP by 31 May 2015 | % achievement of milestones on IDP/Budget/PMS process plan. | 100% | 100% | Operational | Operational | 100% achievement on IDP/ Budget/PMS process plan. | 100% achievement on IDP/ Budget/PMS process plan. | Target Achieved | None | None | INDEP/MM
33 | Improved Governance and Organisational Excellence | SDBIP | To ensure that SDBIP is finalised by 30 June 2015. | Deadline for the approval of the final SDBIP by the Mayor within 28 days after adoption of the final Budget and IDP. | SDBIP approved by Mayor 28 days after adoption of Budget and IDP | SDBIP approved by Mayor 28 days after adoption of budget/IDP/PMS | Operational | Operational | SDBIP approved by Mayor 28 days after adoption of budget/IDP/PMS | SDBIP approved by Mayor 28 days after adoption of budget/IDP/PMS | Target Achieved | None | None | PMS/MM
54 | Improved Governance and Organisational Excellence | OPMS | To ensure annual implementation of the performance management system in the organisation | # of Quarterly performance reports submitted to Council. | 4 Quartrely performance report submitted to council | 4 Quartrely performance report submitted to council | Operational | Operational | 1 Quartrely performance report submitted to council | 1 Quartrely performance report submitted to council | Target Achieved | None | None | PMS/MM
54 | Improved Governance and Organisational Excellence | EPMS | To ensure quartely assessments for S57 Managers is conducted within 30 days after the end of the quarter. | # of quarterly performance assessments conducted within 30 days after the end of the quarter. | 4 Quartrely performance Assessments conducted within 30 days after the end of the quarter | 4 Quartrely performance Assessments conducted within 30 days after the end of the quarter | Operational | Operational | 1 Quartrely performance Assessments conducted within 30 days after the end of the quarter | 0 | Target Not achieved | The Municcipality does not have the Audit Committee | To conduct Individual performance assessments in the 1st Quarter of 2015/16 Financial year | PMS/MM
54 | Improved Governance and Organisational Excellence | Internal Audit | To ensure functionality of Audit committee within the financial year. | # of Audit Committee meetings held per quarter. | 4 Audit Committee meetings held per quarter | 4 Audit Committee meetings held per quarter | Operational | Operational | 1 Audit Committee meetiing held per quarter | 0 | Target Not achieved | The Municcipality does not have the Audit Committee | To conduct Individual performance assessments in the 1st Quarter of 2015/16 Financial year | Internal Audit /MM
54 | Improved Governance and Organisational Excellence | Risk | To ensure functionality of Risk committee within the financial year. | # of Risk Committee meetings held per quarter. | 4 Risk Committee meeting held per quarter | 4 Risk Committee meeting held per quarter | Operational | Operational | 1 Risk Committee held per quarter | 1 Risk Committee held per quarter | Target Achieved | None | None | Risk/MM
54 | Improved Governance and Organisational Excellence | CORPS | To ensure functionality of Council committee within the financial year. | # of Council meetings held per quarter. | 4 Council meetings held per quarter | 4 Council meetings held per quarter | Operational | Operational | 1 Council meeting held | 3 Council meetings held | 1 Ordinary meeting and 2 special meetings | None | None | CORPS/MM
| Improved Governance and Organisational Excellence | CORPS | To ensure functionality of EXCO committee within the financial year. | # of EXCO meetings held per quarter. | 4 EXCO meetings held per quarter | 4 EXCO meetings held per quarter | Operational | Operational | 1 EXCO meeting held | 3 EXCO meetings held | 1 Ordinary meeting and 2 special meetings | None | None | CORPS/MM
54 | Improved Governance and Organisational Excellence | Internal Audit | To conduct quarterly assessment on municipal performance information. | # of performance audit reports issued per quarter. | 4 performance audit reports issued | 4 performance audit reports issued | Operational | Operational | 1 Audit report issued | 1 Audit report issued | 1 Audit report issued | None | None | Internal Audit
54 | Improved Governance and Organisational Excellence | Internal Audit | To develop annual year internal audit plan and implement by 30 June 2015. | Approved internal audit plan and % of the IA plan implementation. | 50% IA plan implementation | 100% IA plan implementation | Operational | Operational | 100% IA plan implementation | 60% | Target Not achieved | Not all issues were resolved | To resolve all outstanding issues within the 1st quarter of 2015/16 | MM
54 | Improved Governance and Organisational Excellence | Operation clean audit | To attain Clean Audit by ensuring compliance to all governance; financial management and reporting requirements by 30 June 2015 | % of AG issues resolved (# of Auditor General issues resolved / # of issues raised) | 78% | 100% AG issues resolved | Operational | Operational | 100% AG issues resolved | 90% | 6 issues are still outstanding | Outstanding issues are awaiting Intenal Audit review | to resolve the outstanding issues by 1st Quarter 2015/16 | All Directors/MM
54 | Improved Governance and Organisational Excellence | Risk management | To ensure efffective implementation of risk mitigations actions 30 June 2015. | % of Risk issues resolved (# Risk issues implemented / resolved / # of risks identified) | 100% | 100% Risk issues resolved | Operational | Operational | 100% Risk issues resolved | 83% | Target Not achieved | Delay in submission of Information | To submit information in time to Risk Management Unit | Risk/MM

## MTOD PROJECTS
KPA 1 MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT PROJECTS
OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING, PLANNING AND SUPPORT, OUTPUT 4: ACTIONS SUPPORTIVE OF THE HUMAN SETTLEMENT OUTCOMES
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project / Initiative | Original Budget 2014/2015 | Adjusted Budget 2014/2015 | Start Date | Completion Date | Annual traget | Milestones Qtr Ending June 2015 | 4th Quarter Actual Performance | Remarks | Challenges | Corrective measures | Project Owner
46 | Improved Governance and Organisational Excellence | Risk Management | To conduct 4 quarterly OHS risk assessment workshop | Risk assessment: OHS | 9000 | 9000 | 01/07/2014 | 30/06/2015 | 4 OHS Risk Assessment workshop | 1 OHS Risk Assessment workshop | Not done | Target Not Achieved | the Assessment was not done | to conduct the assessments in the 2015/16 FY | MM
46 | Improved Governance and Organisational Excellence | OHS | To organise 4 Health and Safety awareness events 30 June 2015 | Health and safety awareness event | 40000 | 40000 | 01/07/2014 | 30/06/2015 | 4 Health and Safety awareness events | 1 Health and Safety awareness events | 1 Health and Safety awareness events | Target Achieved | None | None | CORPS & CFO
46 | Improved Governance and Organisational Excellence | OHS | To purchase OHS signs and posters by 30 June 2015 | OHS signs and posters | 12000 | 5000 | 01/07/2014 | 30/06/2015 | Develop specification, submit to SCM, purchase and paste OHS sign posters | Develop specification, submit to SCM, purchase and paste OHS sign posters | Not done | Target Not Achieved | Slow procurement of SCM process | will be implemented in 2015/16 FY | CORPS & CFO
46 | Improved Governance and Organisational Excellence | Furniture & Equipment | To purchase office signs and posters by 30 June 2014 | Four (4)signs and posters | 2000 | 2000 | 01/07/2014 | 30/06/2015 | Develop specification, submit to SCM, purchase office signs and posters | Develop specification, submit to SCM, purchase office signs and posters | Specifications submitted nd 4 Signs and posters purchased | Target Achieved | None | None | CORPS & CFO
46 | Improved Governance and Organisational Excellence | OHS | To purchase First aid kit by 30 June 2014 | First Aid content | 5000 | 5000 | 01/07/2014 | 30/06/2015 | Develop specification, submit to SCM, purchase first aid kit | Develop specification, submit to SCM, purchase first aid kit | Develop specification, submit to SCM, purchase first aid kit | Target achieved. | First aid content purchased. | None | CORPS & CFO
54 | Improved Governance and Organisational Excellence | Property Services | Purchasing of a scanner for Corporare Services by 30 June 2015 | Purchasing of a scanner for Corporare Services by 30 June 2015 | 5000 | 5000 | 01/07/2014 | 30/06/2015 | Develop specification, submit to SCM, purchase scanner | Develop specification, submit to SCM, purchase scanner | Not done | Target Not Achieved | Slow procurement of SCM process | to implement the procurement plan | CORPS
46 | Improved Governance and Organisational Excellence | Property Services | To develop and implement skills Developemnt programmes by 30 June 2015 | implementation of Skills development levy | 300000 | 300000 | 01/07/2014 | 30/06/2015 | 100 % employees trained | 100% employees trained | 100% employees trained | Target achieved. 100% employees trained | None | None | CORPS
46 | Improved Governance and Organisational Excellence | Human Resources | To award long service award to eligible employees timeously according to policy | monthly Long service awarded to qualifying employees | 169920 | 169920 | 01/07/2014 | 30/06/2015 | 100% of the long service awarded to qualifying employees | 100% of the long service awarded to qualifying employees | 100% of the long service awarded to qualifying employees | Target achieved. | 100% of the long service awarded to qualifying employees | None | CORPS
46 | Improved Governance and Organisational Excellence | IT | To purchase 4 Printers: Senwamokgope, Mokwakwaila, Kgapane and main office. | 4 Printers: Senwamokgope, Mokwakwaila, Kgapane and main office by 30 June 2015 | 100000 | 100000 | 01/07/2014 | 30/06/2015 | 4 printers purchase (Senwamokgope, Mokwakwaila, Ga-kgapane & main office) | Purchase printers | 4 printers not purchased | Target Not Achieved | Tender has been awarded and awaiting delivery | Speed up the process with SCM | CORPS & CFO
46 | Improved Governance and Organisational Excellence | IT | To develop and implement disaster recovery plan by 31 March 2015 | Disaster Recovery Plan and UPS | 300000 | 300000 | 01/10/2014 | 31/03/2015 | Implementation of the DRP and UPS | Implementation of the DRP and UPS at 100% | DRP is implemented. Tender awarded for UPS | Target Not Achieved | Slow procurement of SCM process | Speed up the process with SCM | CORPS & CFO
54 | Improved Governance and Organisational Excellence | Property Services | Construction of parking area for 36 vehicles at main office by 30 June 2015 | Parking at Municipal Offices | 1000000 | 1000000 | 01/07/2014 | 31/03/2015 | Project of municipal office parking at complete | Project of municipal office parking at complete at 100% | Project of municipal office parking at complete at 100% | Target Achieved | None | None | INDEP / B & T

## BSD Indicators
KPA 2 BASIC SERVICE DELIVERY - PERFORMANCE INDICATORS OUTPUT 2: IMPROVING ACCESS TO BASIC SERVICES, OUTPUT 3: IMPLEMENTATION OF THE COMMUNITY WORKS PROGRAMME
Vote Nr | Strategic Objective | Programmes | Measurable Objectives | Performance measures | Baseline / Status | Annual Target (30/06/15) | Original Budget 2014/2015 | Adjusted Budget 2014/2015 | 4th Quarter target | 4th Quarter Actual Performance | Remarks | Challenges | Interventions | Responsible Person
50 | Access to Sustainable Basic Services | Indigent Management | To ensure that all indigent applicants are registered in the indigent register within 14 days of receipt. | # of applications processed and registered in the indigent register | 1725 | 900 | Operational | Operational | 900 | 837 of HH | Target not achieved | Slow response of applicants in the Indigent (most benefificaries have connected illegal) | Intensification of Indigent campaigns | CFO
INDE | Integrated and Sustainable Human Settlement | Spatial Planning | To ensure that land use applications are processed within 90 days of receipt. | % of land use applications processed (# of applications received / # of land use applications processed) within 90 days of receipt | 100% | 100% | Operational | Operational | 100% | 100% | Target Achieved | All received applications have been processed, except those which have arrears on municipal account | Encourage communities to pay municipal accounts | INDEP

## BSD PROJECTS
KPA 2 BASIC SERVICE DELIVERY AND INFRASTRUCTURE KEY PERFORMANCE INDICATORSPROJECTS OUTCOME NINE (OUTPUT 2: IMPROVING ACCESS TO BASIC SERVICES, OUTPUT 3: IMPLEMENTATION OF THE COMMUNITY WORK PROGRAMME)
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project Description | Original Budget 2014/2015 | Adjusted Budget 2014/2016 | Start Date | Completion Date | Milestones Qtr Ending June 2015 | 4th Quarter Actual Performance | Remarks | Interventions | Project Owner
62 | Access to Sustainable Basic Services | Stormwater | Construction of 16m pedestrian bridge at Ga-Kgapane (William Kgatla) by 31 March 2015 | Pedestrian William Kgatle Bridge | 150000 | 150000 | 01/07/2014 | 31/03/2015 | 16m Pedestrian William Kgatle Bridge Project completed | Target Achieved, Project complete | 16m Pedestrian William Kgatle Bridge Project completed | None | INDEP / B & T
62 | Access to Sustainable Basic Services | Stormwater | Design and construction of 4.88m wide low level bridges by 31 March 2015 | Low Level Bridges | 1500000 | 1500000 | 01/07/2014 | 31/03/2015 | 4.88m wide Low Level Bridges at Thabanatshwane and Shaamfana villages completed. | Target not achieved. Low level bridges not completed | Culverts have been delivered. Construction in progress | None | INDEP / B & T
62 | Access to Sustainable Basic Services | Stormwater | Design and construction of 110m stormwater management channels in Modjadjiskloof by 31 March 2015 | Modjadjiskloof- Channels | 2000000 | 2400000 | 01/07/2014 | 31/03/2015 | 110m long Modjadjiskloof Stormwater Management project at construction stage. Excavations complete | Target not achieved. Excavayion not complete | Service provider not appointed | Adherence to procurement plan. | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Purchasing of a 2-tonner truck with quarter canopy for roads maintenance team by 12 December 2014 | 2-Tonner Truck with Quarter Canopy | 300000 | 320000 | 01/07/2014 | 12/12/2014 | 2-tonner truck with quarter canopy purchased | Target Achieved | 2-tonner truck with quarter canopy purchased | None | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Supply and installation of 480 cubic mtrs gabions for Sekgopo by 31 March 2015 | Gabions - Sekgopo | 1200000 |  | 01/07/2014 | 31/03/2015 | 480 cubic mtrs Sekgopo gabions complete | Target not achieved. Gabions not complete | Service Provider busy with preliminary requirements | Fast track construction processes | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Upgrading of gravel to concrete paving blocks for 1.8 km at Mothobeki village by 31 March 2015 | Mothobeki Paving | 6500000 | 7000000 | 01/07/2014 | 31/03/2015 | Layer works for 1.8 km of the paving at Mothobeki complete | Target not achieved. Layer works not started | Service Provider busy with preliminary requirements | Fast track construction processes | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Upgrading of gravel to concrete paving blocks for 1.8 km at Mamaila Phaphadi village by 31 March 2015 | Mamaila Phaphadi Paving | 6500000 | 7000000 | 01/07/2014 | 31/03/2015 | Layer works for 1.8 km of the paving at Mamaila Phaphadi complete | Target not achieved. Layer works not started | Service Provider busy with earthworks | Fast track construction processes | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Upgrading of gravel to concrete paving blocks for 1.8 km at Phooko village by 31 March 2015 | Phooko Head Kraal Paving | 3200000 | 3520000 | 01/07/2014 | 31/03/2015 | Layer works for 1.8 km of the paving at Phooko Head Kraal complete | Target not achieved. Layer works not started | Service Provider busy with earthworks | Fast track construction processes | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Upgrading of gravel to concrete paving blocks for 1.8 km at Raphahlelo village by 31 March 2015 | Raphahlelo Head Kraal Paving | 6550000 | 7000000 | 01/07/2014 | 31/03/2015 | Layer works for 1.8 km of the paving at Raphahlelo complete | Target not achieved. Layer works not started | Service Provider busy with earthworks | Fast track construction processes | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Rehabilitation of 3 km of streets in Modjadjiskloof by 31 March 2015 | Rehabilitation of Modjadjiskloof Streets | 5500000 | 5500000 | 01/07/2014 | 31/03/2015 | 3km of streets rehabilitated (Modjadjiskloof) | Target not achieved. 3km of streets not rehabilitated | Contractor is busy with finishing and still to pave Mooimeisie Street | Project to be completed by mid-August 2015 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Rehabilitation of 3 km of streets in Ga-Kgapane by 31 March 2015 | Rehabilitation of Ga-Kgapane Streets | 5500000 | 5500000 | 01/07/2014 | 31/03/2015 | 3km of streets rehabilitated (Ga-Kgapane) | Target not achieved. 3km of streets not rehabilitated | Layer work has been completed | Project to be completed by end of August 2015 | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Construction of 3.5 km of sidewalks in Modjadjiskloof by 31 March 2015 | Modjadjiskloof Sidewalks | 3000000 | 3000000 | 01/07/2014 | 31/03/2015 | 3.5 km of sidewalks in Modjadjiskloof completed | Target not achieved. Project is not complete | Excavations underway | Fast track construction processes | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Construction of access road to Mokwakwaila Taxi Rank for 600m by 31 March 2015 | Access Road to Mokwakwaila Taxi Rank- Roll over | 3100000 | 3100000 | 01/07/2014 | 31/03/2015 | Appointment of consultants, designs completed and site handed over to contractor at Mokwakwaila Taxi Rank | Target achieved | To commence with construction in July 2015 | None | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Planning and designing of street paving at Itieleng (Sekgosese) by 30 June 2015 | Itieleng- Sekgosese Street Paving | 450000 | 450000 | 01/07/2014 | 30/06/2015 | Designs for Itieleng-Sekgosese Street Paving project completed | Target not achieved. Designs not complete | Service provider not appointed | Adherence to procurement plan. | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Planning and designing of street paving at Lemondokop by 30 June 2015 | Lemondokop Street Paving | 450000 | 450000 | 01/07/2014 | 30/06/2015 | Designs for Lemondkop Street Paving project completed | Target not achieved. Designs not complete | Service provider not appointed | Adherence to procurement plan. | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Planning and designing of street paving at Refilwe village by 30 June 2015 | Refilwe Street Paving | 450000 | 450000 | 01/07/2014 | 30/06/2015 | Designs for Refilwe Street Paving project completed | Target Achieved | Designs completed | None | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Planning and designing of street paving at Mamakata-Raselaka by 30 June 2015 | Mmamakata Raselaka Street Paving | 450000 | 450000 | 01/07/2014 | 30/06/2015 | Designs for Mmamakata Raselaka Street Paving project completed | Target Achieved | Designs completed | None | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Planning and designing of Ivory-route street paving at Modjadji by 30 June 2015 | Modjadji Ivory -route Street Paving | 7000000 | 700000 | 01/07/2014 | 30/06/2015 | Designs for Modjadji Ivory Route Street Paving project completed | Target Achieved | Designs completed | None | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Planning and designing of taxi rank at Khosotupa by 30 June 2015 | Khosutupa Taxi Rank | 220000 | 220000 | 01/07/2014 | 30/06/2015 | Appoint service provider and complete design and planning of Khosutupa Taxi rank project | Target not achieved. Designs not complete | Service provider not appointed | Adherence to procurement plan. | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Planning and designing of taxi rank at Wholesale by 30 June 2015 | Wholesale Taxi Rank | 220000 | 220000 | 01/07/2014 | 30/06/2015 | Appoint service provider and complete design and planning of Wholesale Taxi rank project | Target not achieved. Designs not complete | Service provider not appointed | Adherence to procurement plan. | INDEP / B & T
29 | Access to Sustainable Basic Services | Roads | Planning and designing of taxi rank at Mamphakati by 30 June 2015 | Mamphakati Taxi Rank | 220000 | 220000 | 01/07/2014 | 30/06/2015 | Appoint service provider and complete design and planning of Mamphakati Taxi rank project | Target Achieved | Designs completed | None | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of gravel to concrete paving blocks for 3 km at Ga-Kgapane by 31 March 2015 | Ga-Kgapane Street Upgrading | 8965000 | 10615770 | 01/07/2014 | 31/03/2015 | Layer works for 3 km and 1.5km of paving blocks at Kgapane complete | Target not achieved. Paving blocks not laid for 1.5km | Contractor is busy with earthworks | Fast track construction processes | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of gravel to concrete paving blocks for 1.8 km at Senwamokgope by 31 March 2015 | Senwamokgope Street Upgrading | 5400000 | 5841000 | 01/07/2014 | 30/03/2015 | Layer works for 1.8 km and 0.9 km of paving blocks at Senwamokgope complete | Target not achieved. Paving blocks not laid for 0.9km | Contractor is busy with earthworks and layer works | Fast track construction processes | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of gravel to concrete paving blocks at Thakgalane for 2km by 30 September 2014 | Upgrading of streets - Thakgalane | 1500000 | 4400000 | 01/07/2014 | 30/09/2014 | Construction of 2km Thakgalane Street paving completed | Target Achieved | 2km of streets paved | None | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of gravel to concrete paving blocks for 1.2 km at Kuranta by 31 March 2015 | Upgrading of streets -Kuranta | 3600000 | 3915789 | 01/07/2014 | 31/03/2015 | 1.2 km of street paving at Kuranta complete | Target not achieved. Project is not complete | Layer work has been completed | Fast track construction processes | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of gravel to concrete paving blocks for 2 km at Mokgoba by 31 March 2015 | Upgrading of streets -Mokgoba | 5950000 | 6314423 | 01/07/2014 | 31/03/2015 | 2 km of street paving at Mokgoba streets completed | Target not achieved. Project is not complete | Contractor is busy with earthworks | Fast track construction processes | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of gravel to concrete paving blocks for 2 km at Modjadji Valley by 31 March 2015 | Upgrading of streets -Modjadji Valley | 5950000 | 6198111 | 01/07/2014 | 31/03/2015 | 2 km of street paving at Modjadji Valley complete | Target not achieved. Project is not complete | Contractor is busy with earthworks | Fast track construction processes | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of gravel to concrete paving blocks for 1.8 km at Ratjeke by 31 March 2015 | Ratjeke Street Paving | 5600000 | 6000000 | 01/07/2014 | 31/03/2015 | 1.8 km of street paving at Ratjeke streets completed | Target not achieved. Project is not complete | Contractor is busy with layer works | Fast track construction processes | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of street paving at Seatlaleng village by 30 June 2015 | Seatlaleng Street Paving | 400000 | 400000 | 01/07/2014 | 30/06/2015 | Designs for Seatlaleng Street Paving project completed | Target Achieved | Designs completed | None | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of street paving at Mohlakong village by 30 June 2015 | Mohlakong Street paving | 400000 | 400000 | 01/07/2014 | 30/06/2015 | Designs for Mohlakong Street Paving project completed | Target Achieved | Designs completed | None | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of street paving at Sephukubje village by 30 June 2015 | Sephukhubje Street Paving | 400000 | 400000 | 01/07/2014 | 30/06/2015 | Designs for Sephukhubje Street Paving project completed | Target Achieved | Designs completed | None | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of street paving at Matshelapata village by 30 June 2015 | Matshelapata Street Paving | 400000 | 400000 | 01/07/2014 | 30/06/2015 | Designs for Matshelapata Street Paving project completed | Target not achieved. | Designs not complete | Adherence to procurement plan. | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of street paving at Shawela village by 30 June 2015 | Shawela Street Paving | 400000 | 400000 | 01/07/2014 | 30/06/2015 | Designs for Shawela Street Paving project completed | Target Achieved | Designs completed | None | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of street paving at Sekgop (Maboying) village by 30 June 2015 | Sekgopo Maboying Street Paving | 400000 | 400000 | 01/07/2014 | 30/06/2015 | Designs for Sekgopo Maboying Street Paving project completed | Target Achieved | Designs completed | None | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of street paving at Tlhotlhokwe village by 30 June 2015 | Tlhotlhokwe Street Paving | 400000 | 400000 | 01/07/2014 | 30/06/2015 | Designs for Tlhotlhokwe Street Paving project completed | Target Achieved | Designs completed | None | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of street paving at Shamfana village by 30 June 2015 | Shamfana Street Paving | 400000 | 400000 | 01/07/2014 | 30/06/2015 | Designs for Shamfana Street Paving project completed | Target Achieved | Designs completed | None | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of street paving at Kherobene village by 30 June 2015 | Kherobeng Street Paving | 400000 | 400000 | 01/07/2014 | 30/06/2015 | Designs for Kherobeng Street Paving project completed | Target Achieved | Designs completed | None | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Construction of library at Senwamokgope township by 31 March 2015 | Senwamokgope library | 2100000 | 2321000 | 01/07/2014 | 31/03/2015 | Brick wall and roof for 400m2 Senwamokgope library completed | Target achieved | Brickwall is at roof level | None | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Construction of library at Sekgopo by 31 March 2015 | Sekgopo library | 2100000 | 2337271 | 01/07/2014 | 31/03/2015 | Brick wall and roof for 400m2 Sekgopo library completed | Target achieved | Brickwall is at roof level | None | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Planning and designing of library at Mokwakwaila by 30 June 2015 | Mokwakwaila library | 375000 | 375000 | 01/07/2014 | 30/06/2015 | Brick wall and roof for Mokwakwaila library completed | Target not achieved. | Designs not complete | Finalisation of location of the project | INDEP / B & T
29 | Access to Sustainable Basic Services | Contribution from MIG | Upgrading of Ga-Kgapane stadium by 31 March 2015 | Kgapane stadium | 3600000 | 3600000 | 01/07/2014 | 31/03/2015 | Complete upgrading of Ga-Kgapane Stadium | Target not achieved. Project is not complete | Construction is underway | Fast track construction processes | INDEP / B & T
54 | Access to Sustainable Basic Services | Property Services | Refurbish municipal workshop and stores by 12 December 2014 | Refurbishment of Municipal Workshop and stores | 500000 | 1200000 | 01/07/2014 | 12/12/2014 | Municipal Workshop refurbished (Project completed) | Target not achieved. Project is not complete | Contractor is busy with preliminary requirements | Fast track construction processes | INDEP / B & T
54 | Access to Sustainable Basic Services | Property Services | Renovate 6 Rottaba Cottages in Modjadjiskloof by 31 March 2015 | Rehabilitation of Rotaba Cottages | 500000 | 500000 | 01/10/2014 | 31/03/2015 | 6 Rottaba Cottages renovated , Project copleted (Modjadjiskloof) | Target not achieved. Project is not complete | Service provider not appointed | Adherence to procurement plan. | INDEP / B & T
22 | Improved Local Economy | Community & Social | coordinate and conduct 4 environmental related events and campaigns | Environmental Programmes | 100000 | 100000 | 01/07/2014 | 30/06/2015 | Coordinate and conduct enviromental related events and campaigns (1 per quarter) | 2 environmental related events held | Tree Planting campaigns in Mahekwe on 26 May 2015 and in Bellvue on 25 June 2015. | None | COMM
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Planning and designing of community hall for Ward 2 by 31 March 2015 | Ward 2 Community Hall | 280000 | 280000 | 01/07/2014 | 30/06/2015 | Complete design and planning of Ward 2 Community Hall for 400m2 | Target achieved | Designs completed | None | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Planning and designing of community hall for Ward 5 by 31 March 2015 | Ward 5 Community Hall | 280000 | 280000 | 01/07/2014 | 30/06/2015 | Complete design and planning of Ward 5 Community Hall for 400m2 | Target achieved | Designs completed | None | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Planning and designing of community hall for Matswi village by 31 March 2015 | Matswi Community Hall | 280000 | 280000 | 01/07/2014 | 30/06/2015 | Complete design and planning of Matswi Community Hall for 400m2 | Target achieved | Designs completed | None | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Planning and designing of community hall for Mohlele village by 31 March 2015 | Mohlele Community Hall | 280000 | 280000 | 01/07/2014 | 30/06/2015 | Complete design and planning of Mohlele Community Hall for 400m2 | Target achieved | Designs completed | None | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Planning and designing of community hall for Mamaila (Kolobetona) village by 31 March 2015 | Mamaila - Kolobetona Community Hall | 280000 | 280000 | 01/07/2014 | 30/06/2015 | Complete design and planning of Mamaila - Kolobetona Community Hall for 400m2 | Target achieved | Designs completed | None | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Planning and designing of community hall for Shamfana village by 31 March 2015 | Shamfana Community Hall | 280000 | 280000 | 01/07/2014 | 30/06/2015 | Complete design and planning of Shamfana Community Hall for 400m2 | Target not achieved. Design is not complete | Service provider not appointed | Adherence to procurement plan. | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Planning and designing of new community hall for Rotterdam by 31 March 2015 | Rotterdam (new Community hall) | 2400000 | 2400000 | 01/07/2014 | 30/06/2015 | Brick wall and roof for 400m2 Rotterdam Community Hall completed | Target not achieved. Project is not complete | Service provider appointed | Fast track construction processes | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Construction of Ga-Kgapane Parks (Below Civic Centre and Mesopotamia) by 31 March 2015 | Ga-Kgapane Parks | 500000 | 3389080 | 01/07/2014 | 30/06/2015 | Planning and design of Ga-Kgapane Park completed | Target not achieved. Project is not complete | Service provider not appointed | Adherence to procurement plan. | COMM
34 | Access to Sustainable Basic Services | Sports & Recreation | Enhancement & Beautification of Modjadjiskloof Town Entrances by 30 June 2015 | Enhancement & Beautification of Town Entrances | 700000 | 1000000 | 01/07/2014 | 30/06/2015 | Complete planning and design for enhancement and beautification of Modjadjiskloof town entrances. | Target not Achieved, Project not completed | Late completion of Designs by the service provider. |  | COMM
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of sport complex for Mamanyoha village by 30 June 2015 | Mamanyoha Sports Complex | 500000 | 500000 | 01/07/2014 | 30/06/2015 | Complete planning and design of Mamanyoha Sports Complex | Target not achieved. Design is not complete | Draft designs have been presented by service provider | Finalising design processes | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of sport complex for Rotterdam village by 30 June 2015 | Rotterdam Sports Complex | 500000 | 500000 | 01/07/2014 | 30/06/2015 | Complete planning and design of Rotterdam Sports Complex | Target not achieved. Design is not complete | Busy with designs | Finalising design processes | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of youth centre for Sekgopo village by 30 June 2015 | Sekgopo Youth Centre | 320000 | 320000 | 01/07/2014 | 30/06/2015 | Complete planning and design of Sekgopo Youth Centre | Target not achieved. Design is not complete | Draft designs have been presented by service provider | Finalising design processes | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of youth centre for Ga-Kgapane township by 30 June 2015 | Kgapane Youth Centre | 320000 | 320000 | 01/07/2014 | 30/06/2015 | Complete planning and design of Kgapane Youth Centre | Target achieved | Designs completed | None | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of youth centre for Mokwakwaila village by 30 June 2015 | Mokwakwaila Youth Centre | 320000 | 320000 | 01/07/2014 | 30/06/2015 | Complete planning and design of Mokwakwaila Youth Centre | Target not achieved. Design is not complete | Draft designs have been presented by service provider | Finalising design processes | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of youth centre for Roerfontein village by 30 June 2015 | Roerfontein Youth Centre | 320000 | 320000 | 01/07/2014 | 30/06/2015 | Complete planning and design of Roerfontein Youth Centre | Target not achieved. Design is not complete | Draft designs have been presented by service provider | Finalising design processes | INDEP / B & T
31 | Access to Sustainable Basic Services | Sports & Recreation | Construction of outdoor gym at Maphalle by 31 March 2015 | Maphalle Outdoor gym | 550000 | 550000 | 01/07/2014 | 30/06/2015 | Complete construction of outdoor gym at Maphalle village | Target Achieved | Outdoor Gym completed | None | INDEP / B & T
31 | Access to Sustainable Basic Services | Sports & Recreation | Construction of outdoor gym at Sekgopo village by 31 March 2015 | Sekgopo Outdoor gym | 550000 | 550000 | 01/07/2014 | 30/06/2015 | Complete construction of outdoor gym at Sekgopo village | Target Achieved | Outdoor Gym completed | None | INDEP / B & T
31 | Access to Sustainable Basic Services | Sports & Recreation | Construction of outdoor gym at Abel village by 31 March 2015 | Abel Outdoor gym | 550000 | 550000 | 01/07/2014 | 30/06/2015 | Complete construction of outdoor gym at Abel village | Target Achieved | Outdoor Gym completed | None | INDEP / B & T
31 | Access to Sustainable Basic Services | Sports & Recreation | Construction of outdoor gym at Ga-Kuranta village by 31 March 2015 | Kuranta Outdoor gym | 550000 | 550000 | 01/07/2014 | 30/06/2015 | Complete construction of outdoor gym at Kuranta village | Target Achieved | Outdoor Gym completed | None | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Design and construction of sports ground at Ga-Kgapane by 30 June 2015 | Kgapane Sports ground | 5000000 | 500000 | 01/07/2014 | 30/06/2015 | Complete planning and design of Ga-Kgapane Sports Ground | Target not achieved. Design is not complete | Service provider not appointed | Adherence to procurement plan. | INDEP / B & T
32 | Access to Sustainable Basic Services | Libraries and Archives | Procuring and installation of modular issue counters at Soetfontein library 31 March 2015 | Modular issue Counters (2) | 80000 | 80000 | 01/07/2014 | 31/03/2015 | Modular issue Counters (2) delivered | Target Not Achieved | Service Provider appointed and Modular issues Counter not yet delivered | Liase with the Service Provider to deliver the Counters | COMM

## LED PROJECTS
KPA 3 LOCAL ECONOMIC DEVELOPMENT PROJECTS OUTPUT 3: IMPLEMENTATION OF THE COMMUNITY WORK PROGRAMME
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project Description | Original Budget 2014/2015 | Adjusted Budget 2014/2015 | Start Date | Completion Date | Milestones Qtr Ending June 15 | 4th Quarter Actual Performance | Remarks | Interventions | Project Owner
22 | Access to Sustainable Basic Services | Planning and Development | Design and construction of fence and admin block at the new show ground by 30 June 2015 | GLM Show Ground | 6000000 | 6000000 | 01/07/2014 | 30/06/2015 | Design, fencing, market stalls and exhibition hall for GLM Show Ground completed | Target not achieved. Project is not complete | Construction is underway | Fast track construction processes | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Design and construction of market stalls at Sekgopo by 30 June 2015 | Sekgopo Market stalls | 800000 | 800000 | 01/07/2014 | 30/06/2015 | Design and construction of Sekgopo Market stalls to completion | Target not achieved. Project is not complete | Designs are underway | Finalization of designs | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Design and construction of market stalls at Sekgosese by 30 June 2015 | Sekgosese Market stalls | 800000 | 800000 | 01/07/2014 | 30/06/2015 | Design and construction of Sekgosese Market stalls to completion | Target not achieved. Project is not complete | Draft designs have been presented | Finalization of designs | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Design and construction of market stalls at Maphalle by 30 June 2015 | Maphalle Market stalls | 800000 | 800000 | 01/07/2014 | 30/06/2015 | Design and construction of Maphalle Market stalls to completion | Target not achieved. Project is not complete | Draft designs have been presented | Finalization of designs | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Design and construction of market stalls at Ga-Kgapane by 30 June 2015 | Kgapane Market stalls | 800000 | 800000 | 01/07/2014 | 30/06/2015 | Design and construction of Kgapane Market stalls to completion | Target not achieved. Project is not complete | Designs are underway | Finalization of designs | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Design and construction of market stalls at Mamaila (Phaphadi) by 30 June 2015 | Mamaila-Phaphadi Market stalls | 800000 | 800000 | 01/07/2014 | 30/06/2015 | Design and construction of Mamaila-Phaphadi Market stalls to completion | Target not achieved. Project is not complete | Draft designs have been presented | Finalization of designs | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Design and construction of market stalls at Madumeleng by 30 June 2015 | Madumeleng Market stalls | 800000 | 800000 | 01/07/2014 | 30/06/2015 | Design and construction of to completion | Target not achieved. Project is not complete | Designs are underway | Finalization of designs | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Halls & Facalities | Design and construction of market stalls at Khosuthopa by 30 June 2015 | Khosuthopa Market stalls | 800000 | 800000 | 01/07/2014 | 30/06/2015 | Design and construction of Khosuthopa Market stalls to completion | Target not achieved. Project is not complete | Draft designs have been presented | Finalization of designs | INDEP / B & T
22 | Improved Local Economy | Local Economic Development | Identify and implement SMME support initiatives by 30 June 2015 | Support of SMMEs' | 200000 | 127949 | 01/07/2014 | 30/06/2015 | Implementation of SMME support initiatives | Target Achieved, Completed | Support initiatives implemented | None | INDEP
22 | Improved Local Economy | Local Economic Development | Participate in the annual Tourism Indaba by 30 June 2015 | Tourism Indaba | 150000 | 150000 | 01/07/2014 | 30/06/2015 | Attend and participate in the Tourism Indaba | Target not achieved. Municipality did not participate in the Indaba | Event was not attended | To participate in the next financial year | INDEP
22 | Improved Local Economy | Local Economic Development | Promote tourism activities within GLM by 30 June 2015 | Tourism Development | 400000 | 200000 | 01/07/2014 | 30/06/2015 | Implementation of tourism development initiatives | Target Achieved, Completed | Tourism initiatives implemented | None | INDEP
22 | Improved Local Economy | Planning & Development | Implement agricultural development initiatives by 30 June 2015 | Agricultural development | 60000 | 36000 | 01/07/2014 | 30/06/2015 | Implement agricultural development initiatives | Target Achieved, Completed | Agricultural development initiatives implemented | None | INDEP / B & T
22 | Improved Local Economy | Planning & Development | Identify business support initiatives by 30 June 2015 | Business Support | 60000 | 30000 | 01/07/2014 | 30/06/2015 | Implementation of business support initiatives | Target Achieved, Completed | Support initiatives implemented | None | INDEP
22 | Improved Local Economy | Planning & Development | Develop entrance and fencing for Manokwe cave by 30 June 2015 | Development of Manokwe cave | 400000 | 400000 | 01/07/2014 | 30/06/2015 | Design and fencing of Manokwe cave completed | Target not achieved. Project is not complete | Service provider was not appointed | Adherence to procurement plan | INDEP / B & T
22 | Improved Local Economy | Planning & Development | Support emerging piggery farmers within GLM by 30 June 2015 | GLM Piggery Project | 400000 | 400000 | 01/07/2014 | 30/06/2015 | Support emerging piggery farmers | Target Achieved, Completed | Piggery projects implemented | None | INDEP
22 | Improved Local Economy | Planning & Development | Compile feasibility study for picnic sites in GLM by 30 June 2015 | Feasibility Study for Picnic Sites | 400000 | 400000 | 01/07/2014 | 12/12/2014 | Draft report for Feasibility Study for Picnic Sites completed and submitted to GLM | Target not achieved. Project is not complete | Service provider was not appointed | Adherence to procurement plan | INDEP / B & T
34 | Improved Local Economy | Sports and Recreation | To organise the Wolkberg sports day by 31 March 2015 | Wolkberg Sports day | 120000 | 120000 | 01/07/2014 | 31/03/2015 | Preparatory meetings and development of Implementation plan for the Wolkberg Sports day. | Target Achieved | Preparations meetings and development implementation for the Wolksberg sports was conducted | None | COMM
34 | Improved Local Economy | Sports and Recreation | To organise and host various sport codes by 30 June 2015 | Sports Activities | 200000 | 300000 | 01/07/2014 | 30/06/2015 | Sporting activities coordinated | Target Achieved | 2 Sporting activities was held in Tlhothlokwe and Sekgopo | None | COMM
34 | Improved Local Economy | Sports and Recreation | To organise Choral Music Competition by 31 March 2015 | Choral Music Competition | 100000 | 100000 | 01/07/2014 | 31/03/2015 | Final performance competition for the Choral Music Competition | Target Achieved | Performance competition for Choral Music Competition conducted | None | COMM
22 | Improved Local Economy | Planning and Development | To demarcate and peg sites at Nooitedaght by 31 March 2015 | Dermacation of sites (Nooitedaght Farm) | 600000 | 300000 | 01/07/2015 | 31/03/2015 | EIA, floodline determination, geotechnical investigation and public participation for Dermacation of sites (Nooitedaght Farm) completed | Target not achieved. Sites were not demarcated | Service provider was appointed and busy with preparations | Fast track demarcation processes | INDEP / B & T
22 | Improved Local Economy | Planning & Development | % in Implementantion of Land-use complaints | Land-use Management | 500000 | 250000 | 01/07/2014 | 30/06/2015 | Attend to land-use management queries as and when they arise. eg, pegging, demarcations and evictions | Target Achieved, Completed | Operational budget. E.g evictions | None | INDEP
22 | Improved Local Economy | Planning & Development | Planning for renewal of Modjadjiskloof CBD by 30 June 2015 | Modjadjiskloof Urban Renewal Plan | 400000 | 400000 | 01/07/2014 | 30/06/2015 | Draft layout plan for Modjadjiskloof Urban Renewal Plan completed and submitted to the municipality | Target not achieved. Renewal plan was not completed | Service provider was appointed and busy with preparations | Fast track compilation processes for the renewal plan | INDEP / B & T
Note on F15: Nomsa Makhubela:

## MFMV KPI
KPA 4 MUNICIPAL FINANCIAL VIABILITY KEY PERFORMANCE INDICATORS OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY
Vote Nr | Strategic Objective | Progranmes | Measurable Objectives | Performance measures | Baseline / Status | Annual Target (30/06/15) | Budget 2014/2015 | Budget 2014/2015 | 4th Quarter target | 4th Quarter Actaul Performance | Remarks | Challenges | Intervetions | Responsible Person
50 | Sustainable Financial Institution | Budget and Reporting | To ensure that financial information is supplied to relevant authorities by 30 June 2015. | Dealdline for submiting Financial information supplied to relevant authorities by 30 June 2015 | Information was submitted by 10 June 2015 | 2015-06-30 | Operational | Operational | within 10 working days | Sec 71 were submitted within 10 days | Target Achieved | None | None | CFO
50 | Sustainable Financial Institution | Budget and Reporting | To ensure that quartely financial statements are prepared within 14 days after the end of each quarter. | # of quarterly financial statements and submitted to the relevant authorities | 25% | 4 Financial statements submitted | Operational | Operational | 1 financial statement | 1 Financial statement prepared | Target Achieved | None | None | CFO
50 | Sustainable Financial Institution | Supply Chain Management | To ensure payment of service providers within 30 days of the submission of invoices. | Deadline for payments of invoices wiithin 30 daysof receipt | 100% | Payment of invoices within 30 days of receipt | Operational | Operational | Payment of invoices within 30 days of receipt | payment paid within 30 days of receipts | Target Achieved | None | Implementation of Procurement plan | CFO
50 | Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality within the financial year | % capital budget spent as approved by Council | 70% | 100% | Operational | Operational | 100% | 68.8% | Target not Achieved | Delay in appointment of service providers | Implementation of Procurement plan | CFO/INDEP/MM
50 | Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality within the financial year | % MIG expenditure | 70% | 100% | 46950000 | 46950000 | 100% | 79.5% | Target not Achieved | Most of the construction companies were appointed in April 2015 | Adherence to procurement plan | CFO/INDEP/MM
50 | Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality within the financial year | % FMG expenditure | 90% | 100% | 1550000 | 1550000 | 100% | 100% | Target Achieved | None | Maintain the status quo | CFO/INDEP/MM
50 | Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality within the financial year | % MSIG expenditure | 100% | 100% | 890000 | 890000 | 100% | 100% | Target Achieved | None | Maintain status Quo | CFO/INDEP/MM

## MFMV PROJECTS
KPA 4 MUNICIPAL FINANCIAL VIABILITY PROJECTS OUTCOME NINE (OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY)
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project / Initiative | Budget 2014/2015 | Budget 2014/2015 | Start Date | Completion Date | Milestones Qtr Ending Sept 2014 | 4th Quarter Actual Performance | Remarks | Challenges | Interventions | Project Owner
50 | Sustainable Financial Institution | Indigent Management | To register qualifying indigents 30 June 2015 | Updating of Indigent Register | Operational | Operational | 01/07/2014 | 30/06/2015 | qualifying indigent registered in the indigent register | qualifying indigent registered in the indigent register | Target Achieved | Slow response of applicants in the Indigent (most benefificaries have connected illegal) | Intensification of Indigent campaigns | CFO
50 | Sustainable Financial Institution | Revenue Management | Review, adopt and implement Revenue Enhancement Strategy 30 June 2015 | Revenue Enhancement Strategy | Operational | Operational | 01/07/2014 | 30/06/2015 | Revenue Emhancement strategy reviewed, adopted and implemented | Revenue Enhanement strategy not reviewed | Target Not Achieved | The municipality have a Draft Revenue Enhancement strategy | To conclude reviewing, adopt and implement the strategy | CFO
50 | Sustainable Financial Institution | Revenue Management | To update household billing system information 30 S2014 and implement | Data cleansing | Operational | Operational | 01/07/2014 | 30/06/2015 | Household billing sytem information updated | Household billing system information updated | Target Achieved | None | None | CFO
50 | Sustainable Financial Institution | Asset Management | To monitor the process of unbundling and make progress report by 31 July 2014 | Unbundling of Infrastructure Assets to update the asset register | Operational | Operational | 01/07/2014 | 30/06/2015 | Completion of compilation of GRAP compliant asset register | Completion of compilation of GRAP compliant asset register | Target Achieved | None | None | CFO
50 | Sustainable Financial Institution | Asset Management | To Monitor and management Valuation roll | Valuation Roll | Operational | Operational | 01/07/2014 | 30/06/2015 | Approval of valuation roll by Council | Approval of valuation roll by Council | Target Achieved | None | None | CFO

## GGPP KPI's
KPA 5 GOOD GOVERNANCE AND PUBLIC PARTICIPATION KEY PERFORMANCE INDICATORS OUTCOME 9 (OUTPUT 5: DEEPEN DEMOCRACY THROUGH A REFINED WARD COMMITTEE MODEL, OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY)
Vote Nr | Strategic Objective | Programmes | Measurable Objectives | Performance measures | Baseline / Status | Annual Target (30/06/15) | Original Budget 2014/2015 | 4th Quarter target | 4th Quarter Actual Performance | Remarks | Intervetions | Responsible Person
54 | Improved Governance and Organisational Excellence | Ward Committee | To ensure full participation of ward committees in annual ward programmes within the financial year. | # of ward committee programmes evaluated per month. | 29 | 348 | Operational | 29 | 29 | Target Achieved, | None | MM/CORPS
54 | Improved Governance and Organisational Excellence | Ward Committee | To ensure that community complaints are resolved within time frames. | % of complaints attended per month (# of community complaints received/ # of complaints attended to). | 100% | 100% | Operational | 100% | 100% | Target Achieved, | None | MM
54 | Improved Governance and Organisational Excellence | Local Imbizos | To ensure community participation in the affairs of the municipality within the financial year. | % in # of people who attend events | 100% | 100% | Operational | 100% | 100% | Target Achieved, | None | MM
| Improved Governance and Organisational Excellence | Local Imbizos | To implement Mayoral outreach programme by 30 June 2015 | # of local imbizos held by the Mayor by 30 June 2015. # of Mayoral Imbizo held per quarter | 4 | 4 | Operational | 1 | 1 | Target Achieved, | None | MM/ All Directors
54 | Improved Governance and Organisational Excellence | Traditional Leaders | To establish a good relationship with traditional leaders within the financial year. | # traditional leaders invited to take part in council meetings and activities. | 10 | 10 | Operational | 10 | 10 | Target Achieved, | None | MM
54 | Improved Governance and Organisational Excellence | IT | To publicise official documents in the website within legislated time frames (Budget, IDP, SDBIP) | # of official documents published. PA, SDBIP, APR, AR, Quarterly reports, IDP | 6 | 6 | Operational | 1 | 1 | Target Achieved, | None | IT
54 | Improved Governance and Organisational Excellence | Communication | To promote effective and efficient communication within the financial year. | # of articles issued to the media quartely. | 1 | 4 | Operational | 1 | 0 | Target Not Achieved | to Issue articles to the media | Ass-Director (Mayor's office)/MM
54 | Improved Governance and Organisational Excellence | Communication | To promote effective and efficient communication within the financial year. | # of newslatters issued quarterly. | 4 | 4 | Operational | 1 | 0 | Target Not Achieved | Municipal Newsletters should be developed | Ass-Director (Mayor's office)/MM
54 | Improved Governance and Organisational Excellence | Legal | To ensure proper contract management within the financial year. | % appointed service providers with Service Level Agreement (# of service providers appointed/# of service providers with service level agreement) | 100% | 100% | Operational | 100% | 100% | Target Achieved, | None | CORPS/MM
46 | Improved Human Resource | Skills Development | To ensure effective implementation of the WSP within the financial year. | % employees trained as per the WSP | 100% | 100% | Operational | 100% | 100% | Target Achieved, | None | CORPS
46 | Improved Human Resource | OHS | To ensure a health and safe working environment | # of wellness and OHS campaigns conducted per quarter | 4 | 4 | Operational | 1 | 1 | Target Achieved, | None | CORPS

## GGPP PROJECTS
KPA 5 GOOD GOVERNANCE AND PUBLIC PARTICIPATION PROJECTS OUTPUT 5: DEEPEN DEMOCRACY THROUGH A REFINED WARD COMMITTEE MODEL, OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY)
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project Description | Original Budget 2014/2015 | Adjusted Budget 2014/2015 | Start Date | Completion Date | Milestones Qtr Ending June 2015 | 4th Quarter Actaul performance |  | Intervetions | Project Owner
34 | Improved Governance and Organisational Excellence | Good Governance | Manage events effectively by 30 June 2015 | Communication and event management | 100000 | 100000 | 01/07/2014 | 30/06/2015 | Manage events and 100% of the budget spent | Target Achieved | Municipal events managed as planned | None | MM
40 | Improved Governance and Organisational Excellence | Good Governance | To award academic excellent performers by 30 June 2015 | Municipal Mayor’s excellent award | 200000 | 400000 | 01/01/2015 | 31/03/2015 | Excellence award ceremony | Target Achieved | The Mayors excellent award on the 17 April 2015 | None | MM
34 | Improved Governance and Organisational Excellence | Good Governance | Attending of conference and congresses | Conference and congresses | 100000 | 100000 | 01/07/2014 | 30/06/2015 | Adrehence to procedures and attend conference and congresses | Target Achieved | Conferences planned attended to | None | CORPS
46 | Improved Governance and Organisational Excellence | Skills Development/Training | To improve capacity of councillors by 30 June 2015 | Capacity building: councillors | 318600 | 550000 | 01/10/2014 | 30/06/2015 | 100% councillors trained | Target Achieved | 100% Cllrs trained as planned | None | CORPS
40 | Improved Governance and Organisational Excellence | Bursary Scheme | To fund good performing student from the needy families | Bursary scheme council | R2 000 000 | R2 000 001 | 01/07/2014 | 30/06/2015 | Payment of costs | Target AChieved | Payment of cost of students paid as per the awarded bursaries | None | MM
54 | Improved Governance and Organisational Excellence | Humanitarian | To enhance humanitarian by 30 June 2014 | Humanitarian Aid | 100000 | 110000 | 01/07/2014 | 30/06/2015 | 100% | 100% | The Municipality assisted with food parcels and learning aids for s Creche | None | MM
40 | Improved Governance and Organisational Excellence | Communication | To issue 4 newsletters by 30/06/2015 | News letter | 350000 | 200000 | 01/07/2014 | 30/06/2015 | 1 | Target Not Achoeved | Newsletter not issued | Implement in the 2015/16 FY | MM
40 | Improved Governance and Organisational Excellence | Special Programmes | To facilitate youth development activities by 30 June 2015 | Youth desk activities | 280000 | 180000 | 01/07/2014 | 30/06/2015 | facilitate youth development activities | Target Not Achieved | None | None | MM
40 | Improved Governance and Organisational Excellence | Special Programmes | To facilitate gender desk activities by 30 June 2016 | Gender desk activities | 200000 | 250000 | 01/07/2014 | 30/06/2015 | facilitate Gender Desl activities | Target Achieved | None | None | MM
54 | Improved Governance and Organisational Excellence | Special Programmes | To facilitate Disability desk activities by 30 June 2017 | Disability desk activities | 100000 | 177000 | 01/07/2014 | 30/06/2015 | facilitate Disability desk activities | Target Achieved | None | None | MM
40 | Improved Governance and Organisational Excellence | Special Programmes | To facilitate HIV/AIDS Council activities by 30 June 2015 | HIV & AIDS Council activities | 95000 | 60000 | 01/07/2014 | 30/06/2015 | Facilitae HIV/AIDS Council activities | Target Achieved | None | None | MM
14 | Access to Sustainable Basic Services | Libraries and Archives | Planning and designing of library for Shotong village by 30 June 2015 | Shotong Library | 300000 | 300000 | 01/07/2014 | 30/06/2015 | Complete planning and design of Shotong Library | Target Not Achieved | Delay in SCM process | None | INDEP / B & T
14 | Access to Sustainable Basic Services | Libraries and Archives | Planning and designing of library for Rotterdam village by 30 June 2015 | Rotterdam Library | 300000 | 300000 | 01/07/2014 | 30/06/2015 | Complete planning and design of Rotterdam Library | Target Not Achieved | Designs not conplete |  | INDEP / B & T
32 | Access to Sustainable Basic Services | Community Facilities | To do cemetry layout and fencing at Ga-Kgapane cemetry by 30 June 2015 | Kgapane Cemetry layout and fencing | 1500000 | 3000000 | 01/07/2014 | 30/06/2015 | Complete development of layout and construction of fence at Kgapane Cemetry | Target Not Achieved | Service Provider not appointed | To Apponit the Service provider | COMM
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of old age facility for Madumeleng village by 30 June 2015 | Madumeleng Old Age Facility | 220000 | 220000 | 01/07/2014 | 30/06/2015 | Complete planning and design of Madumeleng Old Age Facility | Target Not Achieved | Designs not conplete | None | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of old age facility for Ga-Kgapane township by 30 June 2015 | Kgapane Old Age Facility | 220000 | 220000 | 01/07/2014 | 30/06/2015 | Complete planning and design of Kgapane Old Age Facility | Target Not Achieved | Designs not conplete | None | INDEP / B & T
34 | Access to Sustainable Basic Services | Sports & Recreation | Planning and designing of old age facility for Roerfontein village by 30 June 2015 | Roerfontein Old Age Facility | 220000 | 220000 | 01/07/2014 | 30/06/2015 | Complete planning and design of Roerfontein Old Age Facility | Target Not Achieved | Designs not conplete | None | INDEP / B & T

## Approval
4th Quarter Performance Report
Approval by the Mayor | Sec 52 of the Local Government: Municipal Finance Management Act, 56 of 2003, requires the Mayor of the municipality must, within 30 days of the end of each quarter, submit a report to council on the implementation of the budget and the financial state of affairs of the municipality.
Signatures | 4th Quarter Performance Report Compiled By: ----------------------------------- ----------------------------- Mrs TG Mashaba DATE Municipal Manager Greater-Letaba Muncipality 4th Quarter Performance Report Approved By: -------------------------------------- ----------------------------- CLLR GH Modjadji DATE Mayor Greater-Letaba Muncipality