## COVER
GREATER LETABA MUNICIPALITY
SERVICE DELIVERY AND BUDGET
IMPLEMENTATION PLAN
2013/2014

## INDEX
Table of Contents
Introduction | 3
Legislation | 3
Methodology and Contents | 4
Strategic Vision, Mission and Strategy Map | 5
Votes and Operational Objectives | 6
Municipal Transformation and Organisational Development KPI's | 7 to 9
Municipal Transformation and Organisational Development Projects | 10 to 10
Basic Service Delivery Projects | 11 to 22
Local Economic Development Projects | 23 to 23
Municipal Financial Viability KPI's | 24 to 24
Municipal Financial Viability Projects | 25 to 25
Good Governance and Public Participation KPI's | 26 to 28
Good Governance and Public Participation Projects | 29 to 31
Capital Worksplan | 31 to 34
Approval | 35 to 35

## INTR AND LEGISLATION
Introduction | The development, implementation and monitoring of a Service Delivery and Budget Implementation Plan (SDBIP) is required by the Municipal Finance Management Act (MFMA). In terms of Circular 13 of National Treasury, “the SDBIP gives effect to the Integrated Development Plan (IDP) and budget of the municipality and will be possible if the IDP and budget are fully aligned with each other, as required by the MFMA.” As the budget gives effect to the strategic priorities of the municipality it is important to supplement the budget and the IDP with a management and implementation plan. The SDBIP serves as the commitment by the Municipality, which includes the administration, council and community, whereby the intended objectives and projected achievements are expressed in order to ensure that desired outcomes over the long term are achieved and these are implemented by the administration over the next twelve months.
The SDBIP provides the basis for measuring performance in service delivery against quarterly targets and implementing the budget based on monthly projections. Circular 13 further suggests that “the SDBIP provides the vital link between the mayor, council (executive) and the administration, and facilitates the process for holding management accountable for its performance. The SDBIP is a management, implementation and monitoring tool that will assist the mayor, councillors, municipal manager, senior managers and community.” The purpose of the SDBIP is to monitor the execution of the budget, performance of senior management and achievement of the strategic objectives set by council. It enables the municipal manager to monitor the performance of senior managers, the mayor to monitor the performance of the municipal manager, and for the community to monitor the performance of the municipality.
In the interests of good governance and better accountability, the SDBIP should therefore determine and be aligned with the performance agreements of the municipal manager and senior managers. The development, implementation and monitoring of a Service Delivery and Budget Implementation Plan (SDBIP) is required by the Municipal Finance Management Act (MFMA). In terms of Circular 13 of National Treasury, “the SDBIP gives effect to the Integrated Development Plan (IDP) and budget of the municipality and will be possible if the IDP and budget are fully aligned with each other, as required by the MFMA.”
Legislation | According to the Municipal Finance Act (MFMA) the definition of a SDBIP is: 'service delivery and budget implementation plan' means a detailed plan approved by the mayor of a municipality in terms of section 53 (1) (c) (ii) for implementing the municipality's delivery of municipal services and its annual budget, and which must indicate- (a) projections for each month of- (i) revenue to be collected, by source; and (ii) operational and capital expenditure, by vote; (b) service delivery targets and performance indicators for each quarter; Section 53 of the MFMA stipulates that the Mayor should approve the SDBIP within 28 days after the approval of the budget. The Mayor must also ensure that the revenue and expenditure projections for each month and the service delivery targets and performance indicators as set out in the SDBIP are made public within 14 days after their approval.
The following National Treasury prescriptions as minimum requirements that must form part of the SDBIP are applicable to the Municipality : (1) Monthly projections of revenue to be collected by source (2) Monthly projections of expenditure (operating and capital) and revenue for each vote * (3) Quarterly projections of service delivery targets and performance indicators for each vote (4) Ward information for expenditure and service delivery (5) Detailed capital works plan broken down per ward for three years * Section 1 of the MFMA defines a “vote” as: a) one of the main segments into which a budget of a municipality is divided for the appropriation of money for the different departments or functional areas of the municipality; and b) which specifies the total amount that is appropriated for the purposes of the department or functional area concerned

## METHODOLOGY AND CONTENT
Methodology and Content | National Treasury directives are clear on the contents and methodology to derive at the SDBIP. As a first step, the IDP objectives need to be quantified and related into key performance indicators. The budget is aligned to the objectives, projects and activities to enable the SDBIP to serve as monitoring tool for service delivery. The SDBIP is describes as a layered plan. The top layer deals with consolidated service delivery targets and time frames. Top Management is held accountable for the implementation of the consolidated projects and Key Performance Indicators. From the consolidated information, top management is expected to develop the next level of detail by breaking up outputs into smaller outputs and then linking and assigning responsibility to middle-level and junior managers.
The SDBIP of the Greater Letaba Municipality consists of Strategic Objectives derived from the IDP that are aligned with the strategic intent of the organisation. Strategic indicators with targets are set to measure the objectives. The Municipal Manager takes responsibility for the Strategic Indicators and Objectives which will form part of his Performance Agreement and Plan. Projects and activities are aligned to the indicators with quarterly targets, time-frame and budget assigned to each. The Strategic Indicators give rise to the Institutional Indicators for which the Directors will take responsibility. These indicators will form part of the Performance Agreements and Plans of Senior Managers (Directors). Indicators are assigned quarterly targets and responsibilities to monitor performance. Derived from this, the next layer is developed, whereby the details with responsibilities for the next level of management is outlined and forms part of the Lower SDBIP. This lower SDBIP is a management tool for the S57 Managers and need not be made public and is a separate document for each internal department. The SDBIP serves as a management, implementation and monitoring tool that will assist the Mayor, Councilors, Municipal Manager and Directors in delivering services to the community

## STRATEGY
Vision and Mission | The strategic vision of the organisation sets the long term goal the Municipality wants to achieve. The vision of Greater Letaba Municipality is: "To be an outstanding agro-processing and eco-cultural tourism hub. The strategic Mission Speaks about what the purpose of Greater Letaba Municipality is: The mission of Greater Letaba Municipality is to ensure an effective, efficient and economically viable municipality through: Provision of accountable, transparent, consultative and co-operative governance Improving the quality of life through economic development and poverty alleviation Provision of sustainable services Ensuring a safe and healthy environment
Strategy map | The Strategy Map depicts the Strategic Objectives on how Greater Letaba Municipality will be able to become an outstanding agro-processing and eco-cultural tourism hub while providing sustainable and affordable services to all. These objectives were positioned in terms of the Balanced Scorecard Perspectives being: Learning and Growth; Institutional Processes; Financial results and Community Satisfaction. All operational outputs (projects, initiatives and process) as contained within the SDBIP are aligned to the attainment of one or more of these objectives.

## OPERATIONAL STRATEGIES
Votes and Operational objectives | Votes | Objectives and Targets
| Municipal Manager Office (Vote 040) | To lead, direct and manage a motivated and inspired Administration and account to the Greater Letaba Municipal Council as Accounting Officer for long term Municipal sustainability to achieve a good creditor rating within the requirements of the relevant legislation and whereas the following sections within the department, i.e. HIV/Aids, Youth, Disabled and Gender Desk, Communication and Internal Auditing is managed for integration, economic growth, marginalised poverty alleviation, efficient, economic and effective communication and service delivery.
| Finance (Vote 050) | To secure sound and sustainable management of the financial affairs of Greater Letaba Municipality by managing the budget and treasury office and advising and if necessary assisting the accounting officer and other directors in their duties and delegation contained in the MFMA. Ensuring that the Greater Letaba Municipality is 100% financially viable when it comes to Cost Coverage and to manage the Grant Revenue of the municipality so that no grant funding is foregone
| Community Services (Vote 028) | To co-ordinate Environmental Health Services, Sports Arts and culture, Education, Libraries, Safety and security, Environmental and Waste management, Health and Social development programmes as well as Disaster management to decrease community affected by disasters
| Infrastructure Development and Economic Planning (Votes 029 and 022) | To ensure that the service delivery requirements for roads are met and maintenance of water, sewerage and electricity are conducted for access to basic services as well as no less than an average of 100% MIG expenditure
To direct the Greater Letaba Municipality’s resources for advanced economic development and investment growth through appropriate town and infrastructure planning in order that an environment is created whereby all residents will have a sustainable income.
| Corporate Services (Vote 046 ) | To ensure efficient and effective operation of council services, human resources and management, legal services and the provision of high quality customer orientated administrative systems. Ensuring 100% compliance to the Skills Development Plan

## MTOD KPI's
KPA 1 MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT
KEY PERFORMANCE INDICATORS
OUTCOME NINE (OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING, PLANNING AND SUPPORT, OUTPUT 4: ACTIONS SUPPORTIVE OF THE HUMAN SETTLEMENT OUTCOMES)
Vote Number | Strategic Objective | Programme | Measurable Objectives | Performance measures | Baseline / Status | Budget | 1st Quarter target | 2nd Quarter target | 3rd Quarter target | 4th Quarter target | Target for 14/15 | Target for 15/16 | Target for 16/17 | Target for 17/18 | Responsible Person
50 | Improved Quality of Life | Indigent Management | To ensure that all indigent groups are registered in the indigent register | % indigent registered (# of registered indigent applied /# of qualifying indigents) | 100% | Operational | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | CFO
22 | Integrated Sustainable Development | IDP | To ensure that IDP and Budget are done within the legislated framework | Draft IDP and Budget adopted by Council by 31 March 2014 | Adopted by Council by 31 March 2014 | Operational | n/a | n/a | Adopted by Council by 31 March 2014 | n/a | Adopted by Council by 31 March 2015 | Adopted by Council by 31 March 2016 | Adopted by Council by 31 March 2017 | Adopted by Council by 31 March 2018 | INDEP/MM
22 | Integrated Sustainable Development | IDP | To ensure that IDP and Budget are done within the legislated framework | Final IDP and budget adopted by 31 May 2014 | Adopted by 31 May 2014 | Operational | n/a | n/a | n/a | Adopted by 31 May 2014 | Adopted by 31 May 2015 | Adopted by 31 May 2016 | Adopted by 31 May 2017 | Adopted by 31 May 2017 | INDEP/MM
22 | Integrated Sustainable Development | IDP | To review drive and monitor implementation of the IDP. | % achievement of milestones on IDP/Budget/PMS process plan | 100% | Operational | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | INDEP/MM
22 | Integrated and Sustainable Human Settlement | Spatial Planning | To ensure proper housing coordination | House demand database submitted within timeframe | Database submitted to COGHSTA by the 31 December 2013 | Operational | n/a | Database submitted to COGHSTA by the 31 December 2013 | n/a | n/a | Database submitted to COGHSTA by the 31 December 2014 | Database submitted to COGHSTA by the 31 December 2015 | Database submitted to COGHSTA by the 31 December 2016 | Database submitted to COGHSTA by the 31 December 2017 | INDEP
22 | Integrated and Sustainable Human Settlement | Spatial Planning | To ensure proper land use management | % land use applications processed (# of land use applications received/# of applications processed) | 100% | Operational | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | INDEP
22 | Integrated and Sustainable Human Settlement | Annual Report | To compile the Draft Annual Report by and submit to council by 31 December 2013 | Draft Annual Report adopted Council by 31 December 2013 | Draft Annual Report adopted Council by 31 December 2013 | Operational | n/a | Draft Annual Report adopted Council by 31 December 2013 | n/a | n/a | Draft Annual Report adopted Council by 31 December 2014 | Draft Annual Report adopted Council by 31 December 2015 | Draft Annual Report adopted Council by 31 December 2016 | Draft Annual Report adopted Council by 31 December 2017 | MM
33 | Improved Governance and Organisational Excellence | Annual Report | To compile the Final Annual Report by and submit to council by 31 January 2014 | Final Annual Report approved by council by 31 January 2014 | Final Annual Report approved by council by 31 January 2014 | Operational | n/a | n/a | Final Annual Report approved by council by 31 January 2014 | n/a | Final Annual Report approved by council by 31 January 2015 | Final Annual Report approved by council by 31 January 2016 | Final Annual Report approved by council by 31 January 2017 | Final Annual Report approved by council by 31 January 2018 | MM
33 | Improved Governance and Organisational Excellence | SDBIP | To ensure that the SDBIP is done within the legislated framework | SDBIP approved by Mayor 28 days after adoption of budget | SDBIP approved by Mayor 28 days after adoption of budget | Operational | n/a | n/a | n/a | SDBIP approved by Mayor 28 days after adoption of budget | SDBIP approved by Mayor 28 days after adoption of budget | SDBIP approved by Mayor 28 days after adoption of budget | SDBIP approved by Mayor 28 days after adoption of budget | SDBIP approved by Mayor 28 days after adoption of budget | MM
54 | Improved Governance and Organisational Excellence | OPMS | To ensure implementation of the performance management system in the organisation | # Quarterly performance reports submitted to Council | 4 | Operational | 1 | 2 | 3 | 4 | 4 | 4 | 4 | 4 | MM
54 | Improved Governance and Organisational Excellence | EPMS | To ensure implementation of the performance management system in the organisation | % S57 staff with signed performance agreements | 100% (5/5) | Operational | 100% (5/5) | n/a | n/a | n/a | 100% (5/5) | 100% (5/5) | 100% (5/5) | 100% (5/5) | MM
54 | Improved Governance and Organisational Excellence | EPMS | To ensure implementation of the performance management system in the organisation | Annual formal assessment (S57) for 2012/2013 conducted | 1 | Operational | 1 | n/a | n/a | n/a | 1 | 1 | 1 | 1 | MM
54 | Improved Governance and Organisational Excellence | EPMS | To ensure implementation of the performance management system in the organisation | Mid Year formal assessment (S57) for 2013/2014 conducted | 1 | Operational | n/a | n/a | 1 | n/a | 1 | 1 | 1 | 1 | MM

## MTOD PROJECTS
KPA 1 MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT PROJECTS
OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING, PLANNING AND SUPPORT, OUTPUT 4: ACTIONS SUPPORTIVE OF THE HUMAN SETTLEMENT OUTCOMES
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project / Initiative | Budget 2013/2014 | Start Date | Completion Date | Milestones Qtr Ending Sept 13 | Milestones Qtr Ending Dec 13 | Milestones Qtr Ending March 2014 | Milestones Qtr Ending June 2014 | Project Owner
54 | Improved Governance and Organisational Excellence | Furniture & Equipment | To purchase 6 fax machines, 2 steel filing cabinets, 6 photocopy machines, 2 mobile units and 3 flip chartboards | Fax machines (6), steel filing cabinets (2), photocopy machines (6), mobile units (2) and flip chartboards (3) | 155000 | 01/10/2013 | 31/03/2014 | n/a | Develop specifications and submit to SCM | Procurement processes, appointment of service provider and delivery of goods | n/a | CORPS
54 | Improved Governance and Organisational Excellence | Furniture & Equipment | To purchase office furniture | Office furniture | 1200000 | 01/10/2013 | 30/06/2014 | n/a | Develop specifications and submit to SCM | Advertisement and appointment of service providers | Delivery of furniture | CORPS
39 | Improved Governance and Organisational Excellence | Information Technology | To purchase colour printer, laptops and computers | Colour printer, laptops and computers | 300000 | 01/10/2013 | 30/06/2014 | n/a | Develop specifications and submit to SCM | Advertisement and appointment of service providers | Delivery of furniture | CORPS
54 | Improved Governance and Organisational Excellence | Furniture & Equipment | To purchase 5 aqua coolers | Aqua coolers (5) and camera | 8000 | 01/01/2014 | 31/03/2014 | n/a | n/a | Submission of specifications and procurement of goods | n/a | CORPS
54 | Improved Governance and Organisational Excellence | Property Services | To purchese filling cabinet for PMS Office | Filling Cabinet for PMS Office | 10000 | 01/01/2014 | 31/03/2014 | n/a | n/a | Submission of specifications and procurement of goods | n/a | CORPS
54 | Improved Governance and Organisational Excellence | Property Services | Building of counter at registry office | Building a counter for registry | 20000 | 01/04/2014 | 30/06/2014 | n/a | n/a | n/a | Submission of specifications and procurement of goods | CORPS
54 | Improved Governance and Organisational Excellence | Property Services | Purchasing of printer for registry, shredding machine, conventional tent, tables and fax machine | Printer for registry, shredding machine, conventional tent (gazebo), tables and fax machine | 78000 | 01/10/2013 | 31/03/2014 | n/a | Develop specifications and submit to SCM | Procurement processes, appointment of service provider and delivery of goods | n/a | CORPS
54 | Improved Governance and Organisational Excellence | Property Services | Purchasing of mobile filing cabinet | Mobile filing cabinet | 60000 | 01/10/2013 | 31/03/2014 | n/a | Develop specifications and submit to SCM | Procurement processes, appointment of service provider and delivery of goods | n/a | CORPS
54 | Improved Governance and Organisational Excellence | Property Services | To install mounted projectors for Mayor and MM's boardrooms; and Council Chamber | Projectors for boardrooms and Council Chamber | 100000 | 01/10/2013 | 31/03/2014 | n/a | Develop specifications and submit to SCM | Procurement processes, appointment of service provider and delivery of goods | n/a | CORPS
54 | Integrated Sustainable Development | IDP | To review the IDP | IDP Review | Operational | 01/07/2013 | 30/06/2014 | 25% implementation of the process plan | 50% implementation of the process plan | 75% implementation of the process plan | 100% implementation of the process plan | INDEP
54 | Improved Governance and Organisational Excellence | SDBIP | To review the SDBIP | SDBIP Review | Operational | 01/07/2013 | 30/06/2014 | n/a | n/a | n/a | SDBIP approved by Mayor 28 days after adoption of budget | MM
54 | Improved Governance and Organisational Excellence | Bursary Scheme | To fund good performing student from needy families | Bursary Scheme | 1056570 | 01/07/2013 | 30/06/2014 | Payment of costs | Advertise for application for the academic year 2013 | Adjudication of all applications | Payment of costs | MM
54 | Improved Governance and Organisational Excellence | Risk Management | To train the risk committee | Risk Committee Training | 118272 | 01/07/2013 | 31/12/2013 | Preparation for the workshop | Workshop conducted and report compiled | n/a | n/a | MM
54 | Improved Governance and Organisational Excellence | Risk Management | To develop risk management startegy | Development and implementation of Risk Assessment Strategy | 59136 | 01/07/2013 | 31/12/2013 | Assess and evaluate current strategy to ensure relevance | Risk Strategy review | n/a | n/a | MM
54 | Improved Governance and Organisational Excellence | OHS | To do health safety awareness events | Heath & Safety Awareness Events | 20000 | 01/07/2013 | 30/06/2014 | 1 Heath & Safety Awareness Events | 1 Heath & Safety Awareness Events | 1 Heath & Safety Awareness Events | 1 Heath & Safety Awareness Events | CORPS
54 | Improved Governance and Organisational Excellence | OHS | To purchase and install signs and posters at offices | OHS Signs and posters | 50000 | 01/01/2014 | 31/03/2014 | n/a | n/a | Submission of specifications and procurement of goods | n/a | CORPS
54 | Improved Governance and Organisational Excellence | OHS | Purchase and distribute safety clothing to employees | Protective Clothing | 40000 | 01/01/2014 | 31/03/2014 | n/a | n/a | Submission of specifications and procurement of goods | n/a | CORPS
46 | Improved Human Resource | Skills Development | To develop the WSP by 30 June 2014 | Workplace Skills Plan | 300000 | 01/07/2013 | 30/06/2014 | Identification of gaps and collection of information | Identification of gaps and collection of information | Develop the Draft WSP | Final WSP submitted | CORPS
39 | Improved Governance and Organisational Excellence | Information Technology | Networking of Kgapane, Senwamokgope and Mokwakwaila sub-offices | Networking of sub-offices | 250000 | 01/10/2013 | 31/03/2014 | n/a | Develop specifications and submit to SCM | Procurement processes, appointment of service provider and complete networking | n/a | CORPS
39 | Improved Governance and Organisational Excellence | Information Technology | Upgrading of Information Technology System | Network upgrade | 200000 | 01/10/2013 | 31/03/2014 | n/a | Develop specifications and submit to SCM | Procurement processes, appointment of service provider and complete network upgrading | n/a | CORPS
39 | Improved Governance and Organisational Excellence | Information Technology | Develop maintenance Plan for all IT Systems | Maintenance Plan for all IT Systems | 100000 | 01/10/2013 | 31/03/2014 | n/a | Develop specifications and submit to SCM | Procurement processes, appointment of service provider and complete maintenance plan | n/a | CORPS
39 | Improved Governance and Organisational Excellence | Internal Audit | Purchase and install teamate Software (Internal Audit) | Teamate Software (Internal Audit) | 200000 | 01/10/2013 | 31/03/2014 | n/a | Develop specifications and submit to SCM | Procurement processes, appointment of service provider and complete project | n/a | MM
39 | Improved Governance and Organisational Excellence | Human Resources | Installation of security features at Customer Care office | security features at Customer Care office | 60000 | 01/10/2013 | 31/03/2014 | n/a | Develop specifications and submit to SCM. | Procurement processes, appointment of service provider and complete the project | n/a | CORPS
39 | Improved Governance and Organisational Excellence | Human Resources | Purchasing and pasting of office signage and labels | Office signage and labelling | 60000 | 01/10/2013 | 31/03/2014 | n/a | Develop specifications and submit to SCM. | Procurement processes, appointment of service provider and complete the project | n/a | CORPS

## BSD PROJECTS
KPA 2 BASIC SERVICE DELIVERY AND INFRASTRUCTURE KEY PERFORMANCE INDICATORSPROJECTS OUTCOME NINE (OUTPUT 2: IMPROVING ACCESS TO BASIC SERVICES, OUTPUT 3: IMPLEMENTATION OF THE COMMUNITY WORK PROGRAMME)
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project / Initiative | Budget 2013/2014 | Start Date | Completion Date | Milestones Qtr Ending Sept 13 | Milestones Qtr Ending Dec 13 | Milestones Qtr Ending March 2014 | Milestones Qtr Ending June 2014 | Project Owner
54 | Access to Sustainable Basic Services | Property Services | To purchase 8 air conditioners by 31 March 2014 (3 for HR and registry) | Air Conditioners | 60000 | 01/01/2014 | 30/06/2014 | n/a | n/a | Develop specifications and submit to supply chain. | Procurement and installation of goods | INDEP/CFO/MM
54 | Access to Sustainable Basic Services | Property Services | Construction of security Gate at DTTC Modjadjiskloof | Security Gate at DTTC Modjadjiskloof | 20000 | 01/10/2013 | 31/03/2014 | n/a | Develop specifications and submit to supply chain | Appointment of service provider and erection of gate | n/a | COMM
54 | Access to Sustainable Basic Services | Property Services | The renovation of Municipal Workshop | Renovation of Municipal Workshop | 500000 | 01/01/2014 | 30/06/2014 | n/a | n/a | Develop specifications and submit to supply chain | Appointment of service provider and complete renovation | INDEP
54 | Access to Sustainable Basic Services | Community Facilities | Construction of Rotterdam Community Hall | Rotterdam Community Hall | 2400000 | 01/10/2013 | 30/06/2014 | n/a | Advertisement for contractors | Appointment of service provider and construction at 50% | Construction progress 100% complete | INDEP
54 | Access to Sustainable Basic Services | Street Lighting | Erection of highmass lights at Phooko, Moroatshehla, Thakgalang, Mapaana, Shamfana, Mmamokgadi, Malematja and Mamphakathi villages | Highmass lights in villages | 4800000 | 01/10/2013 | 31/03/2014 | n/a | Develop specifications and submit to SCM unit. Advertisement for contractors | Appointment for service providers and erection of lights 100% complete | n/a | INDEP
54 | Access to Sustainable Basic Services | Sports and Recreation | Construction of Ga-Kgapane Parks (Below Civic Centre and Mesopotamia) | Construction of Ga-Kgapane Parks | 2600000 | 01/07/2013 | 31/03/2014 | Submission of specifications and advertisement for service providers | Appoint service providers and construction progress at 25% | Construction progress 100% complete | n/a | COMM
31 | Access to Sustainable Basic Services | Sports and Recreation | Enhancement & Beautification of Modjadjiskloof Town Entrances | Enhancement & Beautification of Town Entrances | 300000 | 01/07/2013 | 31/03/2014 | Obtain quotations from Architectures and start with designs | Advertisement for contractors | Construction 100% complete | n/a | COMM
39 | Access to Sustainable Basic Services | Vehicle Licencing and Test | Purchasing of Traffic signs | Traffic Signs | 100000 | 01/07/2013 | 31/12/2013 | Develop specifications and submit to supply chain. | Appointment of service provider and procurement of goods | n/a | n/a | COMM
39 | Access to Sustainable Basic Services | Vehicle Licencing and Test | Purchasing of Uniform for Traffic Interns | Uniform for Traffic Interns | 100000 | 01/07/2013 | 31/12/2013 | Submission of specifications to SCM. Advertisement for service providers | Procurement of traffic uniform (Interns) | n/a | n/a | COMM
31 | Access to Sustainable Basic Services | Sports and Recreation | Construction of 3 outdoor gyms at GaKgapane, Modjadjiskloof and Senwamokgope | Outdoor gyms (3) | 1500000 | 01/10/2013 | 30/06/2014 | n/a | Submission of specifications to SCM. Advertisement for service providers | Appoint service providers and construction progress at 25% | Construction progress 100% complete | COMM
34 | Access to Sustainable Basic Services | Waste Management | To procure compactor for refuse collection | Compactor | 500000 | 01/10/2013 | 31/03/2014 | n/a | Submission of specifications to SCM. Advertisement for service providers | Appointment of service provider and procurement of goods | n/a | COMM
34 | Access to Sustainable Basic Services | Waste Management | Construction of 3 x transfer stations | Transfer stations | 1800000 | 01/07/2013 | 30/06/2014 | Develop specifications and submit to SCM | Advertise for designs and appoint consultant | Appointment of contractor and construction progress 25% complete | Construction progress 100% complete | COMM
34 | Access to Sustainable Basic Services | Waste Management | To procure 14 skip bins & versa trolleys | Skip bins (14) & versa trolleys | 400000 | 01/10/2013 | 31/03/2014 | n/a | Develop specifications and submit to SCM | Appoint service provider and procurement of goods | n/a | COMM
34 | Access to Sustainable Basic Services | Waste Management | To procure skip truck | Skip truck | 900000 | 01/10/2013 | 31/03/2014 | n/a | Develop specifications and submit to SCM | Appoint service provider and procurement of goods | n/a | COMM
34 | Access to Sustainable Basic Services | Waste Management | To procure bakkie for waste management | Waste bakkie | 250000 | 01/10/2013 | 31/03/2014 | n/a | Develop specifications and submit to SCM | Appoint service provider and procurement of goods | n/a | COMM
34 | Access to Sustainable Basic Services | Waste Management | Construction of municipal landfill site | Landfill site | 10000000 | 01/01/2014 | 30/06/2014 | n/a | n/a | Construction progress at 50% | Construction progress at 100% | COMM
29 | Access to Sustainable Basic Services | Road and Stormwater | To construct bridge at Ga-Kgapane Stadium | Ga-Kgapane Stadium Bridge | 5800000 | 01/07/2013 | 30/06/2014 | Appoint consultant and completion of designs. | Advertise for contractors | Construction progress at 50% | Construction progress at 100% | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | To construct a bridge to Shawela graveyard | Shawela Bridge | 5200000 | 01/07/2013 | 30/06/2014 | Appoint consultant and completion of designs. | Advertise for contractors | Construction progress at 50% | Construction progress at 100% | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | To purchase two (2) graders | Graders | 5400000 | 01/10/2013 | 31/03/2014 | n/a | Develop specifications and submit to SCM | Appoint service provider and procurement of goods | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | To purchase water cart for roads maintenance | Water Cart | 600000 | 01/10/2013 | 31/03/2014 | n/a | Develop specifications and submit to SCM | Appoint service provider and procurement of goods | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | To purchase TLB (Backhoe Loader) for roads maintenance | TLB (Backhoe loader) | 682000 | 01/10/2013 | 31/03/2014 | n/a | Develop specifications and submit to SCM | Appoint service provider and procurement of goods | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | To purchase a tipper truck | Tipper truck | 620000 | 01/10/2013 | 31/03/2014 | n/a | Develop specifications and submit to SCM | Appoint service provider and procurement of goods | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | To purchase bulldozer | Bulldozer | 2600000 | 01/10/2013 | 31/03/2014 | n/a | Develop specifications and submit to SCM | Appoint service provider and procurement of goods | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Design of streets from gravel to paving blocks at Mothobeki | Mothobeki Street Paving | 450000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to SCM | Advertise for consultant and designs | Appoint consultants to complete designs | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Design of streets from gravel to paving blocks at Mamaila Phaphadi | Mamaila Phaphadi Street Paving | 450000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to SCM | Advertise for consultant and designs | Appoint consultants to complete designs | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Design of streets from gravel to paving blocks at Phooko Headkraal | Phooko Headkraal Street Paving | 320000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to SCM | Advertise for consultant and designs | Appoint consultants to complete designs | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Design of streets from gravel to paving blocks at Raphahlelo Headkraal | Raphahlelo Street Paving | 450000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to SCM | Advertise for consultant and designs | Appoint consultants to complete designs | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of streets from gravel to paving blocks at Jamela village for 1,8 km | Jamela Street Paving | 3600000 | 01/07/2013 | 31/03/2014 | Appoint contractor to resume with construction work | construction progress 50% | Construction progress 100% complete | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of streets from gravel to paving blocks at Sedibeng village for 2,5 km | Sedibeng Street Paving | 6000000 | 01/07/2013 | 31/03/2014 | Appoint contractor to resume with construction work | construction progress 50% | Construction progress 100% complete | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of streets from gravel to paving blocks at Sefofotse village for 1,8km | Sefofotse Street Paving | 3600000 | 01/07/2013 | 31/03/2014 | Appoint contractor to resume with construction work | construction progress 50% | Construction progress 100% complete | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of streets from gravel to paving blocks at Rotterdam (Duvula) for 1,2km | Rotterdam (Duvula) Street Paving | 3200000 | 01/07/2013 | 31/03/2014 | Appoint contractor to resume with construction work | construction progress 50% | Construction progress 100% complete | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of streets from gravel to paving blocks at Mamaila Kolobetona for 1,2 km | Mamaila Kolobetona Street Paving | 3200000 | 01/07/2013 | 31/03/2014 | Appoint contractor to resume with construction work | construction progress 50% | Construction progress 100% complete | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of streets from gravel to paving blocks at Rotterdam (Mahonsi) for 0,7 km | Rotterdam (Mahonsi) Street Paving | 2000000 | 01/07/2013 | 31/03/2014 | Appoint contractor to resume with construction work | construction progress 50% | Construction progress 100% complete | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of streets from gravel to paving blocks at Medingen for 2,0 km | Medingen Street Paving | 5500000 | 01/07/2013 | 31/03/2014 | Appoint contractor to resume with construction work | construction progress 50% | Construction progress 100% complete | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of streets from gravel to paving blocks at Matswi for 1,8 km | Matswi Street Paving | 4600000 | 01/07/2013 | 31/03/2014 | Appoint contractor to resume with construction work | construction progress 50% | Construction progress 100% complete | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | To improve access to existing taxi rank at Mokwakwaila for 1km | Access road to Mokwakwaila Taxi Rank | 3100000 | 01/07/2013 | 30/06/2014 | Develop terms of reference and advertise for consultant | Appoint consultant to resume with designs | Complete designs and advertise for construction | Appoint contractor and Construction progress at 100% | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Construction of gabions at Uitzicht street, Modjadjiskloof | Modjadjiskloof Gabions | 1000000 | 01/07/2013 | 30/06/2014 | Develop terms of reference and advertise for consultant | Appoint consultant to resume with designs | Complete designs and advertise for construction | Appoint contractor and Construction progress at 100% | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of Hill and Kerk Streets from gravel to tar for 0,8km | Upgrading of Hill and Kerk Streets | 2800000 | 01/07/2013 | 30/06/2014 | Appoint consultant and completion of designs. | Advertise for contractors | Construction progress at 50% | Construction progress at 100% | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Construction of sidewalks at Ga-Kgapane streets for 6km | Ga-Kgapane Sidewalks | 2500000 | 01/07/2013 | 30/06/2014 | Develop specifications and submit to SCM. Advertise for construction | Appointment of contractors and resume with construction | Construction progress at 50% | Construction progress at 100% | INDEP
34 | Access to Sustainable Basic Services | Vehicle licencing and testing | To purchase bakkie for Traffic of Officers | Traffic Bakkie | 250000 | 01/10/2013 | 31/03/2014 | n/a | Develop specification and submit to SCM | Appoint service provider and procurement of goods | n/a | COMM
34 | Access to Sustainable Basic Services | Vehicle licencing and testing | To purchase Sedan for Traffic of Officers | Traffic Sedan | 250000 | 01/10/2013 | 31/03/2014 | n/a | Develop specification and submit to SCM | Appoint service provider and procurement of goods | n/a | COMM
34 | Access to Sustainable Basic Services | Vehicle licencing and testing | To purchase 6 stop watches | Stop Watches (6) | 5000 | 01/10/2013 | 31/03/2014 | n/a | Develop specification and submit to SCM | Appoint service provider and procurement of goods | n/a | COMM
34 | Access to Sustainable Basic Services | Vehicle licencing and testing | To procure road marking machine | Road marking machine | 150000 | 01/10/2013 | 31/03/2014 | n/a | Develop specification and submit to SCM | Appoint service provider and procurement of goods | n/a | COMM
52 | Access to Sustainable Basic Services | Electricity Distribution | To install maximum demand metering | Maximum demand metering | 1200000 | 01/07/2013 | 31/03/2014 | Advertisement for contractors | Appointment of contractors and resume with construction. Progress at 25% | Construction progress at 100% | n/a | INDEP
52 | Access to Sustainable Basic Services | Electricity Distribution | To upgrade electricty network at Modjadjiskloof to NER standard - NER Compliance | Upgrading electricty network to NER standard | 1200000 | 01/07/2013 | 30/06/2014 | Develop specifications and submit to SCM. Advertise for construction | Appointment of contractors and resume with construction | Construction progress at 50% | Construction progress at 100% | INDEP
52 | Access to Sustainable Basic Services | Electricity Distribution | Purchasing of bakkie for electricity maintenance | Electricity Bakkie | 300000 | 01/10/2013 | 31/03/2014 | n/a | Develop specification and submit to SCM | Appoint service provider and procurement of goods | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of streets from gravel to paving blocks at Thakgalang for 2,0 km | Thakgalang Street Paving | 5400000 | 01/07/2013 | 31/03/2014 | Appoint contractor to resume with construction work | construction progress 50% | Construction progress 100% complete | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of streets from gravel to paving blocks at Rapitsi for 0,7 km | Rapitsi Street Paving | 1800000 | 01/07/2013 | 31/03/2014 | Appoint contractor to resume with construction work | construction progress 50% | Construction progress 100% complete | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of streets from gravel to paving blocks at Sekgopo for 1,0 km | Sekgopo Street Paving | 2700000 | 01/07/2013 | 31/03/2014 | Appoint contractor to resume with construction work | construction progress 50% | Construction progress 100% complete | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of streets from gravel to paving blocks at Mandela Park for 1,8 km | Mandela Park Street Paving | 3600000 | 01/07/2013 | 31/03/2014 | Appoint contractor to resume with construction work | construction progress 50% | Construction progress 100% complete | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Upgrading of streets from gravel to paving blocks at Modjadji Headkraal for 1,8 km | Modjadji Headkraal Street Paving | 4900000 | 01/07/2013 | 31/03/2014 | Appoint contractor to resume with construction work | construction progress 50% | Construction progress 100% complete | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Design of Ga-Kgapane Streets from gravel to paving blocks | Ga-Kgapane Streets Upgrading | 500000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to SCM | Advertise for consultant and designs | Appoint consultants to complete designs | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Design of Senwamokgope Streets from gravel to paving blocks | Senwamokgope Streets Upgrading | 500000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to SCM | Advertise for consultant and designs | Appoint consultants to complete designs | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Design of Modjadji Valley Streets from gravel to paving blocks | Modjadji Valley Streets Upgrading | 400000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to SCM | Advertise for consultant and designs | Appoint consultants to complete designs | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Design of streets from gravel to paving blocks at Kuranta | Kuranta Street Paving | 400000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to SCM | Advertise for consultant and designs | Appoint consultants to complete designs | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Design of streets from gravel to paving blocks at Mokgoba | Mokgoba Street Paving | 400000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to SCM | Advertise for consultant and designs | Appoint consultants to complete designs | n/a | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Design of streets from gravel to paving blocks at Ratjeke | Ratjeke Street Paving | 400000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to SCM | Advertise for consultant and designs | Appoint consultants to complete designs | n/a | INDEP
29 | Access to Sustainable Basic Services | Community Facilities | Construction of market stalls at Maphalle | Maphalle Market Stalls | 500000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to SCM | Advertise for consultant and designs | Appoint consultants to complete designs | n/a | INDEP
29 | Access to Sustainable Basic Services | Community Facilities | Design of Library for contruction at Senwamokgope | Senwamokgope Library | 250000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to SCM | Advertise for consultant and designs | Appoint consultants to complete designs | n/a | INDEP
29 | Access to Sustainable Basic Services | Community Facilities | Design of Library for contruction at Sekgopo | Sekgopo Library | 250000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to SCM | Advertise for consultant and designs | Appoint consultants to complete designs | n/a | INDEP
29 | Access to Sustainable Basic Services | Community Facilities | Upgrading and renovation of Kgapane Stadium | Ga-Kgapane Stadium | 1000000 | 01/07/2013 | 30/06/2014 | Advertisement for contractors | Appointment of contractors and resume with construction | Construction progress at 50% | Construction progress 100% complete | INDEP
29 | Access to Sustainable Basic Services | Community Facilities | Construction of Lebaka Sports Complex phase III | Lebaka Sports Complex | 9320000 | 01/07/2013 | 30/06/2014 | Review of designs and specifications | Construction progress at 10% | Construction progress at 80% | Construction progress 100% complete | INDEP
29 | Access to Sustainable Basic Services | Community Facilities | Construction of Sekgopo Sports complex phase III | Sekgopo Sports complex | 12020000 | 01/07/2013 | 30/06/2014 | Review of designs and specifications | Construction progress at 10% | Construction progress at 80% | Construction progress 100% complete | INDEP
29 | Access to Sustainable Basic Services | Community Facilities | Construction of Shaamiriri Sports Complex phase III | Shaamiriri Sports Complex | 7890000 | 01/07/2013 | 30/06/2014 | Review of designs and specifications | Construction progress at 10% | Construction progress at 80% | Construction progress 100% complete | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Development of Intergrated Roads & Transport Plan | Intergrated Roads & Transport Plan | 400000 | 01/07/2013 | 30/06/2014 | n/a | Develop terms of reference and submit to SCM. Advertise for consultants | Appoint consultants and start with draft plan | Complete Integrated Roads & Transport Plan | INDEP
29 | Access to Sustainable Basic Services | Electricity Distribution | Development of Electriciry Master Plan | Electricity Master Plan | 844800 | 01/07/2013 | 30/06/2014 | n/a | Develop terms of reference and submit to SCM. Advertise for consultants | Appoint consultants and start with draft plan | Complete Master Plan | INDEP
29 | Access to Sustainable Basic Services | Road and Stormwater | Repairing of two (2) graders standing at ELB | Repairing of graders | 500000 | 01/07/2013 | 31/03/2014 | n/a | Invite bids from service providers | Appoint service provider and repair graders | n/a | INDEP

## LED PROJECTS
KPA 3 LOCAL ECONOMIC DEVELOPMENT PROJECTS OUTPUT 3: IMPLEMENTATION OF THE COMMUNITY WORK PROGRAMME
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project / Initiative | Budget 2013/2014 | Start Date | Completion Date | Milestones Qtr Ending Sept 13 | Milestones Qtr Ending Dec 13 | Milestones Qtr Ending March 2014 | Milestones Qtr Ending June 2014 | Project Owner
22 | Improved Local Economy | Planning and Development | Purchasing of land to expand development | Purchasing of land | 12000000 | 01/07/2014 | 31/03/2014 | Development of terms of reference and submit to SCM | Advertisement and submission of bids by interested parties | Procurement of land | n/a | INDEP
22 | Improved Local Economy | Local Economic Development | Construction of paving at Tourism centre | Paving at Tourism Information Centre | 250000 | 01/10/2014 | 30/06/2014 | n/a | Develop specifications and submit to SCM for adverisement | Appoint service provider and resume with construction | Construction progress 100% complete | INDEP
22 | Improved Local Economy | Local Economic Development | Construction activities at Show Ground | GLM Show Ground | 1000000 | 01/07/2014 | 31/03/2014 | Develop specifications and submit to SCM for advertisement | Appoint service provider and resume with construction | Construction progress at 100% | n/a | INDEP
22 | Improved Local Economy | Local Economic Development | Support on Youth Development Programme / project | Youth Development Programme | 200000 | 01/07/2014 | 30/06/2014 | Support initiatives for Khumeloni Youth Development Programme | Support initiatives for Khumeloni Youth Development Programme | Support initiatives for Khumeloni Youth Development Programme | Support initiatives for Khumeloni Youth Development Programme | INDEP
22 | Improved Local Economy | Planning and Development | To peg sites at Modjadjiskloof Extension 11 | Pegging of Modjadjiskloof Extension 11 sites | 100000 | 01/07/2014 | 30/06/2014 | Development of terms of reference and submit to SCM | Advertise for appointment of professional service provider | Appoint service provider and resume with pegging | Pegging progress100% complete | INDEP
22 | Improved Local Economy | Planning and Development | Rezoning and demarcation of parks at Ga-Kgapane | Rezoning of Kgapane Parks | 350000 | 01/07/2014 | 30/06/2014 | Development of terms of reference and submit to SCM | Advertise for appointment of professional service provider | Appoint service provider and resume with rezoning | Rezoning progress100% complete | INDEP
22 | Improved Local Economy | Local Economic Development | Feasibility Study of Potential LED projects | Feasibility Study (LED) | 350000 | 01/07/2014 | 30/06/2014 | Development of terms of reference and submit to SCM | Advertise for appointment of professional service provider | Appoint service provider and resume with the study | Feasibility study progress 100% complete | INDEP
22 | Improved Local Economy | Local Economic Development | Establish agro-processing initiatives and support | Agro-processing projects | 316000 | 01/07/2014 | 30/06/2014 | n/a | Support and implement agro-processing initiatives | Support and implement agro-processing initiatives | Support and implement agro-processing initiatives | INDEP
22 | Improved Local Economy | Local Economic Development | To do feasibility study by 30 June 2013 | Feasibility Study of Manokwe Caves | 250000 | 01/07/2013 | 31/03/2013 | Draft feasibility study complete and submitted to the municipality | Feasibility study 100% complete | n/a | n/a | INDEP
22 | Improved Local Economy | Planning and Development | To demarcate and peg sites at Goudplaas | Demarcation of sites - Goudplaas | 400000 | 01/07/2014 | 30/06/2014 | Development of terms of reference and submit to SCM | Advertise for appointment of professional service provider | Appoint service provider and resume with demarcation | Demarcation progress 100% complete | INDEP
22 | Improved Local Economy | Planning and Development | To peg sites at Vrystaat Farm - Modjadjiskloof | Site pegging (Vrystaat) | 200000 | 01/07/2014 | 30/06/2014 | Development of terms of reference and submit to SCM | Advertise for appointment of professional service provider | Appoint service provider and resume with pegging | Pegging study progress 100% complete | INDEP
22 | Improved Local Economy | Local Economic Development | To review the LED strategy by 30 June 2014 | Reveiw of LED strategy (MSIG) | 200000 | 01/07/2013 | 30/12/2013 | Draft LED Strategy complete and submitted to the municipality | Final LED Strategy submitted to Council for approval | n/a | n/a | INDEP
22 | Improved Local Economy | Local Economic Development | Review of existing Spatial Development Framework (SDF) | SDF Review | 400000 | 01/07/2014 | 30/06/2014 | Development of terms of reference and submit to SCM | Advertise for appointment of professional service provider | Appoint service provider and resume with review | SDF 100% complete | INDEP
22 | Improved Local Economy | Local Economic Development | To attend and participate in Tourism Indaba by 31 May 2014 | Tourism Indaba | 150000 | 01/07/2013 | 31/06/2014 | Review of outcomes from previous Tourism Indaba event | Implementation of resolutions of the Tourism Indaba report | Preparation for the Tourism Indaba | Attend and participate in the Tourism Indaba | INDEP
22 | Improved Local Economy | OHS | To organize and conduct environmental programme within the municipality | Environmental Programmes | 274000 | 01/07/2013 | 31/06/2014 | Coordinate and conduct enviromental related events and campaigns (1 per quarter) | Coordinate and conduct enviromental related events and campaigns (1 per quarter) | Coordinate and conduct enviromental related events and campaigns (1 per quarter) | Coordinate and conduct enviromental related events and campaigns (1 per quarter) | COMM
34 | Improved Local Economy | Sports and Recreation | To organise the rainmaking ceremony by 31 December 2013 | Rain making ceremony | 100000 | 01/07/2013 | 31/12/2013 | Attend to preparatory meetings | Participate in the celebratory activities | n/a | n/a | COMM
34 | Improved Local Economy | Sports and Recreation | To organise the Wolkberg sports day by 31 March 2014 | Wolkberg Sports day | 100000 | 01/07/2013 | 31/03/2014 | Development of Implementation plan | Advertisement to invite various sporting codes | Tournament held for various sporting codes | n/a | COMM
34 | Improved Local Economy | Sports and Recreation | To organise SAIMSA games by 31 December 2013 | SAIMSA games | 500000 | 01/07/2013 | 31/12/2013 | GLM soccer, netball and Pool teams to compete in SAIMSA games | n/a | n/a | n/a | COMM
34 | Improved Local Economy | Sports and Recreation | To organise and host various sport codes | Sports Activities | 300000 | 01/07/2013 | 31/03/2014 | Development of Implementation plan | Advertisement to invite various sporting codes | Tournament held for various sporting codes | n/a | COMM
34 | Improved Local Economy | Sports and Recreation | To organise event for cultural activities | Cultural Activities | 100000 | 01/07/2013 | 30/06/2014 | n/a | Development of Implementation plan | Advertisement to invite cultural related groups | Event held for various cultural activities | COMM
34 | Improved Local Economy | Sports and Recreation | To organise Choral Music Competition by 31 March 2014 | Coral Music Competition | 80000 | 01/07/2013 | 31/03/2014 | Develop implementation plan and advertisement to invite participants | Group stages competition | Final performance competition | n/a | COMM

## MFMV KPI
KPA 4 MUNICIPAL FINANCIAL VIABILITY KEY PERFORMANCE INDICATORS OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY
Vote Nr | Strategic Objective | Progranmes | Measurable Objectives | Performance measures | Baseline / Status | Budget 2013/2014 | 1st Quarter target | 2nd Quarter target | 3rd Quarter target | 4th Quarter target | Target for 13/14 | Target for 14/15 | Target for 15/16 | Target for 16/17 | Responsible Person
50 | Sustainable Financial Institution | Budget and Reporting | To ensure that financial information is supplied to relevant authorities within timeframe | Financial information supplied to relevant office by 31 May | Information was submitted by 31 May 2013 | Operational | n/a | n/a | n/a | 100% | 100% | 100% | 100% | 100% | B&T
50 | Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality | % capital budget spent as approved by Council | 100% | Operational | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | B&T/MM/INDEP
50 | Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality | % MIG expenditure | 100% | 46950000 | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | MM/INDEP
50 | Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality | % FMG expenditure | 100% | 1550000 | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | B&T/MM/INDEP
50 | Sustainable Financial Institution | Expenditure Management | To effectively manage the financial affairs of the municipality | % MSIG expenditure | 100% | 890000 | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | B&T/MM/INDEP

## MFMV PROJECTS
KPA 4 MUNICIPAL FINANCIAL VIABILITY PROJECTS OUTCOME NINE (OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY)
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project / Initiative | Budget 2013/2014 | Start Date | Completion Date | Milestones Qtr Ending Sept 13 | Milestones Qtr Ending Dec 13 | Milestones Qtr Ending March 2014 | Milestones Qtr Ending June 2014 | Project Owner
50 | Sustainable Financial Institution | Indigent Management | To register the indigents. | Updating of Indigent Register | Operational | 01/07/2013 | 30/06/2014 | Collection of information on indigent households and update the register | Collection of information on indigent households and update the register | Collection of information on indigent households and update the register | Collection of information on indigent households and update the register | B&T
50 | Sustainable Financial Institution | Revenue Management | Review of Revenue Enhancement Strategy | Revenue Enhancement Strategy | 106000 | 01/07/2013 | 30/06/2014 | n/a | Develop terms of reference and submit to bid specification committee. Advertisement for service providers | Appoint service provider and submission of draft Revenue Enhancement Strategy | Revenue Enhancement Strategy complete | B&T
50 | Sustainable Financial Institution | Revenue Management | To upgrade household information | Data cleansing | 106000 | 01/07/2013 | 30/09/2013 | Update households information on billing system by end of quarter | n/a | n/a | n/a | B&T
50 | Sustainable Financial Institution | Asset Management | To monitor the process of unbundling and make progress report | Unbundling of Infrastructure Assets to update the asset register | 200000 | 01/10/2013 | 31/03/2014 | n/a | Continuation of unbundling of assets and updating of asset register. | Continuation of unbundling of assets and updating of asset register. | n/a | B&T
50 | Sustainable Financial Institution | Supply Chain Management | Purchasing of the Automated Procurement Software | Automated Procurement Software | 250000 | 01/10/2013 | 30/06/2014 | n/a | Develop specifications and submit to bid specification committee. | Advertise tender and appointment of service provider. | Installation of automated procurement software completed. | B&T
50 | Sustainable Financial Institution | Supply Chain Management | Linking the Assets to the GIS software | Linking the Assets to the GIS software | 150000 | 01/07/2013 | 31/03/2014 | Develop terms of reference and submit to the bid specification committee. | Advertise tender and appointment of service provider. | Linking of assets to GIS software. | n/a | B&T
50 | Sustainable Financial Institution | Asset Management | Updating of valuation roll | Valuation Roll | 159600 | 01/07/2013 | 31/12/2013 | Conduct assessment of supplementary valuation roll. | Complete assessment of supplementary valuation roll. | n/a | n/a | B&T
50 | Sustainable Financial Institution | Asset Management | To purchase two (2) Small Bakkie for water reading | Small Bakkie | 400000 | 01/10/2013 | 31/03/2014 | n/a | Develop specifications and submit to supply chain. | Advertise tender, appointment of service provider and procurement of goods. | n/a | B&T
50 | Sustainable Financial Institution | Asset Management | To purchase two (2) small bakkies | Sedan | 200000 | 01/10/2013 | 31/03/2014 | n/a | Develop specifications and submit to supply chain. | Advertise tender, appointment of service provider and procurement of goods. | n/a | B&T
50 | Sustainable Financial Institution | Office furnisher | To procure printers (2) - Salary Section & Revenue Section | Printers (2) - Salary Section & Revenue Section | 400000 | 01/10/2013 | 31/03/2014 | n/a | Develop specifications and submit to supply chain. | Advertise tender, appointment of service provider and procurement of goods. | n/a | B&T
50 | Sustainable Financial Institution | Auxillary Services | Supply and delivery of fuel | Fuel supply | 1600000 | 01/10/2013 | 31/12/2013 | Develop specifications for appointment of service providers | Appoint service provider for delivery of fuel | n/a | n/a | B&T

## GGPP KPI's
KPA 5 GOOD GOVERNANCE AND PUBLIC PARTICIPATION KEY PERFORMANCE INDICATORS OUTCOME 9 (OUTPUT 5: DEEPEN DEMOCRACY THROUGH A REFINED WARD COMMITTEE MODEL, OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY)
Vote Nr | Strategic Objective | Programmes | Measurable Objectives | Performance measures | Baseline / Status | Budget 2013/2014 | 1st Quarter target | 2nd Quarter target | 3rd Quarter target | 4th Quarter target | Target for 13/14 | Target for 14/15 | Target for 15/16 | Target for 16/17 | Responsible Person
54 | Improved Governance and Organisational Excellence | Ward Committee | To ensure full participation of ward committees | # ward committees evaluated per month | 29 | Operational | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | MM/CORPS
54 | Improved Governance and Organisational Excellence | Ward Committee |  | % complaints attended (# of community complaints received/ # of complaints atteneded to). | 100% | Operational | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | MM
54 | Improved Governance and Organisational Excellence | Local Imbizos | To ensure community participation | # of local imbizos held by the Mayor | 4 | 1000000 | 1 | 2 | 3 | 4 | 4 | 4 | 4 | 4 | MM
54 | Improved Governance and Organisational Excellence | Local Imbizos | To ensure community participation | % public participation events publicised on the newspaper and website) (# fo public participation events publicised in the newspapers and website | 100% | Operational | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | MM
54 | Improved Governance and Organisational Excellence | Traditional Leaders | To establish a good relationship with traditional leaders | # traditional leaders invited to take part in council | 9 | Operational | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | MM
54 | Improved Governance and Organisational Excellence | Auditing | To promote accountability | % AG queries raised in last financial year addressed at the end of the quarter of the current financial year | 100% | Operational | n/a | n/a | n/a | 100% | 100% | 100% | 100% | 100% | MM
54 | Improved Governance and Organisational Excellence | Communication | To promote effective and efficient communication | % of article issued to the media on Mayoral events (# of events hosted/# of article issued) | 100% | Operational | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | MM
54 | Improved Governance and Organisational Excellence | Communication | To promote effective and efficient communication | # of newslatters issued | 4 | Operational | 1 | 2 | 3 | 4 | 4 | 4 | 4 | 4 | MM
54 | Improved Governance and Organisational Excellence | Communication | To promote effective and efficient communication | # of meetings held by the Commicators Forum | 4 | Operational | 1 | 2 | 3 | 4 | 4 | 4 | 4 | 4 | MM
54 | Improved Governance and Organisational Excellence |  | To ensure proper contract management | % appointed service providers with Service Level Agreement (# of service providers appointed/# of service providers with service level agreement) | 100% | Operational | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | CORPS/MM
46 | Improved Human Resource |  | To ensure effective implementation of the WSP | % employees trained as per the WSP | 100% | Operational | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | CORPS
46 | Improved Human Resource |  | To ensure a health and safe working environment | # of wellness campaign conducted per quarter | 4 | Operational | 1 | 2 | 3 | 4 | 4 | 4 | 4 | 4 | CORPS

## GGPP PROJECTS
KPA 5 GOOD GOVERNANCE AND PUBLIC PARTICIPATION PROJECTS OUTPUT 5: DEEPEN DEMOCRACY THROUGH A REFINED WARD COMMITTEE MODEL, OUTPUT 6: ADMINISTRATIVE AND FINANCIAL CAPABILITY)
Vote Nr | Strategic Objective | Programme | Measurable Objective | Project / Initiative | Budget 2013/2014 | Start Date | Completion Date | Milestones Qtr Ending Sept 13 | Milestones Qtr Ending Dec 13 | Milestones Qtr Ending March 2014 | Milestones Qtr Ending June 2014 | Project Owner
40 | Improved Governance and Organisational Excellence | Furniture and Equipments | To procure recording system/ video camera | Recording System/ Video Camera | 20000 | 01/10/2013 | 31/03/2014 | n/a | Develop specifications and submit to SCM. Advertise for appointment of service providers | Appointment of service provider and procure goods | n/a | CORPS
40 | Improved Governance and Organisational Excellence | Furniture and Equipments | To procure council vehicles | Council Vehicles | 600000 | 01/10/2013 | 31/03/2014 | n/a | Develop specifications and submit to SCM. Advertise for appointment of service providers | Appointment of service provider and procure goods | n/a | CORPS
54 | Improved Governance and Organisational Excellence | Property Services | Interior design and decoration of the Council Chamber and foyer including purchasing of podium | Decoration of Council Chamber (Including the foyer and podium) | 1505000 | 01/07/2013 | 31/03/2014 | Develop specifications and submit to SCM. Advertise for appointment of service providers | Appointment of service provider and resume with design | Decoration completed | n/a | CORPS

## Capital Works Plan 1
VOTE | DIRECTORATE | WARD | PROJECT NAME | TOTAL | PLANNED START DATE | PLANNED END DATE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE
54 | Furniture & Equipment | 29 | Fax machines (6), steel filing cabinets (2), photocopy machines (6), mobile units (2) and flip chartboards (3) | 155000 |  |  | MARCH: 155000
54 | Furniture & Equipment | 29 | Office furniture | 1200000 |  |  | JUNE: 1200000
39 | Information Technology | 29 | Colour printer, laptops and computers | 300000 |  |  | JUNE: 300000
54 | Furniture & Equipment | 29 | Aqua coolers (5) and camera | 8000 |  |  | MARCH: 8000
54 | Property Services | 29 | Filling Cabinet for PMS Office | 10000 |  |  | MARCH: 10000; JUNE: 20000
54 | Property Services | 29 | Building a counter for registry | 20000
54 | Property Services | 29 | Printer for registry, shredding machine, conventional tent (gazebo), tables and fax machine | 78000 |  |  | MARCH: 78000
54 | Property Services | 29 | Mobile filing cabinet | 60000 |  |  | MARCH: 60000
54 | Property Services | 29 | Projectors for boardrooms and Council Chamber | 100000 |  |  | MARCH: 100000
54 | OHS | 29 | OHS Signs and posters | 50000 |  |  | MARCH: 50000
39 | Information Technology | 4, 13, 27 | Networking of sub-offices | 250000 |  |  | MARCH: 250000
39 | Information Technology | 29 | Network upgrade | 200000 |  |  | MARCH: 200000
39 | Human Resources | 29 | security features at Customer Care office | 60000 |  |  | MARCH: 60000
39 | Human Resources | 29 | Office signage and labelling | 60000 |  |  | MARCH: 60000
54 | Property Services | 29 | Air Conditioners | 60000 |  |  | JUNE: 60000
54 | Property Services | 29 | Security Gate at DTTC Modjadjiskloof | 20000 |  |  | MARCH: 20000
54 | Property Services | 29 | Renovation of Municipal Workshop | 500000 |  |  | JUNE: 500000
54 | Community Facilities | 16, 28 | Rotterdam Community Hall | 2400000 |  |  | MARCH: 300000; APRIL: 800000; MAY: 800000; JUNE: 500000
54 | Street Lighting | Various | Highmass lights in villages | 4800000 |  |  | MARCH: 4800000
54 | Sports and Recreation | 3, 4 | Construction of Ga-Kgapane Parks | 2600000 |  |  | JANUARY: 800000; FEBRUARY: 1000000; MARCH: 800000
31 | Sports and Recreation | 29 | Enhancement & Beautification of Town Entrances | 300000 |  |  | MARCH: 300000
39 | Vehicle Licencing and Test | 29 | Traffic Signs | 100000 |  |  | DECEMBER: 100000
31 | Sports and Recreation | 3, 4,13, 27 | Outdoor gyms (3) | 1500000 |  |  | APRIL: 500000; MAY: 500000; JUNE: 500000
34 | Waste Management | 29 | Compactor | 500000 |  |  | MARCH: 500000
34 | Waste Management | 3, 4,13, 27 | Transfer stations | 1800000 |  |  | APRIL: 500000; MAY: 800000; JUNE: 500000
34 | Waste Management | Various | Skip bins (14) & versa trolleys | 400000 |  |  | MARCH: 400000
34 | Waste Management | 29 | Skip truck | 900000 |  |  | MARCH: 900000
34 | Waste Management | 29 | Waste bakkie | 250000 |  |  | MARCH: 250000
34 | Waste Management | 20 | Landfill site | 10000000 |  |  | FEBRUARY: 1000000; MARCH: 3000000; APRIL: 2000000; MAY: 2000000; JUNE: 2000000
29 | Road and Stormwater | 4 | Ga-Kgapane Stadium Bridge | 5800000 |  |  | APRIL: 1000000; MAY: 2800000; JUNE: 2000000
29 | Road and Stormwater | 20 | Shawela Bridge | 5200000 |  |  | APRIL: 1000000; MAY: 1200000; JUNE: 2000000
29 | Road and Stormwater | 29 | Graders | 5400000 |  |  | MARCH: 5400000
29 | Road and Stormwater | 29 | Water Cart | 600000 |  |  | MARCH: 600000
29 | Road and Stormwater | 29 | TLB (Backhoe loader) | 682000 |  |  | MARCH: 682000
29 | Road and Stormwater | 29 | Tipper truck | 620000 |  |  | MARCH: 620000
29 | Road and Stormwater | 29 | Bulldozer | 2600000 |  |  | MARCH: 2600000
29 | Road and Stormwater | 21 | Mothobeki Street Paving | 450000 |  |  | MARCH: 450000
29 | Road and Stormwater | 22 | Mamaila Phaphadi Street Paving | 450000 |  |  | MARCH: 450000
29 | Road and Stormwater | 15 | Phooko Headkraal Street Paving | 320000 |  |  | MARCH: 320000
29 | Road and Stormwater | 15 | Raphahlelo Street Paving | 450000 |  |  | MARCH: 450000
29 | Road and Stormwater | 19 | Jamela Street Paving | 3600000 |  |  | JANUARY: 1000000; FEBRUARY: 1600000; MARCH: 1000000
29 | Road and Stormwater | 23 | Sedibeng Street Paving | 6000000 |  |  | JANUARY: 1000000; FEBRUARY: 3000000; MARCH: 2000000
29 | Road and Stormwater | 23 | Sefofotse Street Paving | 3600000 |  |  | JANUARY: 1000000; FEBRUARY: 1600000; MARCH: 1000000
29 | Road and Stormwater | 28 | Rotterdam (Duvula) Street Paving | 3200000 |  |  | JANUARY: 1000000; FEBRUARY: 1200000; MARCH: 1000000
29 | Road and Stormwater | 17 | Mamaila Kolobetona Street Paving | 3200000 |  |  | JANUARY: 1000000; FEBRUARY: 1200000; MARCH: 1000000
29 | Road and Stormwater | 28 | Rotterdam (Mahonsi) Street Paving | 2000000 |  |  | FEBRUARY: 1200000; MARCH: 800000
29 | Road and Stormwater | 5 | Medingen Street Paving | 5500000 |  |  | JANUARY: 1000000; FEBRUARY: 3000000; MARCH: 1500000
29 | Road and Stormwater | 11 | Matswi Street Paving | 4600000 |  |  | JANUARY: 1000000; FEBRUARY: 2600000; MARCH: 1000000
29 | Road and Stormwater | 27 | Access road to Mokwakwaila Taxi Rank | 3100000 |  |  | APRIL: 1000000; MAY: 1100000; JUNE: 1000000
29 | Road and Stormwater | 29 | Modjadjiskloof Gabions | 1000000 |  |  | JUNE: 1000000
29 | Road and Stormwater | 29 | Upgrading of Hill and Kerk Streets | 2800000 |  |  | APRIL: 500000; MAY: 1800000; JUNE: 500000
29 | Road and Stormwater | 3,4 | Ga-Kgapane Sidewalks | 2500000 |  |  | APRIL: 500000; MAY: 1500000; JUNE: 500000
34 | Vehicle licencing and testing | 29 | Traffic Bakkie | 250000 |  |  | MARCH: 250000
34 | Vehicle licencing and testing | 29 | Traffic Sedan | 250000 |  |  | MARCH: 250000
34 | Vehicle licencing and testing | 29 | Stop Watches (6) | 5000 |  |  | MARCH: 5000
34 | Vehicle licencing and testing | 29 | Road marking machine | 150000 |  |  | MARCH: 150000
52 | Electricity Distribution | 29 | Maximum demand metering | 1200000 |  |  | MARCH: 1200000
52 | Electricity Distribution | 29 | Upgrading electricty network to NER standard | 1200000 |  |  | JUNE: 1200000
52 | Electricity Distribution | 29 | Electricity Bakkie | 300000 |  |  | MARCH: 300000
29 | Road and Stormwater | 12 | Thakgalang Street Paving | 5400000 |  |  | JANUARY: 1000000; FEBRUARY: 3000000; MARCH: 1400000
29 | Road and Stormwater | 8 | Rapitsi Street Paving | 1800000 |  |  | FEBRUARY: 1000000; MARCH: 800000
29 | Road and Stormwater | 10 | Sekgopo Street Paving | 2700000 |  |  | FEBRUARY: 1000000; MARCH: 1700000
29 | Road and Stormwater | 8 | Mandela Park Street Paving | 3600000 |  |  | JANUARY: 1000000; FEBRUARY: 1600000; MARCH: 1000000
29 | Road and Stormwater | 1 | Modjadji Headkraal Street Paving | 4900000 |  |  | JANUARY: 1000000; FEBRUARY: 2900000; MARCH: 1000000
29 | Road and Stormwater | 3,4 | Ga-Kgapane Streets Upgrading | 500000 |  |  | MARCH: 500000
29 | Road and Stormwater | 13 | Senwamokgope Streets Upgrading | 500000 |  |  | MARCH: 500000
29 | Road and Stormwater | 2,6,7 | Modjadji Valley Streets Upgrading | 400000 |  |  | MARCH: 400000
29 | Road and Stormwater | 26 | Kuranta Street Paving | 400000 |  |  | MARCH: 400000
29 | Road and Stormwater | 29 | Mokgoba Street Paving | 400000 |  |  | MARCH: 400000
29 | Road and Stormwater | 26 | Ratjeke Street Paving | 400000 |  |  | MARCH: 400000
29 | Community Facilities | 20 | Maphalle Market Stalls | 500000 |  |  | MARCH: 500000
29 | Community Facilities | 13 | Senwamokgope Library | 250000 |  |  | MARCH: 250000
29 | Community Facilities | 9,10 | Sekgopo Library | 250000 |  |  | MARCH: 250000
29 | Community Facilities | 4 | Ga-Kgapane Stadium | 1000000 |  |  | MAY: 600000; JUNE: 400000
29 | Community Facilities | 19 | Lebaka Sports Complex | 9320000 |  |  | MARCH: 2000000; APRIL: 3000000; MAY: 3000000; JUNE: 1320000
29 | Community Facilities | 10 | Sekgopo Sports complex | 12020000 |  |  | MARCH: 3000000; APRIL: 4000000; MAY: 4000000; JUNE: 1020000
29 | Community Facilities | 25 | Shaamiriri Sports Complex | 7890000 |  |  | MARCH: 2000000; APRIL: 2890000; MAY: 2000000; JUNE: 1000000
29 | Electricity Distribution | 29 | Electricity Master Plan | 844800 |  |  | JUNE: 844800
22 | Planning and Development | Various | Purchasing of land | 12000000 |  |  | MARCH: 12000000
22 | Local Economic Development | 29 | Paving at Tourism Information Centre | 250000 |  |  | JUNE: 250000
22 | Local Economic Development | 21 | GLM Show Ground | 1000000 |  |  | JANUARY: 300000; FEBRUARY: 400000; MARCH: 300000
50 | Asset Management | 29 | Small Bakkie | 400000 |  |  | MARCH: 400000
50 | Asset Management | 29 | Sedan | 200000 |  |  | MARCH: 200000
50 | Office furnisher | 29 | Printers (2) - Salary Section & Revenue Section | 400000 |  |  | MARCH: 400000
40 | Furniture and Equipments | 29 | Recording System/ Video Camera | 20000 |  |  | MARCH: 20000
40 | Furniture and Equipments | 29 | Council Vehicles | 600000 |  |  | MARCH: 600000
54 | Property Services | 29 | Decoration of Council Chamber (Including the foyer and podium) | 1505000 |  |  | MARCH: 1505000

## Approval
Approval of Mayor
| G H MODJADJI | DATE